## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2024-09-09
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.
2 | T&M Support | Time and Material ad hoc support, capped at 30 hours per month | In Progress | Contract End Date | 2024-09-30 | Open Box met with Jaic to discuss renewal options. Shaun followed up on 9 Sep to see which option Grainger would like to move forward with. Grainger confirmed nothing needs to be done in relation to the PO for this contractual period taking the additional hours into account. | Grainger to confirm contract renewal option.
3 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2024-12-31 | Sprint 3 deployed to UAT on 9 Sept. | Grainger to complete UAT by 13 Sep.
4 | Renewals - Consultancy | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | In Progress | Consultancy Complete | 2024-10-15 | Workshops completed: - Renewals #1: 22 Jul - Renewals #2: 24 Jul - Prop Man & Resi Services #1: 29 Jul - Asset Management #1: 30 Jul - Accounts Receivable - Credit Control #1: 31 Jul - Complaints Process #1: 06 Aug - Accounts Receivable - Credit Control # 2: 08 Aug - Renewals Team #3: 16 Aug | Workshops Scheduled: - Demo of MRI Evolution: Complaints Functionality, Work Orders, PVIs (Complaints Process #2): 10 Sep - Customer Lifetime Value: 16 Sep - Lettings: Review Price Book, viewing feedback & high-level lettings process: 12 Sep - Finance: Qube: 18 Sep - Qube-GREP Integration: 23 Sep Shaun to schedule Consultancy Close Out Meeting to present findings.
5 | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | SOW in Review | Tentative Project Start Date | 2024-10-01 | Updated SOW delivered on 29 Jul. Yvonne started to collate annual leave and availability of the working group. Open Box is able to begin analysis ahead of the project proposed start date. | Yvonne to follow up with Anish to confirm that the POC Open Box is working on has no impact on the existing SOW costs. Grainger to review the SOW and provide feedback of approval. Confirm priority / timings with Right to Rent and Commercial Lead to Lease
6 | Commercial Property Leasing Journey | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | SOW Signed | Tentative Project Start Date | 2024-11-01 | SOW Signed. Jira board created. | Shaun to work with Yvonne to confirm when we can start Sprint 0
7 | Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | SOW Signed | Consultancy Complete | 2024-09-30 | SOW Signed. Jira board created. Kick-off call scheduled | Schedule workshops
8
| General | Code freeze at end of Financial Year (30 Sep). Understand this will not impact any work we are doing on Salesforce (support or projects). Yvonne to confirm
Risks/Issues
| Personnel Notes | Sam is in UK. Confirmed dates are 16 - 20 Sep
Note on B73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AP: Include the forecast hours if known. This allows visibility into where we expect to finish as we progress with the T&M time.

## Drop Down Menus (hidden)
Status | MileStone
Awaiting Feedback | Analysis Complete
Analysis | Consultancy Complete
Build | Build Complete
UAT | UAT Complete
Production | Production Support
Cancelled | Production Support Complete
Completed | Project Closed
Delayed | Contract End Date
Scheduled | Tentative Project Start Date
SOW Signed
SOW Agreed in Principle
SOW in Review