## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2024-10-17
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | T&M Support | Time and Material ad hoc support, capped at 40 hours per month | In Progress | Contract End Date | 2024-03-31 | Progressing well, nothing to note.
2 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2024-12-31 | Sprint 4 deployed to production on 14 Oct. | Sprint 5 will be deployed to UAT on 1 Nov. Open Box to draft new contract for 2025. Yvonne & Jon touching base to confirm what the next step is Grainger to consider 'working group' people and see if there is a need to expand this / prioritise better across the business
3 | Renewals - Consultancy | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | Delayed | Consultancy Complete | 2024-10-31 | Workshop Scheduled: - Qube-Salesforce Data Model Alignment (Fri 18 Oct) Open Box is looking to deliver a high level Exec Presentation (include costs & timelines) as well as a Project Proposal with the detail.
4 | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | On Hold | Tentative Project Start Date | 2025-01-13 | It has been decided to put this project on hold to enable further understanding around the data being collected through interim inspections and then how this can be pushed into Power BI for better customer insight. This will allow Grainger Trust to consider next steps and how Salesforce can be used to offer efficiencies rather than developing the Grainger Trust journey for capturing of data. | Grainger to provide further detail once known.
5 | Grainger Trust - New opportunity | Meeting on Tuesday 22 Oct to get a high level understanding of what is needed. | Scheduled | Project Intro Session | 2024-10-22 | Grainger are looking to collate an Opportunity Outline Document for inclusion and review at the next Business Optimisation Forum which is scheduled for 24th October Looking to for input from Open Box as to the ‘art of the possible’ around timeline and cost etc would be great to include within that document.
6 | Commercial Lead to Lease | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | Scheduled | Project Start Date | 2024-11-04 | 2 "Sprint 0" sessions have been scheduled per week.
7 | Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | Completed | Sprint 0 | 2024-09-30 | Sprint 0 completed. Open Box working with Grainger to assess if the scope can be reduced for the initial phase of the project. | Open Box spearate requirements into: 1. Foundational 2. Release 1 3. Backlog
8
| General | Document Ingester POC demo scheduled for Wed 23 Oct Business Optimization Forum - 24 Oct. Is Grainger able to provide some clarity on Scotts responsibilities in his new role as 'Technology Transformation Director'.
| Risks/Issues | Renewals Consultancy timelines. Right to Rent Project (Costs and timelines). There is a low probability that Commercial Lead to Lease may be impacted by delays in Renewals and Right to Rent.
| Personnel Notes | December Leave

## Completed Projects
Completed Projects
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps
| GDPR Anonymisation CC1 | Additional functionality to accommodate 2 scenarios that were not included in the initial release: 1. Contacts / Leads are added to new opps during the “Communication Opt in Window” 2. Converted Leads that never made it to Closed Won Opportunities are not being anonymised | Production | Project Closed | 2024-09-23 | Deployed to Production on 23 Sep | Project Retro on 2 Oct with Grainger and Open Box to review lessons learnt.
| GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.

## Drop Down Menus (hidden)
Status | MileStone
In Progress | Analysis Complete
Awaiting Feedback | Consultancy Complete
Analysis | Build Complete
Build | UAT Complete
UAT | Production Support
Production | Production Support Complete
Cancelled | Project Closed
Completed | Contract End Date
Delayed | Tentative Project Start Date
Scheduled | Project Start Date
SOW Signed | Sprint 0
SOW Agreed in Principle
SOW in Review
On Hold
At Risk