## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2024-11-07
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | T&M Support | Time and Material ad hoc support, capped at 40 hours per month | In Progress | Contract End Date | 2024-03-31 | Progressing well, nothing to note.
2 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2024-12-31 | Sprint 5 deployed to PROD on 11 Nov. | Sprint 6 will be deployed to Prod on 9 December, UAT next week Grainger to consider 'working group' people and see if there is a need to expand this / prioritise better across the business 6m extension agreed. Shaun to send SOW to Grainger to get admin done before Christmas
3 | Renewals - Consultancy | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | Delayed | Consultancy Complete | 2024-10-31 | Consultancy complete & Proposal delivered. Open Box working with Grainger to assess the delivery approach. | Open Box to update SoW to frame the releases as 'Foundation' and 'Renewals Journey'. To be reviewed by Grainger Need to discuss potential build start dates Due to cost, CEO needs to have visibility of the project. Jon to put paper together. Open Box to consider early start. Formality to have sign-off
4 | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | On Hold | Tentative Project Start Date | 2025-01-13 | Open Box provided revised scope and costs on 29 Oct | Grainger to review and provide feedback
6 | Commercial Lead to Lease | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | In Progress | Sprint 0 | 2024-11-04 | Sprint 0 started - first session was on 04 Nov. All sessions have been scheduled Open Box have a number of stories scoped for Sprint 1 | Ongoing sessions to scope solution as part of Sprint 0. Jaic looking at intergration/Qube work incase this needs to be factored in. Potential for further questions from Grainger post Refinement sessions, fresh ideas and what could the solution look like
7 | Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | Build | Sprint 1 | 2024-12-02 | Sprint 1 underway, UAT next week. Sprint Demo scheduled for Monday 2nd Decemeber | Grainger to review and provide feedback. Open Box to provide an updated SOW with the proposed solution.
8 | LeadPro Replacement with Form Assembly |  | Build | Sprint 1 | 2024-12-06 | Timeline extended for development by 1 week to allow more time for depencies to be resolved. No cost implication, same level of effort | Grainger to update with Form Assembly implementation and Hosting location
9 | T&M Marketing Cloud Investigation |  |  |  | 2024-12-02 | Investigations due to start on 2nd December to identify issues and extent of the issues. This is needed before any advancement on Touchpoint Surveys can be made | Open Box to send SOW regarding Investingation of Marketing Cloud Connection issues.
| General | Review of the Grainger project roadmap for 2025 with Scott has been moved to a later date, dates to be confirmed with Grainger. Specific Individual Functionality Improvements: EoT phase 2 - Grainger following up internally to see where this is and what the next steps are.
Risks/Issues
| Personnel Notes | Shaun on leave from 26 - 29 Nov (he will miss the next Program Management meeting and meeting with Scott to discuss the Projects Roadmap) Open Box team leave shared with Yvonne - See leave Tab

## Completed Projects
Completed Projects
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps
| GDPR Anonymisation CC1 | Additional functionality to accommodate 2 scenarios that were not included in the initial release: 1. Contacts / Leads are added to new opps during the “Communication Opt in Window” 2. Converted Leads that never made it to Closed Won Opportunities are not being anonymised | Production | Project Closed | 2024-09-23 | Deployed to Production on 23 Sep | Project Retro on 2 Oct with Grainger and Open Box to review lessons learnt.
| GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.

## Drop Down Menus (hidden)
Status | MileStone
In Progress | Analysis Complete
Awaiting Feedback | Consultancy Complete
Analysis | Build Complete
Build | UAT Complete
UAT | Production Support
Production | Production Support Complete
Cancelled | Project Closed
Completed | Contract End Date
Delayed | Tentative Project Start Date
Scheduled | Project Start Date
SOW Signed | Sprint 0
SOW Agreed in Principle
SOW in Review
On Hold
At Risk