## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2025-01-22
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | T&M Support | Time and Material ad hoc support, capped at 40 hours per month | In Progress | Contract End Date | 2024-03-31 | It is reassuring to see that support items are on the decline | Open Box to initiate renewal discussions in February
2 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2025-06-30 | 2025 SOW for 6 months was delivered to Grainger on Dec 18. Next 3 sprints planned for 'mini projects' - a specific set of grouped functionality to have a better sense of consistency. Updated meetings for sprint review/preview/office hours/uat prep | Grainger to approve the SOW Jacob to send Yvonne monthly sprint updates to aid in communicating changes to the business.
3 | Renewals | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | Delayed | Consultancy Complete | 2024-10-31 | Verbal approval has been received. Awaiting signed SOW | Open Box would like to start development on Monday 27 Jan as it is the last week before Nikki goes on leave. Open Box is willing to take this on at risk if the SOW has not been signed. Open Box meeting with Cluster on Friday 24th Jan
4 | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | On Hold | Tentative Project Start Date | 2025-02-17 | Grainger met last Friday to refine requirements and determine what is needed. | Grainger Trust team is meeting end of this week to review the newly created user stories Grainger created. Would like to get this compeleted this financial year (end of Sep)
6 | Commercial Lead to Lease | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | In Progress | Build Complete | 2025-02-21 | Sprint 1 UAT started on Monday 20 Jan and end Fri 31 Jan
7 | Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | UAT | UAT Complete | 2025-01-31 | UAT Started Monday 20th | Open Box meeting internally to discuss cut over plan 27 Jan UAT check-in scheduled for 27 Jan Prod deployment scheduled for 03 Feb
8 | LeadPro Replacement with Form Assembly |  | UAT | UAT Complete | 2025-01-28 | All UAT completed | Awaiting go/no-go decision from Grainger before we deploy to production.
9 | T&M Marketing Cloud Investigation |  | In Progress | SOW Delivered | 2025-01-23 | Investigation feedback given via call to Alistair, Andy, Jaic, Jenny, Robert and Jenny. | Open Box to prepare SOW for Jenny to cover the rebuild of touchpoint survey process leveraging FormAssembly to a) fix the issues with the current process and b) give additional functionality being asked for by Jenny. The SOW will also include a strategy to reload the historical touchpoint survey data into Salesforce to allow accurate reporting.
| General | We are looking to deliver the Touchpoint Survey SOW today. Sam is chatting to Robert Anderson this week to see how Open Box can support Grainger in managing Marketing Cloud. OwnBackup: We understand that this has been installed and as a result do not feel it is necessary to continue with the manual backups for GDPR.
Risks/Issues
| Personnel Notes | Nikki is on leave from 03 - 19 Feb

## Completed Projects
Completed Projects
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps
| GDPR Anonymisation CC1 | Additional functionality to accommodate 2 scenarios that were not included in the initial release: 1. Contacts / Leads are added to new opps during the “Communication Opt in Window” 2. Converted Leads that never made it to Closed Won Opportunities are not being anonymised | Production | Project Closed | 2024-09-23 | Deployed to Production on 23 Sep | Project Retro on 2 Oct with Grainger and Open Box to review lessons learnt.
| GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.

## Drop Down Menus (hidden)
Status | MileStone
In Progress | Analysis Complete
Awaiting Feedback | Consultancy Complete
Analysis | Build Complete
Build | UAT Complete
UAT | Production Support
Production | Production Support Complete
Cancelled | Project Closed
Completed | Contract End Date
Delayed | Tentative Project Start Date
Scheduled | Project Start Date
SOW Signed | Sprint 0
SOW Agreed in Principle
SOW in Review
On Hold
At Risk