## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2025-06-26
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | T&M Support | Time and Material ad hoc support, capped at 40 hours per month | In Progress | Contract End Date | 2025-09-30 | Work effort has been reduced this month to accommodate last months overrun. | Closing out the Marketing Cloud enhancement
2 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2025-09-30 | Renewal confirmed for 3 months. Changes are being made in SIT which is impacting our deployment process. | Confirm CAB ticket ownership/who completes it - was meant to be on hold until end of CJR
3 | SVOT & Tenancy Review | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | Build | Build Complete | 2025-08-01 | Sprint 6 UAT: 21 Jul - 1 Aug Sprint 7 SIT Testing: 5 Aug - 6 Aug Sprint 7 UAT: 7 Aug - 22 Aug Prod Deployment: Weekend of 30 Aug Go-Live: 1 Sep | Open Box to send over draft Steerco presentation. Demo will form a big part of this meeting and the messaging around that.
4 | On the Market Integration | This project will allow Grainger Salesforce to initiate listings and delisting of units on OTM directly from within Salesforce. It will also allow prospective tenant details submitted to OTM to be captured as Leads in Salesforce so that the Lettings team can then follow the existing qualification and conversion process | Build | UAT Complete | 2025-07-25 | SIT Testing complete Deployed to UAT on 23 Jul | Grainger to complete UAT and approve Production deployment for 28 Jul
Opportunities
NA | Rent Collection & Arrears Management | Moving our arrears management / rent collection processes fully into Salesforce |  | Tentative Project Start Date | 2026-01-01 | Open Box delivered the Consultancy SOW (180 - 250 hours) on 17 June Aiming to starts: - Consultancy asap (dependent on Grainger availability). This is not needed for budgeting purposes for the Build phase - Project in 2026 FY (from Oct) | Grainger to provide feedback / approval on the Consultancy SOW. Not likely to happen this financial year
NA | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio |  | Tentative Project Start Date | 2026-03-01 | Grainger is busy consolidating the last of the requirements. Grainger is planning to re-engage with Open Box towards the end of June/July. | Jan to March 2026
NA | End of Tenancy Phase 2 | Enhancing the existing EoT process to include other task templates for different property types, as well as adding functionality related to deposits, and different levels of work |  | Tentative Project Start Date | 2026-02-01 | Open Box delivered high level costs on 25 June | Grainger working on requirements. Will revert with the requirements End Aug Q1 - Q2: Oct to March
NA | Start of Tenancy "Move-In" | Develop the inverse of the EoT process so that Operations teams have a streamlined (and not on excel) way to manage the compliance and works related to a tenant moving into a new home |  | Tentative Project Start Date | 2026-10-01 |  | Potential overlap with End of Tenancy Phase 2 2027 fin year
NA | Commercial Lead to Lease - Migration | Data migration of existing Commercial Leases into Salesforce (Commercial Tenancies/Opportunities) |  | Tentative Project Start Date | 2026-05-01 | Further enhancements being requested through CAB to improve process | Keep on the backlog and drop the priority
NA | Complaints CRM |  |  | Tentative Project Start Date | 2025-10-01 | Providing high level costs next week | Q1
NA | Replace MRI Evolution |  |  | Tentative Project Start Date | 2026-10-01 | Agreed to move into "rolling licenses" so no urgency around that. Grainger looking at other options in the meantime | 2027 (Oct 2026)
NA | New Lets | How can we make the New Let process more efficient |  | Tentative Project Start Date |  | Met with Jon on 3 June to discuss this at a high level and to provide our feedback | Merge into Start of Tenanct Project
NA | Lead management | How can we revamp the Lead management process |  | Tentative Project Start Date | 2025-11-01 | Very high level costing given to Jon verbally for inclusion in budget | Q1
NA | Renters Rights changes to Tenancy Review | Final changes required for Tenancy Review process to make it RRB compliant |  | Tentative Project Start Date | 2026-01-01 | Indicative cost and timeline to be provided to Jon today (24th July) | Q1/Q2
NA | Anti-Social behaviour |  |  | Tentative Project Start Date | 2026-02-01 |  | Q1/Q2
NA | Pet Registration & Management Process |  |  | Tentative Project Start Date | 2026-04-01 |  | Q1/Q2
Renters Rights
| General | Marketing Cloud SMS Entitlement & Usage Sam and Jacob are attending Proptech Connect in the UK in early Sept
Risks/Issues
| Personnel Notes | Leave: - Yvonne: 29 Jul - 18 Aug - Jon: 1 Aug - 18 Aug

## Completed Projects
Completed Projects
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps
| GDPR Anonymisation CC1 | Additional functionality to accommodate 2 scenarios that were not included in the initial release: 1. Contacts / Leads are added to new opps during the “Communication Opt in Window” 2. Converted Leads that never made it to Closed Won Opportunities are not being anonymised | Production | Project Closed | 2024-09-23 | Deployed to Production on 23 Sep | Project Retro on 2 Oct with Grainger and Open Box to review lessons learnt.
| GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.
7 | Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | Production | Production Support Complete | 2025-02-17 | Project Closed | Project Review on Thu 20 Feb
8 | LeadPro Replacement with Form Assembly |  | Production | Production Support Complete | 2025-02-17 | Project Closed
6 | Commercial Lead to Lease | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | Completed | Project Closed | 2025-05-28 | Project Completed. Some project backlog items already being worked on in BAU. Consideraiton for other items to take place in the future to identify complexity and priority of backlog items.

## Drop Down Menus (hidden)
Status | MileStone
In Progress | Analysis Complete
Awaiting Feedback | Consultancy Complete
Analysis | Build Complete
Build | UAT Complete
UAT | Production Support
Production | Production Support Complete
Cancelled | Project Closed
Completed | Contract End Date
Delayed | Tentative Project Start Date
Scheduled | Project Start Date
SOW Signed | Sprint 0
SOW Agreed in Principle
SOW in Review
On Hold
At Risk