Project Management Review Summary – Grainger PLC

| Project | End of Tenancy |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 08th – 15th Nov 2023 |  |  |  |
| Status Overview | Sprint 3: UAT Sprint 4: Build |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Feedback on Sprint 4 items |  | - 10th Nov | - Grainger |
|  | - Sprint 3 Demo |  | - 10th Nov | - Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Sprint 3 UAT Feedback | - 17th Nov | - Grainger | - WIP |
|  | - Go-Live Preparation | - WIP | - Grainger | - Change Management, Training, Support |
|  | - End-to-End UAT | - 4th Dec | - Grainger | - Completed by 15th Dec |
|  | - Steerco #2 | - 5th Dec | - Grainger / Open Box | - Date to be confirmed |
|  | - Go-Live | - January 2024 | - Grainger / Open Box | - Date to be confirmed |
| Discussions/Risks /Issues | 271 story points are currently allocated to the project. The initial backlog was 185 story points. Planning for support beyond post go-live hypercare (e.g. Open Box 0.5 FTE) |  |  |  |
| Personnel Notes | Jacob on leave in December. Open Box will be taking extended leave over December. |  |  |  |

Sprint Metrics

Dashboard can be located here

Initial Backlog

| Summary | Issue key | Story Points |
| --- | --- | --- |
| Calculate void duration | FVVP-197 |  |
| See Tasks for a Void | FVVP-190 | 8 |
| View / Update Task Details | FVVP-189 | 3 |
| Replace Internal Notification Emails | FVVP-132 | 2 |
| Reporting - See Teams with High Number of Tasks | FVVP-127 | 1 |
| Dashboard - See Active Voids Behind Schedule | FVVP-125 | 2 |
| Property Calendar - See Onsite Void Tasks | FVVP-117 | 1 |
| Detailed Tasks - Close Down Tenancy | FVVP-116 | 2 |
| Detailed Tasks - Deposit Release | FVVP-115 | 2 |
| Detailed Tasks - Finalize Check Out | FVVP-114 | 2 |
| Detailed Tasks - Review Check Out | FVVP-113 | 2 |
| Detailed Tasks - Check Property Condition | FVVP-112 | 2 |
| Detailed Tasks - Check Out | FVVP-111 | 2 |
| Detailed Tasks - Book Works | FVVP-110 | 2 |
| Detailed Tasks - Cancel Direct Debit | FVVP-109 | 2 |
| Detailed Tasks - Check Compliance | FVVP-108 | 2 |
| Detailed Tasks - Notify Stakeholders | FVVP-107 | 2 |
| Detailed Tasks - Validate Required Information is Captured | FVVP-106 | 2 |
| Detailed Tasks - Confirm Notice | FVVP-105 | 2 |
| Detailed Tasks - Validate Notice | FVVP-104 | 2 |
| See Active Voids for a Building | FVVP-101 | 1 |
| See History of Voids on a Unit | FVVP-100 | 1 |
| See Void & Task Audit History | FVVP-99 | 1 |
| Upload Void Documents | FVVP-98 | 1 |
| See Unit View Arrangements & Key Location | FVVP-97 | 2 |
| Update Salesforce Unit - Keep Available Date Up-to-Date | FVVP-96 | 2 |
| Update Salesforce Unit - Keep FV Date Up-to-Date | FVVP-95 | 2 |
| Update Salesforce Unit - Keep Unit Status Up-to-Date | FVVP-94 | 5 |
| Update Salesforce Unit - New Void | FVVP-92 | 5 |
| See Estimated Available Date & Void Completion Date | FVVP-90 | 5 |
| Create a Void with Refurb / Refresh / Clean Only-Specific Tasks | FVVP-89 | 5 |
| Update Relet Status - Update Tasks | FVVP-87 | 5 |
| Create a Void with Relet Tasks | FVVP-86 | 5 |
| Dashboard - See New Voids Confirmed for Sale | FVVP-85 | 1 |
| New Void - Default Unit Sale Status from Salesforce | FVVP-84 | 1 |
| Dashboard - Other KPIs for R1 | FVVP-82 | 10 |
| Dashboard - See Open Tasks | FVVP-80 | 2 |
| Cancel a Void | FVVP-78 | 1 |
| Close a Void | FVVP-77 | 3 |
| See Summary of Void Phases & % Completion | FVVP-76 | 3 |
| Complete Voids are Read-Only | FVVP-75 |  |
| Dashboard - KPI: Vacant Days | FVVP-72 |  |
| Complete a Phase | FVVP-71 | 5 |
| Update Timelines - Tasks Dependent on a Void Date | FVVP-66 | 8 |
| Update Void Works Type - Update Tasks | FVVP-65 |  |
| Update Timelines - Tasks Dependent on Completion of Prior Tasks | FVVP-64 | 13 |
| Detailed Tasks - PVI | FVVP-63 |  |
| Rename "Void" Terminology | FVVP-62 |  |
| Set Tasks to Not Applicable [Close] | FVVP-61 | 1 |
| Capture a Reason for Updating Key Void Information | FVVP-59 | 3 |
| New End of Tenancy - Capture End of Tenancy Details | FVVP-58 | 3 |
| See Salesforce Unit & Building Attributes in a Void | FVVP-57 | 1 |
| New Void - Calculate Estimated PVI Date | FVVP-56 | 3 |
| Data Migration - Void Queues | FVVP-54 | 3 |
| New End of Tenancy - Assign Tasks to Responsible Queues | FVVP-53 | 5 |
| Calculate Estimated Timelines - Tasks Dependent on Completion of Prior Tasks | FVVP-51 | 13 |
| Calculate Estimated Timelines - Tasks Tied to an EOT Date | FVVP-50 | 5 |
| New End of Tenancy - Generate Phases & Tasks from a Template | FVVP-49 | 13 |
| New End of Tenancy - Create an End of Tenancy | FVVP-48 | 5 |
|  |  | 185 |

Historical Reports

| Project | End of Tenancy |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 2nd – 08th Nov 2023 |  |  |  |
| Status Overview | Sprint 3: Build |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Change Management Plan Discussion |  | - 1st Nov | - Grainger / Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Feedback on Sprint 4 items | - 10th Nov | - Grainger | - On Track |
|  | - Sprint 3 Demo | - 10th Nov | - Open Box | - On Track |
|  | - Sprint 3 UAT Feedback | - 17th Nov | - Grainger | - 1 week from 10th Nov |
|  | - Go-Live Preparation | - WIP | - Grainger | - Change Management, Training, Support |
|  | - End-to-End UAT | - 4th Dec | - Grainger | - Completed by 15th Dec |
|  | - Go-Live | - January 2024 | - Grainger / Open Box | - On Track |
| Discussions/Risks /Issues | 251 story points are currently allocated to the project. The initial backlog was 185 story points. Sprint 4 is likely to have fewer user stories (points) due to the progress made in sprints 1,2 & 3. We are also reserving some capacity to handle feedback from Sprint 3 & regression test the timeline calculations. |  |  |  |
| Personnel Notes | Open Box will be taking extended leave over December. |  |  |  |

| Project | End of Tenancy |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 25th Oct – 2 Nov 2023 |  |  |  |
| Status Overview | Sprint 3: Build |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Reporting feedback ahead of the Mon refinement session |  | - 27th Oct | - Grainger |
|  | - Sprint 2 UAT feedback |  | - 27th Oct | - Grainger |
|  | - Call to discuss change management strategy |  | - 2nd Nov | - Open Box |
|  | - Steerco Presentation |  | - 2nd Nov | - Grainger / Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Sprint 3 Demo | - 10th Nov | - Open Box | - On Track |
|  | - Sprint 3 UAT | - 17th Nov | - Grainger | - 1 week from 10th Nov |
|  | - Change Management Plan | - TBC | - Grainger | - Open Box to assist Grainger in determining feasible change management process |
| Discussions/Risks /Issues | 242 story points are currently allocated to the project. The initial backlog was 185 story points. Sprint 4 is likely to have fewer user stories (points) due to the progress made in sprints 1,2 & 3. We are also reserving some capacity to handle feedback from Sprint 3. Planning required for January ‘24 go-live, training and support. |  |  |  |
| Personnel Notes | None |  |  |  |

| Project | End of Tenancy - Implementation |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 3rd – 10th Oct |  |  |  |
| Status Overview | Sprint 2: Build |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Sprint 1 UAT |  | - 6th Oct | - Grainger |
|  | - New QA/UAT environment (Staging) refreshed from Prod |  | - 9th Oct | - Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Incorporate additional user stories in Sprint 2 | - 13th Oct | - Open Box | - On Track |
|  | - Sprint 2 UAT (in Staging) | - 23rd Oct | - Grainger | - 1 week in duration - Sprint 1 UAT bugs will also be made available for retest |
| Discussions/Risks /Issues | 128 story points currently allocated to sprint 1 & 2. Initial backlog was 185 story points. |  |  |  |
| Personnel Notes | Shaun out next week. |  |  |  |

| Project | End of Tenancy - Implementation |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 27th Sep – 3rd Oct |  |  |  |
| Status Overview | Sprint 1: UAT Sprint 2: Build |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Sprint 1 Demo |  | - 2nd Oct | - Grainger / Open Box |
|  | - Refinement |  | - 3rd Oct | - Grainger / Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Sprint 1 UAT | - 6th Oct | - Grainger | - On Track |
| Discussions/Risks /Issues | Open Box will work with Grainger to see what additional user stories can be brought into sprint 2. |  |  |  |
| Personnel Notes | Sam travelling Thu and Fri this week. |  |  |  |

| Project | End of Tenancy - Implementation |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 20th – 27th Sep |  |  |  |
| Status Overview | Sprint 1 in progress |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Realignment on User Stories for Sprint 1 |  | - 22nd Sep | - Open Box |
|  | - Onboarding of new Open Box team members |  | - 22nd Sep | - Grainger / Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Sprint 1 Demo | - 2nd Oct | - Grainger / Open Box | - Rescheduled to align with Sam’s visit |
|  | - Refinement | - 3rd Oct | - Grainger / Open Box | - Rescheduled to align with Sam’s visit |
|  | - Sprint 1 UAT | - 2nd Oct | - Grainger | - 1 week |
| Discussions/Risks /Issues | As mentioned in our sprint ceremonies, sprint 1 required a lot of foundational work / effort. As a result, some user stories may roll over to sprint 2. This is not anticipated to have an impact on project cost or timelines. |  |  |  |
| Personnel Notes | Sam will be in the Grainger office from Oct 2nd. |  |  |  |

| Project | End of Tenancy - Implementation |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 5th – 20th Sep |  |  |  |
| Status Overview | Sprint 1 in progress |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Project kick-off meeting |  | - 5th Sep | - Grainger / Open Box |
|  | - Confirmation of sprint ceremonies |  | - 9th Sep | - Grainger / Open Box |
|  | - Confirmation of Purchase Order |  | - 8th Sep | - Grainger |
|  | - Fine-tuning Jira |  | - 14th Sep | - Grainger / Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Sprint 1 Demo | - 2nd Oct | - Grainger / Open Box | - Rescheduled to align with Sam’s visit |
|  | - Refinement | - 3rd Oct | - Grainger / Open Box | - Rescheduled to align with Sam’s visit |
|  | - Sprint 1 UAT | - 2nd Oct | - Grainger | - 1 week |
| Discussions/Risks /Issues | Open Box is reviewing items in sprint 1 & 2 to ensure dependencies will not impact our velocity. This will result in some cards moving between sprint 1 & 2. |  |  |  |
| Personnel Notes | Holiday in South Africa on Monday 25th September |  |  |  |