Project Management Review Summary – Grainger PLC

| Project | Rent Smart Wales |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 1st – 12th Dec 2023 |  |  |  |
| Status Overview | Project on hold. |  |  |  |
| Progress in the last week | Item |  | Completed | Responsible |
|  | Approval of additional effort / extended timelines |  | 1st Dec | Grainger |
|  | RSW-25 Approval |  | 30th Nov | Grainger / Open Box |
|  | Provide updated wording for emails (& any other documents) that need to be updated for Opportunities |  | 3rd Nov | Grainger |
|  | Confirm list of Special Clauses for Occupation Contracts |  | 11th Dec | Grainger |
|  | Updated all email templates with final versions |  | 12th Dec | Open Box |
| Upcoming deliverables / feedback required | Item | Due | Responsible | Status |
|  | Provide Occupation Contract Template | 3rd Nov | Grainger | Project on hold until these are received |
|  | Provide updated draft tenancy document | 3rd Nov | Grainger | Project on hold until these are received |
|  | Demo | 28th Nov | Grainger / Open Box | Delayed |
|  | UAT | 29th Nov | Grainger | Delayed |
|  | Prod Deployment | 15 Jan | Open Box | Will be delayed |
| Discussions/Risks /Issues | - The project is on hold until all the final templates have been received. |  |  |  |
| Personnel Notes | - Jacob on leave from 15th December. - Open Box will be taking extended leave over December. |  |  |  |

Initial Backlog

| # | Priority | User Story |
| --- | --- | --- |
| 1 | Must Have | As a TPT User, I want to generate an Occupation Contract from an Opportunity for a Welsh property, So that the document can be sent out to be signed |
| 2 | Must Have | As a TPT User, I want to send an occupation Contract to all Contract Holders, So that they can sign the document online. |
| 3 | Must Have | As a Lettings User, I want the Agreement Type to be occupation Contract for all opportunities in Wales, So that an incorrect document cannot be sent |
| 4 | Must Have | As a Grainger User, I want any communication sent to an opportunity for a Welsh property to have the correct Welsh terminology, So we adhere to Rent Smart Wales legislation |
| 5 | Must Have | As a Grainger User, I want any communication sent to an account that is currently living in a Welsh property to have the correct Welsh terminology, So we adhere to Rent Smart Wales legislation |
| 9 | Must Have | As a Grainger User, I want any communications sent to a lead that is for a Welsh property to have the correct Welsh terminology, So we adhere to Rent Smart Wales legislation |

Historical Reports

| Project | Rent Smart Wales |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 22nd – 29th Nov 2023 |  |  |  |
| Status Overview | Project on hold. |  |  |  |
| Progress in the last week | Item |  | Completed | Responsible |
|  | Additional effort / extended timelines communicated to Grainger |  | 28th Nov | Open Box |
| Upcoming deliverables / feedback required | Item | Due | Responsible | Status |
|  | Approval of Additional effort / extended timelines | 1st Dec | Grainger | On Track |
|  | RSW-25 Approval | 30th Nov | Grainger / Open Box | On Track |
|  | Provide updated wording for emails (& any other documents) that need to be updated for Opportunities | 3rd Nov | Grainger | Project on hold until these are received |
|  | Provide Occupation Contract Template | 3rd Nov | Grainger | Project on hold until these are received |
|  | Confirm list of Special Clauses for Occupation Contracts | 3rd Nov | Grainger | Project on hold until these are received |
|  | Demo | 28th Nov | Grainger / Open Box | Delayed |
|  | UAT | 29th Nov | Grainger | Delayed |
|  | Prod Deployment | 15 Jan | Open Box | At risk |
| Discussions/Risks /Issues | - Open Box has completed as much of the development that is possible using dummy templates. The project is on hold until all the final templates have been received. - Implications of putting the project on hold and the subsequent cost was discussed with Grainger. Open Box is awaiting confirmation on how Grainger want to proceed. |  |  |  |
| Personnel Notes | - Jacob on leave from 15th December. - Open Box will be taking extended leave over December. |  |  |  |

| Project | Rent Smart Wales |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 15th – 22nd Nov 2023 |  |  |  |
| Status Overview | Build Started |  |  |  |
| Progress in the last week | Item |  | Completed | Responsible |
|  | Review of Production Deployment dates |  | 21st Nov | Grainger / Open Box |
|  | Confirmation of emails that need to be updated for Opportunities |  | 21st Nov | Grainger |
| Upcoming deliverables / feedback required | Item | Due | Responsible | Status |
|  | Provide updated wording for emails (& any other documents) that need to be updated for Opportunities | 3rd Nov | Grainger | Delayed. Putting UAT dates at risk. |
|  | Provide Occupation Contract Template | 3rd Nov | Grainger | Delayed. Putting UAT dates at risk. |
|  | Confirm list of Special Clauses for Occupation Contracts | 3rd Nov | Grainger | Delayed. Putting UAT dates at risk. |
|  | Demo | 28th Nov | Grainger / Open Box | Will use the RSW Refinement meeting slot. Grainger to confirm who needs to be included. |
|  | UAT | 29th Nov | Grainger | At risk. |
|  | Prod Deployment | 15 Jan | Open Box | Date pushed out as the Qube upgrade takes place in Dec. Do not want changes in the Salesforce environment before the upgrade. |
| Discussions/Risks /Issues | - Open Box are mitigating the risk of delayed document & email templates by: - Assisting Grainger in identifying all required emails by inspecting existing Salesforce configuration and listing all workflows, process builders and flows where emails are sent. - Proceeding with development of the RSW workflows using dummy email templates which will be replaced once final versions are available. |  |  |  |
| Personnel Notes | - Jacob on leave from 15th December. - Open Box will be taking extended leave over December. |  |  |  |

| Project | Rent Smart Wales |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 8th – 15th Nov 2023 |  |  |  |
| Status Overview | Build Started |  |  |  |
| Progress in the last week | Item |  | Completed | Responsible |
|  | Meeting to confirm additional requirements for Tenant Portal. New stories added to backlog. |  | 8th Nov | Open Box |
| Upcoming deliverables / feedback required | Item | Due | Responsible | Status |
|  | Confirmation of emails (& any other documents) that need to be updated for Opportunities | 3rd Nov | Grainger | Delayed |
|  | Provide Occupation Contract Template | 3rd Nov | Grainger | Delayed |
|  | UAT | 29th Nov | Grainger | On Track |
|  | Prod Deployment | 6th Dec | Open Box | Go Live support will be initiated from this date |
| Discussions/Risks /Issues | - Timeline remains unchanged with PROD deployment planned for early December before Jacob goes on leave. - Open Box are mitigating the risk of delayed email templates by: - Assisting Grainger in identifying all required emails by inspecting existing Salesforce configuration and listing all workflows, process builders and flows where emails are sent. - Proceeding with development of the RSW workflows using dummy email templates which will be replaced once final versions are available. |  |  |  |
| Personnel Notes | - Jocob on leave in December. - Open Box will be taking extended leave over December. |  |  |  |

| Project | Rent Smart Wales |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 2nd – 8th Nov 2023 |  |  |  |
| Status Overview | Build Started |  |  |  |
| Progress in the last week | Item |  | Completed | Responsible |
|  | Confirmation of building availability – coming online in Jan 2024 |  | 7th Nov | Grainger |
|  | Salesforce build started |  | 8th Nov | Open Box |
| Upcoming deliverables / feedback required | Item | Due | Responsible | Status |
|  | Confirmation of emails (& any other documents) that need to be updated for Opportunities | 3rd Nov | Grainger | Delayed |
|  | Provide Occupation Contract Template | 3rd Nov | Grainger | Delayed |
|  | UAT | 29th Nov | Grainger | On Track |
|  | Prod Deployment | 6th Dec | Open Box | Go Live support will be initiated from this date |
| Discussions/Risks /Issues | - PC for building has been delayed, but project timeline remains unchanged with PROD deployment planned for early December before Jacob goes on leave. |  |  |  |
| Personnel Notes | - Open Box will be taking extended leave over December. |  |  |  |

| Project | Rent Smart Wales |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 26th Oct – 2nd Nov 2023 |  |  |  |
| Status Overview | Project Approved |  |  |  |
| Progress in the last week | Item |  | Completed | Responsible |
|  | Kick-off call |  | 3rd Nov | Grainger / Open Box |
|  | Sprint ceremonies to be scheduled |  | 2nd Nov | Open Box |
| Upcoming deliverables / feedback required | Item | Due | Responsible | Status |
|  | Confirmation of building availability | ASAP | Grainger | The 5-week project duration needs to be considered when planning for the lease commercials |
|  | Confirmation of emails (& any other documents) that need to be updated | 3rd Nov | Grainger | On Track |
|  | Provide Occupation Contract Template | 3rd Nov | Grainger | On Track |
| Discussions/Risks /Issues | - Risk: - Timing of when the building will become available. If it is available at the earliest communicated date, then there is a risk this project will not be completed in time. Open Box is assessing options to close out this project in the shortest timeframe possible. |  |  |  |
| Personnel Notes | - None |  |  |  |

| Project | Rent Smart Wales |  |  |  |
| --- | --- | --- | --- | --- |
| Period | 26th Oct |  |  |  |
| Status Overview | Project Approved |  |  |  |
| Progress in the last week | Item |  | Completed | Responsible |
|  | SOW Signed |  | 26th Oct | Grainger / Open Box |
|  | Jira project setup |  | 26th Oct | Grainger |
| Upcoming deliverables / feedback required | Item | Due | Responsible | Status |
|  | Kick-off call | 3rd Nov | Grainger / Open Box | Open Box to schedule |
| Discussions/Risks /Issues | - None |  |  |  |
| Personnel Notes | - None |  |  |  |