## Pivot
Month | May |  | <- Filter By Month
Sum of Hours | Column Labels |  |  | 2.1 COST
Row Labels | General Support (Billable) | General Support (Non-Billable) | Grand Total | The cost for the services detailed in this document are as follows:
Anjali Salecha | 26.5 |  | 26.5 | 1. Support services will be provided on a Time and Materials (T&M) basis at a rate of
Tafadzwa Toro |  | 7 | 7 | £120 per hour.
Sam Duncan | 1 |  | 1 | a. A minimum amount of £3600 / month will be billed, entitling Grainger PLC
Carami Le Grange |  | 0.75 | 0.75 | to 30 hours of work
Dillan Landsberg | 8.5 | 3.25 | 11.75
Shaun Barrett |  | 3.5 | 3.5 | The contract will begin on 1 April 2024 and end on 30 September 2024
Grand Total | 36 | 14.5 | 50.5
Keeping an eye on Non-Billable
Tickets in comments on PW
Jira Ticket | Status | Assigned To
BSS-13 Flow error message improvement | To Do | Jaic George
BSS-27 Lead tenant validation preventing creation of renewal opps | To Do | Jaic George
BSS-15 Trim the spaces before sending to HomeLet | To Do | Jaic George
BSS-24 Update recipients for Process Automation Settings | To Do | Jaic George
BSS-23 An Error Occurred with Your "Renewals - Send email to OCRs" Flow | To Do | Jaic George
BSS-22 Welsh Occupation Contract validation blocking opportunities for Parking Garages in Cardiff | In Progress | Dillan Landsberg
BSS-4 Agreement not pulling the template with 1 tenant and 2 guarantors | In Progress | Dillan Landsberg
BSS-20 Lead Tenant being sent twice to HomeLet | Client Confirmation (Grainger) | Jaic George
BSS-14 An unhandled fault occurred in this flow | Client Confirmation (Grainger) | Saji Gunasekaran
BSS-16 Unable to send to Homelet | Client Confirmation (Grainger) | Jaic George
BSS-28 Contract Sign Date not displaying | Client Confirmation (Grainger) | Jaic George
BSS-9 HomeLet referencing error showing in this opportunity | Client Confirmation (Grainger) | Jaic George
BSS-17 Guarantor not being sent for referencing | Done | Sam Duncan
BSS-8 Unable to complete task on EOT | Done | Saji Gunasekaran
BSS-21 Re-send guarantor to HomeLet | Done | Jaic George
BSS-19 The Units with status “On the market – no access” are not able to be posted onto Rightmove | Done | Dillan Landsberg
BSS-25 Update UAT Organization-Wide Addresses | Done | Dillan Landsberg

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-03-22 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 227014 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | -- Investigated FVVP 417 and Production bugs | Not submitted | 3 | March
2024-03-26 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 229192 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 238.02 | 58.02 | IN08074 | GBP | Reviewed | Discussion with Sam related to RJ-30 root cause. Likely relationship with fix of RJ-26. Fixed RJ-30 in staging and testing. | Not submitted | 3 | March
2024-03-26 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 228560 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | Worked on FVVP-416 | Not submitted | 3 | March
2024-03-27 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 229334 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | checked if sandbox openbox can be deleted. worked on fixing test class - Renewals_OpportunityCloneTest for RJ-30 in staging | Not submitted | 3 | March
2024-03-27 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 228528 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | kick-off & admin | Not submitted | 3 | March
2024-03-27 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 229177 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | Fixed the production bug FVVP 416 in Staging | Not submitted | 3 | March
2024-03-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 228826 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | pre project prep | Not submitted | 3 | March
2024-03-28 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 229978 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | Troubleshooting RSW ticket: https://graingerplc.atlassian.net/browse/RSW-62 | Not submitted | 3 | March
2024-04-02 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 230412 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Reports | Not submitted | 4 | April
2024-04-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 230872 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-04 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 231490 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Support Process Planning | Not submitted | 4 | April
2024-04-04 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 231333 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | BSS-6 Making change in UAT and deploying to PROD | Not submitted | 4 | April
2024-04-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 231546 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-05 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 231672 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Meeting with Helpdesk | Not submitted | 4 | April
2024-04-05 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 231787 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 231837 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 232801 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | Homelet demo to Dillan Landsberg in uat. | Not submitted | 4 | April
2024-04-08 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 232453 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Process Refinement & Flow diagram drafting | Not submitted | 4 | April
2024-04-08 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 232286 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | BSS-8: Investigating ticket and providing feedback to Saji | Not submitted | 4 | April
2024-04-08 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 232311 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | HomeLet overview with Anjali | Not submitted | 4 | April
2024-04-08 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 232216 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | Updating historical opps for HomeLet go-live https://graingerplc.atlassian.net/browse/BSS-7 | Not submitted | 4 | April
2024-04-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 232524 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-09 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 233077 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Jira changes | Not submitted | 4 | April
2024-04-09 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 232949 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | BSS-8 | Not submitted | 4 | April
2024-04-09 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 232898 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | BSS-9 Investigating and responding to Jaic | Not submitted | 4 | April
2024-04-09 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 233122 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-10 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 233353 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | BSS-11 and BSS-12 investigation and feedback | Not submitted | 4 | April
2024-04-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 233821 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-11 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 234192 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Jira issue type changes | Not submitted | 4 | April
2024-04-11 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 233858 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | BSS-8 Investigation and feedback to Saji | Not submitted | 4 | April
2024-04-11 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 234332 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Chat with Anjali regarding BSS-8 | Not submitted | 4 | April
2024-04-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 234263 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-12 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 234548 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Diagram run through with Melissa | Not submitted | 4 | April
2024-04-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 234430 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-15 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 235384 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 4 | April
2024-04-15 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 235144 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 238.02 | 58.02 | IN08074 | GBP | Reviewed | BSS-8 BSS-3 | Not submitted | 4 | April
2024-04-15 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 235145 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed | BSS-8 | Not submitted | 4 | April
2024-04-15 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 235324 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-16 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 235864 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Signl4 integration | Not submitted | 4 | April
2024-04-16 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 235698 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 208.26 | 50.76 | IN08074 | GBP | Reviewed | BSS-14 investigation & error replication BSS-3: Close ticket | Not submitted | 4 | April
2024-04-16 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 235696 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 3 | 3:00 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-16 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 235992 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-17 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 236594 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP | Reviewed | Flow diagram workings & standup | Not submitted | 4 | April
2024-04-17 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 236100 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.25 | 1:15 | 0 |  |  |  | GBP | Reviewed | Grainger EOT issue Meeting with Sam & Avi | Not submitted | 4 | April
2024-04-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 236701 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-18 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 236896 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 29.75 | 7.25 | IN08074 | GBP | Reviewed | Discussion with Dillan about HomeLet Bug - removing spaces from phone number before sending to Homelet. | Not submitted | 4 | April
2024-04-18 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 236900 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | BSS-15 Call with Anjali Investigation & feedback | Not submitted | 4 | April
2024-04-18 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 236740 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 237125 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 237719 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 29.75 | 7.25 | IN08074 | GBP | Reviewed | Discussion with Dillan about 'ApplicantExistsWithSameEmail' error. | Not submitted | 4 | April
2024-04-19 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 237570 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Diagram changes | Not submitted | 4 | April
2024-04-19 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 237309 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 208.26 | 50.76 | IN08074 | GBP | Reviewed | AVM-16 | Not submitted | 4 | April
2024-04-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 237711 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-22 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 237971 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 178.51 | 43.51 | IN08074 | GBP | Reviewed | Checked the root cause for BSS-16 and discussion with Dillan. | Not submitted | 4 | April
2024-04-22 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 237812 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 89.26 | 21.76 | IN08074 | GBP | Reviewed | BSS-16 call with Anjali | Not submitted | 4 | April
2024-04-22 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 238353 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-23 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 238745 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 89.26 | 21.76 | IN08074 | GBP | Reviewed | AVM-14 Test Case | Not submitted | 4 | April
2024-04-23 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 240660 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | BSS-16 | Not submitted | 4 | April
2024-04-23 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 239022 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-24 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 239365 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 178.51 | 43.51 | IN08074 | GBP | Reviewed | BSS-18 | Not submitted | 4 | April
2024-04-24 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 239576 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-25 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 240111 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 59.5 | 14.5 | IN08074 | GBP | Reviewed | Discussion with Sam about BSS-16. | Not submitted | 4 | April
2024-04-25 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 240672 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | BSS-8 | Not submitted | 4 | April
2024-04-25 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 240339 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-26 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 240088 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 238.02 | 58.02 | IN08074 | GBP | Reviewed | BSS8 call with Sam BSS-19 | Not submitted | 4 | April
2024-04-26 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 240433 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | BSS-8 | Not submitted | 4 | April
2024-04-26 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 240434 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 119.01 | 29.01 | IN08074 | GBP | Reviewed | BSS-16 | Not submitted | 4 | April
2024-04-26 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 240375 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-29 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 241549 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 4 | April
2024-04-29 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 240870 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 178.51 | 43.51 | IN08074 | GBP | Reviewed | HomeLet issue - https://graingerplc.atlassian.net/browse/BSS-16 | Not submitted | 4 | April
2024-04-29 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 241891 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-29 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 241507 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-30 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 241946 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-05-01 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 242573 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 29.75 | 7.25 | IN08074 | GBP | Reviewed | Chat with Jaic about Homelet opps issues. BSS-21 | Not submitted | 5 | May
2024-05-02 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 243530 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 6.25 | 6:15 | 562.5 |  |  |  | GBP | Reviewed | 1. Discussion with Sam and Dillan - HomeLet issue - https://graingerplc.atlassian.net/browse/BSS-16 2. Analysis and debug logs for issue BSS-16 3. Discussion with client - BSS-16 catchup. | Not submitted | 5 | May
2024-05-02 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 242593 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed | BSS-19 | Not submitted | 5 | May
2024-05-03 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 243531 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed | 1. Discussion with Sam 2. Worked on BSS-20 in sit environment. 3. Manual deployment of fixes from uat to sit 4. Testing in uat because of 403 forbidden error. | Not submitted | 5 | May
2024-05-03 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 243054 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 |  |  |  | GBP | Reviewed | BSS-19 BSS - 8 | Not submitted | 5 | May
2024-05-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 243418 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-06 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 243733 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 5 | May
2024-05-06 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 243722 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed | BSS-22 BSS-23 BSS-25 | Not submitted | 5 | May
2024-05-06 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 243723 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed | Grainger catchup with Sam and Anjali | Not submitted | 5 | May
2024-05-06 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 243831 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 244331 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 |  |  |  | GBP | Reviewed | 1. Discussion with Sam. 2. Worked on BSS-20. 3. Prepared data for opps already cloned and Opps not already cloned. 4. Root cause analysis. | Not submitted | 5 | May
2024-05-07 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 243918 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  | BSS-21 and BSS-22 investigation and updates in JIRA | Not submitted | 5 | May
2024-05-07 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 244356 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-07 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 244430 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | BSS-28 Investigation | Not submitted | 5 | May
2024-05-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 244755 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP | Reviewed | Worked on analysing debug logs for BSS-27 | Not submitted | 5 | May
2024-05-08 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 244453 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Process discussion | Not submitted | 5 | May
2024-05-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 244599 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-08 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 244738 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-09 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 245625 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 |  |  |  | GBP |  | Worked on BSS-27. Daily standup . Discussion with Sam. | Not submitted | 5 | May
2024-05-09 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 245372 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | FTE Hours Sync Up | Not submitted | 5 | May
2024-05-09 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 245138 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed | BSS-19 review and deployment with Sam | Not submitted | 5 | May
2024-05-09 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 245137 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.75 | 1:45 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 5 | May
2024-05-09 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 245361 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 5 | May
2024-05-09 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 245768 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP |  | BSS-28 | Not submitted | 5 | May
2024-05-10 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 245907 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed | BSS-22 | Not submitted | 5 | May
2024-05-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 245722 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP |  |  | Not submitted | 5 | May
2024-05-10 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 245776 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP |  |  | Not submitted | 5 | May

## Jira List
15-04-2024
Issue Type | Key | Summary |  | Status | Assignee | Due date | Priority | Labels | Created | Updated | Reporter
Bug | BSS-8 | Unable to complete task on EOT | BSS-8 Unable to complete task on EOT | In Progress | Dillan Landsberg |  | Priority 3 |  | 2024-04-08 | 2024-04-15 | Saji Gunasekaran
Bug | BSS-9 | HomeLet referencing error showing in this opportunity | BSS-9 HomeLet referencing error showing in this opportunity | Awaiting Feedback | Jaic George |  | Priority 3 |  | 2024-04-09 | 2024-04-09 | Jaic George
Bug | BSS-3 | EOT task- Couldn't be cancelled through approver ( record owner) | BSS-3 EOT task- Couldn't be cancelled through approver ( record owner) | Awaiting Feedback | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-11 | 2024-04-09 | Saji Gunasekaran
Bug | BSS-4 | Agreement not pulling the template with 1 tenant and 2 guarantors | BSS-4 Agreement not pulling the template with 1 tenant and 2 guarantors | Awaiting Feedback | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-02-28 | 2024-04-09 | Saji Gunasekaran
Bug | BSS-2 | Receiving an error on every task I try and complete | BSS-2 Receiving an error on every task I try and complete | Done | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-21 | 2024-04-02 | Saji Gunasekaran
Bug | BSS-5 | Security deposit not populated for renewals | BSS-5 Security deposit not populated for renewals | Done | Dillan Landsberg |  | Priority 3 | BAU_SUPPORT | 2024-03-15 | 2024-04-02 | Sam Duncan
Task | BSS-6 | Update the noOfAdultOccupants calculation | BSS-6 Update the noOfAdultOccupants calculation | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-04 | 2024-04-11 | Jaic George
Task | BSS-7 | Update the referencing Provider to HomeLet | BSS-7 Update the referencing Provider to HomeLet | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-08 | 2024-04-11 | Jaic George
22-04-2024
Issue Type | Key | Summary |  | Status | Assignee | Due date | Priority | Labels | Created | Updated | Reporter
Bug | BSS-8 | Unable to complete task on EOT | BSS-8 Unable to complete task on EOT | In Progress | Dillan Landsberg |  | Priority 3 |  | 2024-04-08 | 2024-04-18 | Saji Gunasekaran
Bug | BSS-14 | An unhandled fault occurred in this flow | BSS-14 An unhandled fault occurred in this flow | In Progress | Dillan Landsberg |  | Priority 3 |  | 2024-04-16 | 2024-04-16 | Saji Gunasekaran
Bug | BSS-16 | Unable to send to Homelet | BSS-16 Unable to send to Homelet | Awaiting Feedback (Grainger) | Saji Gunasekaran |  | Priority 3 |  | 2024-04-18 | 2024-04-22 | Jaic George
Bug | BSS-15 | Trim the spaces before sending to HomeLet | BSS-15 Trim the spaces before sending to HomeLet | Awaiting Feedback (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-18 | 2024-04-19 | Jaic George
Bug | BSS-9 | HomeLet referencing error showing in this opportunity | BSS-9 HomeLet referencing error showing in this opportunity | Awaiting Feedback (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-09 | 2024-04-09 | Jaic George
Bug | BSS-4 | Agreement not pulling the template with 1 tenant and 2 guarantors | BSS-4 Agreement not pulling the template with 1 tenant and 2 guarantors | Awaiting Feedback (Grainger) | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-02-28 | 2024-04-09 | Saji Gunasekaran
Bug | BSS-2 | Receiving an error on every task I try and complete | BSS-2 Receiving an error on every task I try and complete | Done | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-21 | 2024-04-02 | Saji Gunasekaran
Bug | BSS-5 | Security deposit not populated for renewals | BSS-5 Security deposit not populated for renewals | Done | Dillan Landsberg |  | Priority 3 | BAU_SUPPORT | 2024-03-15 | 2024-04-02 | Sam Duncan
Task | BSS-6 | Update the noOfAdultOccupants calculation | BSS-6 Update the noOfAdultOccupants calculation | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-04 | 2024-04-11 | Jaic George
Task | BSS-7 | Update the referencing Provider to HomeLet | BSS-7 Update the referencing Provider to HomeLet | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-08 | 2024-04-11 | Jaic George
Bug | BSS-3 | EOT task- Couldn't be cancelled through approver ( record owner) | BSS-3 EOT task- Couldn't be cancelled through approver ( record owner) | Done | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-11 | 2024-04-22 | Saji Gunasekaran
Story | BSS-13 | Flow error message improvement | BSS-13 Flow error message improvement | To Do | Dillan Landsberg |  | Priority 3 | Technical | 2024-04-15 | 2024-04-15 | Dillan Landsberg
29-04-2024
Issue Type | Key | Summary |  | Status | Assignee | Due date | Priority | Labels | Created | Updated | Reporter
Bug | BSS-16 | Unable to send to Homelet | BSS-16 Unable to send to Homelet | In Progress | Anjali Salecha |  | Priority 3 |  | 2024-04-18 | 2024-04-26 | Jaic George
Bug | BSS-19 | The Units with status “On the market – no access” are not able to be posted onto Rightmove | BSS-19 The Units with status “On the market – no access” are not able to be posted onto Rightmove | In Progress | Sam Duncan |  | Priority 3 |  | 2024-04-26 | 2024-04-26 | Jaic George
Bug | BSS-14 | An unhandled fault occurred in this flow | BSS-14 An unhandled fault occurred in this flow | Awaiting Feedback (Grainger) | Saji Gunasekaran |  | Priority 3 |  | 2024-04-16 | 2024-04-26 | Saji Gunasekaran
Bug | BSS-8 | Unable to complete task on EOT | BSS-8 Unable to complete task on EOT | Awaiting Feedback (Grainger) | Saji Gunasekaran |  | Priority 3 |  | 2024-04-08 | 2024-04-26 | Saji Gunasekaran
Bug | BSS-18 | Limit Exceeded Error while trying to update a Unit via Salesforce connector | BSS-18 Limit Exceeded Error while trying to update a Unit via Salesforce connector | Done | Jaic George |  | Priority 3 |  | 2024-04-24 | 2024-04-29 | Jaic George
Bug | BSS-17 | Guarantor not being sent for referencing | BSS-17 Guarantor not being sent for referencing | Client Confirmation (Grainger) | Sam Duncan |  | Priority 3 |  | 2024-04-23 | 2024-04-29 | Sam Duncan
Bug | BSS-15 | Trim the spaces before sending to HomeLet | BSS-15 Trim the spaces before sending to HomeLet | Awaiting Feedback (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-18 | 2024-04-19 | Jaic George
Bug | BSS-9 | HomeLet referencing error showing in this opportunity | BSS-9 HomeLet referencing error showing in this opportunity | Awaiting Feedback (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-09 | 2024-04-09 | Jaic George
Bug | BSS-4 | Agreement not pulling the template with 1 tenant and 2 guarantors | BSS-4 Agreement not pulling the template with 1 tenant and 2 guarantors | Awaiting Feedback (Grainger) | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-02-28 | 2024-04-09 | Saji Gunasekaran
Story | BSS-13 | Flow error message improvement | BSS-13 Flow error message improvement | To Do | Dillan Landsberg |  | Priority 3 | Technical | 2024-04-15 | 2024-04-15 | Dillan Landsberg
Bug | BSS-2 | Receiving an error on every task I try and complete | BSS-2 Receiving an error on every task I try and complete | Done | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-21 | 2024-04-02 | Saji Gunasekaran
Bug | BSS-5 | Security deposit not populated for renewals | BSS-5 Security deposit not populated for renewals | Done | Dillan Landsberg |  | Priority 3 | BAU_SUPPORT | 2024-03-15 | 2024-04-02 | Sam Duncan
Task | BSS-7 | Update the referencing Provider to HomeLet | BSS-7 Update the referencing Provider to HomeLet | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-08 | 2024-04-11 | Jaic George
Task | BSS-6 | Update the noOfAdultOccupants calculation | BSS-6 Update the noOfAdultOccupants calculation | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-04 | 2024-04-23 | Jaic George
Bug | BSS-3 | EOT task- Couldn't be cancelled through approver ( record owner) | BSS-3 EOT task- Couldn't be cancelled through approver ( record owner) | Done | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-11 | 2024-04-22 | Saji Gunasekaran
06-05-2024
Issue Type | Key | Summary |  | Status | Assignee | Due date | Priority | Labels | Created | Updated | Reporter
Bug | BSS-22 | An Error Occurred with Your "Opportunity Contact Role PB Handler" Flow | BSS-22 An Error Occurred with Your "Opportunity Contact Role PB Handler" Flow | To Do | Dillan Landsberg |  | Priority 3 | Bug | 2024-05-06 | 2024-05-06 | Dillan Landsberg
Bug | BSS-23 | An Error Occurred with Your "Renewals - Send email to OCRs" Flow | BSS-23 An Error Occurred with Your "Renewals - Send email to OCRs" Flow | To Do | Dillan Landsberg |  | Priority 3 | Bug | 2024-05-06 | 2024-05-06 | Dillan Landsberg
Story | BSS-13 | Flow error message improvement | BSS-13 Flow error message improvement | To Do | Dillan Landsberg |  | Priority 3 | Technical | 2024-04-15 | 2024-04-15 | Dillan Landsberg
Bug | BSS-15 | Trim the spaces before sending to HomeLet | BSS-15 Trim the spaces before sending to HomeLet | Awaiting Feedback (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-18 | 2024-04-29 | Jaic George
Bug | BSS-9 | HomeLet referencing error showing in this opportunity | BSS-9 HomeLet referencing error showing in this opportunity | Awaiting Feedback (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-09 | 2024-04-29 | Jaic George
Bug | BSS-4 | Agreement not pulling the template with 1 tenant and 2 guarantors | BSS-4 Agreement not pulling the template with 1 tenant and 2 guarantors | Awaiting Feedback (Grainger) | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-02-28 | 2024-04-29 | Saji Gunasekaran
Bug | BSS-20 | Lead Tenant being sent twice to HomeLet | BSS-20 Lead Tenant being sent twice to HomeLet | Client Confirmation (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-29 | 2024-05-06 | Sam Duncan
Bug | BSS-19 | The Units with status “On the market – no access” are not able to be posted onto Rightmove | BSS-19 The Units with status “On the market – no access” are not able to be posted onto Rightmove | Client Confirmation (Grainger) | Jacob Smycz |  | Priority 3 |  | 2024-04-26 | 2024-05-06 | Jaic George
Bug | BSS-8 | Unable to complete task on EOT | BSS-8 Unable to complete task on EOT | Client Confirmation (Grainger) | Saji Gunasekaran |  | Priority 3 |  | 2024-04-08 | 2024-05-06 | Saji Gunasekaran
Bug | BSS-14 | An unhandled fault occurred in this flow | BSS-14 An unhandled fault occurred in this flow | Client Confirmation (Grainger) | Saji Gunasekaran |  | Priority 3 |  | 2024-04-16 | 2024-04-29 | Saji Gunasekaran
Bug | BSS-16 | Unable to send to Homelet | BSS-16 Unable to send to Homelet | Client Confirmation (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-18 | 2024-05-06 | Jaic George
Bug | BSS-17 | Guarantor not being sent for referencing | BSS-17 Guarantor not being sent for referencing | Done | Sam Duncan |  | Priority 3 |  | 2024-04-23 | 2024-04-30 | Sam Duncan
Bug | BSS-21 | Re-send guarantor to HomeLet | BSS-21 Re-send guarantor to HomeLet | Done | Jaic George |  | Priority 3 |  | 2024-05-01 | 2024-05-06 | Sam Duncan
Bug | BSS-2 | Receiving an error on every task I try and complete | BSS-2 Receiving an error on every task I try and complete | Done | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-21 | 2024-04-02 | Saji Gunasekaran
Bug | BSS-5 | Security deposit not populated for renewals | BSS-5 Security deposit not populated for renewals | Done | Dillan Landsberg |  | Priority 3 | BAU_SUPPORT | 2024-03-15 | 2024-04-02 | Sam Duncan
Task | BSS-7 | Update the referencing Provider to HomeLet | BSS-7 Update the referencing Provider to HomeLet | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-08 | 2024-04-11 | Jaic George
Task | BSS-6 | Update the noOfAdultOccupants calculation | BSS-6 Update the noOfAdultOccupants calculation | Done | Sam Duncan |  | Priority 3 | BAU_SUPPORT | 2024-04-04 | 2024-04-23 | Jaic George
Bug | BSS-3 | EOT task- Couldn't be cancelled through approver ( record owner) | BSS-3 EOT task- Couldn't be cancelled through approver ( record owner) | Done | Saji Gunasekaran |  | Priority 3 | BAU_SUPPORT | 2024-03-11 | 2024-04-22 | Saji Gunasekaran
Bug | BSS-18 | Limit Exceeded Error while trying to update a Unit via Salesforce connector | BSS-18 Limit Exceeded Error while trying to update a Unit via Salesforce connector | Done | Jaic George |  | Priority 3 |  | 2024-04-24 | 2024-04-29 | Jaic George
13-05-2024
Issue Type | Key | Summary |  | Status | Assignee | Due date | Priority | Labels | Created | Updated | Reporter
Story | BSS-13 | Flow error message improvement | BSS-13 Flow error message improvement | To Do | Jaic George |  | Priority 3 | Technical | 2024-04-15 | 2024-05-13 | Dillan Landsberg
Bug | BSS-27 | Lead tenant validation preventing creation of renewal opps | BSS-27 Lead tenant validation preventing creation of renewal opps | To Do | Jaic George |  | Priority 1 |  | 2024-05-07 | 2024-05-10 | Sam Duncan
Bug | BSS-15 | Trim the spaces before sending to HomeLet | BSS-15 Trim the spaces before sending to HomeLet | To Do | Jaic George |  | Priority 3 |  | 2024-04-18 | 2024-05-13 | Jaic george
Story | BSS-24 | Update recipients for Process Automation Settings | BSS-24 Update recipients for Process Automation Settings | To Do | Jaic George |  | Priority 3 |  | 2024-05-06 | 2024-05-13 | Dillan Landsberg
Bug | BSS-23 | An Error Occurred with Your "Renewals - Send email to OCRs" Flow | BSS-23 An Error Occurred with Your "Renewals - Send email to OCRs" Flow | To Do | Jaic George |  | Holding Place | Bug | 2024-05-06 | 2024-05-13 | Dillan Landsberg
Bug | BSS-22 | Welsh Occupation Contract validation blocking opportunities for Parking Garages in Cardiff | BSS-22 Welsh Occupation Contract validation blocking opportunities for Parking Garages in Cardiff | In Progress | Dillan Landsberg |  | Priority 1 | Bug | 2024-05-06 | 2024-05-10 | Dillan Landsberg
Bug | BSS-4 | Agreement not pulling the template with 1 tenant and 2 guarantors | BSS-4 Agreement not pulling the template with 1 tenant and 2 guarantors | In Progress | Dillan Landsberg |  | Priority 3 | BAU_SUPPORT | 2024-02-28 | 2024-05-13 | SAJI GUNASEKARAN
Bug | BSS-20 | Lead Tenant being sent twice to HomeLet | BSS-20 Lead Tenant being sent twice to HomeLet | Client Confirmation (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-29 | 2024-05-13 | Sam Duncan
Bug | BSS-14 | An unhandled fault occurred in this flow | BSS-14 An unhandled fault occurred in this flow | Client Confirmation (Grainger) | Saji Gunasekaran |  | Priority 3 |  | 2024-04-16 | 2024-04-29 | SAJI GUNASEKARAN
Bug | BSS-16 | Unable to send to Homelet | BSS-16 Unable to send to Homelet | Client Confirmation (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-18 | 2024-05-06 | Jaic george
Bug | BSS-28 | Contract Sign Date not displaying | BSS-28 Contract Sign Date not displaying | Client Confirmation (Grainger) | Jaic George |  | Priority 1 |  | 2024-05-07 | 2024-05-13 | Jaic george
Bug | BSS-9 | HomeLet referencing error showing in this opportunity | BSS-9 HomeLet referencing error showing in this opportunity | Client Confirmation (Grainger) | Jaic George |  | Priority 3 |  | 2024-04-09 | 2024-05-13 | Jaic george
Bug | BSS-17 | Guarantor not being sent for referencing | BSS-17 Guarantor not being sent for referencing | Done | Sam Duncan |  | Priority 3 |  | 2024-04-23 | 2024-04-30 | Sam Duncan
Bug | BSS-8 | Unable to complete task on EOT | BSS-8 Unable to complete task on EOT | Done | Saji Gunasekaran |  | Priority 3 |  | 2024-04-08 | 2024-05-13 | SAJI GUNASEKARAN
Bug | BSS-21 | Re-send guarantor to HomeLet | BSS-21 Re-send guarantor to HomeLet | Done | Jaic George |  | Priority 3 |  | 2024-05-01 | 2024-05-06 | Sam Duncan
Bug | BSS-19 | The Units with status “On the market – no access” are not able to be posted onto Rightmove | BSS-19 The Units with status “On the market – no access” are not able to be posted onto Rightmove | Done | Dillan Landsberg |  | Priority 3 |  | 2024-04-26 | 2024-05-09 | Jaic george
Story | BSS-25 | Update UAT Organization-Wide Addresses | BSS-25 Update UAT Organization-Wide Addresses | Done | Dillan Landsberg |  | Priority 3 |  | 2024-05-06 | 2024-05-09 | Dillan Landsberg