## Pivot
Month | (All) |  | <- Filter By Month
Sum of Hours | Column Labels |  |  | Phase | Hours | Lower Bound | Upper Bound
Row Labels | Delivery (Billable) | Grand Total |  | Analysis | 60 - 78 | £7,200 | £9,360
Nikki Papenfus | 31.25 | 31.25 |  | Build | 200 - 260 | £24,000 | £31,200
Sam Duncan | 6.5 | 6.5 |  | Project Management | 12 - 15.6 | £1,440 | £1,872
Shaun Barrett | 1.75 | 1.75 |  | UAT | 40 - 52 | £4,800 | £6,240
Anjali Salecha | 38 | 38 |  | Production | 5 - 6.5 | £600 | £780
Khonani Davhana | 1.75 | 1.75 |  | Total | 317 - 412 | £38,040 | £49,452
Tafadzwa Toro | 4 | 4
Grand Total | 83.25 | 83.25

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-04-01 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 230625 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Daily standup with Nikki. Workedon RMAXIS-196 Calculate when 'Axis Fields Last Modified' so that we can inform Axis of changes to relevant EOT details. worked on RMAXIS-196 in devxas deployed to devxob and tested. Prepared questions to discuss with Sam and Nikki | Not submitted | 4 | April
2024-04-02 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 230627 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Worked on RMAXIS-185 in devxob. Daily standup. Meeting with client - Grainger: Axis Void Management Refinement. Understanding and analysis of requirements for RMAXIS-180 | Not submitted | 4 | April
2024-04-03 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 231180 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Daily standup. Worked on RMAXIS-181 RMAXIS-180. Test class for RMAXIS-196. | Not submitted | 4 | April
2024-04-04 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 231179 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Daily standup. Discussion with Sam about new sandbox setup. Questions on stories. Worked on RMAXIS-180. Testing. Worked on moving stories from devxob sadnbox to new dev sandbox called grainger.dev. Refinement session. | Not submitted | 4 | April
2024-04-05 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232187 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP |  | Daily standup. Worked on AVM-18. Could not complete AVM-18 due to other dependant stories. Worked on AVM-6. Researched about using time fields in flow. | Not submitted | 4 | April
2024-04-03 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231087 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-04 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231086 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-05 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231762 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-03-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 220377 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 210 | 52.5 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 222480 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 223599 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-25 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 227600 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 228789 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 540 | 135 | IN07963 | GBP | Reviewed | .. | Not submitted | 3 | March
2024-03-28 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 229677 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 | 300 | 75 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-04-01 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 230320 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 230323 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-03 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 230327 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 231189 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 231856 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-03-06 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 222230 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 180 | 45 | IN07963 | GBP | Reviewed | User story review & discussion | Not submitted | 3 | March
2024-03-11 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 223051 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07963 | GBP | Reviewed | Requirments gathering session with Jaic Jacob Scott | Not submitted | 3 | March
2024-04-02 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231445 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP |  | Daily standup (15 mins) Refinement session (2 hours) | Not submitted | 4 | April
2024-04-03 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231463 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  | Daily standup (15 mins) | Not submitted | 4 | April
2024-04-04 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231462 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP |  | Refinement session (1 hour) Daily standup (15 mins) | Not submitted | 4 | April
2024-04-05 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231464 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  | Daily standup (15 mins) | Not submitted | 4 | April
2024-03-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 228823 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07963 | GBP | Reviewed | stand up | Not submitted | 3 | March
2024-04-02 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230406 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230870 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231545 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231550 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-02 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232225 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP |  | Refinement Stand Up | Not submitted | 4 | April
2024-04-03 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232229 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-04 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232231 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP |  | Refinement Stand Up | Not submitted | 4 | April
2024-04-05 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232236 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 4 | April