## Pivot
Month | (All) |  | <- Filter By Month
Billable Timecode | Billable timecode
|  |  |  | Phase | Hours | Lower Bound | Upper Bound
Sum of Hours | Column Labels |  |  | Analysis | 8 - 10 | £960 | £1,200
Row Labels | Build | Grand Total |  | Build | 40 - 48 | £4,800 | £5,760
Sam Duncan | 3 | 3 |  | Project Management | 4 - 5 | £480 | £600
Anjali Salecha | 13.5 | 13.5 |  | UAT | 8 - 10 | £960 | £1,200
Grand Total | 16.5 | 16.5 |  | Production | 5 - 6.5 | £600 | £780
|  |  |  | Total | 65 - 80 | £7,800 | £9,540

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-05-22 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 250098 | Build | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | 1. Daily standup. 2. Analysing stories 3. Understanding existing code in github 4. Discussion with Sam. | Not submitted | 5 | May
2024-05-23 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 251587 | Build | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP |  | GA-3 Worked on setting up fieldsets and other new fields and prefixed github code with 'GDPR_' | Not submitted | 5 | May
2024-05-24 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 251329 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP |  | GDPR Anonymisation - Refinement Session (OpenBox) | Not submitted | 5 | May
2024-05-27 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 251984 | Build | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 |  |  |  | GBP |  | 1. Worked on GA-3. New fields on Contact Account and Lead. Prepared list of changes. | Not submitted | 5 | May
2024-05-20 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 249451 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP |  | Grainger GDPR kick-off & Jira check | Not submitted | 5 | May
2024-05-24 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251387 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP |  | refinement | Not submitted | 5 | May
2024-05-20 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 249510 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP |  |  | Not submitted | 5 | May
2024-05-21 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 249509 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  |  | Not submitted | 5 | May
2024-05-22 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 250689 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  |  | Not submitted | 5 | May
2024-05-23 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 250690 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  |  | Not submitted | 5 | May
2024-05-24 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251355 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP |  |  | Not submitted | 5 | May
2024-05-20 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251755 | Build | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP |  | Implementation approach | Not submitted | 5 | May
2024-05-24 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000654 | GDPR Anonymisation | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 251770 | Build | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  | Refinement session | Not submitted | 5 | May