## Pivot
Month | (All) |  | <- Filter By Month | Project Phases | Duration | Lower Bound | Upper Bound
Billable Timecode | Billable timecode |  |  | Sprint 0 | 2-3 weeks | £6,000 | £9,000
|  |  |  | Sprint 1 - 2 | 3-6 weeks | £23,400 | £46,800
Sum of Hours | Column Labels |  |  | UAT | 2 weeks | £3,600 | £3,600
Row Labels | Delivery | Grand Total |  | Production Deployment & Post Go-Live Support | 2 weeks | £3,600 | £3,600
Sam Duncan | 1 | 1 |  | User guide creation | Done in parallel with sprints | £3,150 | £3,150
Nikki Papenfus | 30.5 | 30.5
Grand Total | 31.5 | 31.5 |  | Total | 9 -13 weeks | £39,750 | £66,150

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-09-10 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 295597 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Kick off Meeting | Not submitted | 9 | September
2024-09-12 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 296751 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-20 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 300039 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP |  |  | Not submitted | 9 | September
2024-09-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 295307 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 295796 | Delivery | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 296231 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 296762 | Delivery | Billable timecode | Standard Timecode | 90 | 4.75 | 4:45 | 427.5 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 297337 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-16 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 298126 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-17 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 298527 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-18 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 299113 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-19 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 299601 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 300229 | Delivery | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 |  |  |  | GBP |  |  | Not submitted | 9 | September
2024-09-10 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 297512 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed | Kickoff call | Not submitted | 9 | September
2024-09-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 295853 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.25 | 1:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 295852 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 297013 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 297291 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-16 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 298099 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 298904 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 299339 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 299694 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 300199 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  |  | Not submitted | 9 | September