## Pivot
Sprint 0
Month | (All) |  | <- Filter By Month
Billable Timecode | Billable timecode
Sum of Hours | Column Labels
Row Labels | Delivery | Grand Total
Sam Duncan | 4 | 4
Nikki Papenfus | 56.5 | 56.5
Grand Total | 60.5 | 60.5
Delivery
Month | (All)
Billable Timecode | (All)
Sum of Hours | Column Labels |  |  |  | Project Phases | Duration | Lower Bound | Upper Bound
Row Labels | Delivery (Non-Billable) | Delivery | Sprint 0 Overrun | Grand Total | Sprint 0 | 2-3 weeks | £6,000 | £9,000
Shaun Barrett | 3.75 |  | 7.25 | 11 | Sprint 1 - 2 | 3-6 weeks | £23,400 | £46,800
Jacob Smycz | 3.25 |  |  | 3.25 | UAT | 2 weeks | £3,600 | £3,600
Khonani Davhana |  | 3.5 |  | 3.5 | Production Deployment & Post Go-Live Support | 2 weeks | £3,600 | £3,600
Nikki Papenfus |  |  | 12.5 | 12.5 | User guide creation | Done in parallel with sprints | £3,150 | £3,150
Tafadzwa Toro | 3.25 |  |  | 3.25
Sam Duncan |  |  | 1.75 | 1.75 | Total | 9 -13 weeks | £39,750 | £66,150
Grand Total | 10.25 | 3.5 | 21.5 | 35.25

## Delivery Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-10-08 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 307718 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-09 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 307733 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-10 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 308431 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.75 | 1:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 307946 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-09 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 307945 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-10 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 308690 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 305483 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-07 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 306897 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 4.75 | 4:45 | 427.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 307499 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 308468 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 309119 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-14 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 309509 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 310138 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-16 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 310630 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 10 | October
2024-10-17 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 311051 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 10 | October
2024-10-18 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 311593 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 10 | October
2024-10-21 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Delivery | 312097 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 10 | October
2024-10-10 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 309488 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 |  |  |  | GBP | Reviewed | Story point estimation (1h45) | Not submitted | 10 | October
2024-10-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 306050 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 306049 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-07 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 307310 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 308256 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-09 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 308257 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 308255 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 309015 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-14 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 309675 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-15 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 310185 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-16 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 310850 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 10 | October
2024-10-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 311171 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 10 | October
2024-10-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Delivery | 312545 | Sprint 0 Overrun | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  |  | Not submitted | 10 | October
2024-10-08 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 309053 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-09 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 309060 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Estimation | Not submitted | 10 | October
2024-10-10 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000726 | Right to Rent - Delivery (FC) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Delivery | 309066 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.75 | 1:45 | 0 |  |  |  | GBP | Reviewed | Estimation | Not submitted | 10 | October

## Sprint 0 Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-09-23 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 300856 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 9 | September
2024-09-30 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 304593 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | time report | Not submitted | 9 | September
2024-10-07 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 307189 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 10 | October
2024-10-14 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 309575 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 10 | October
2024-09-10 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 295597 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Kick off Meeting | Not submitted | 9 | September
2024-09-12 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 296751 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-20 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 300039 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-26 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 301819 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-10-01 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 305367 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-03 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 305842 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-08 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 307716 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-10 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 308436 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-09-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 295307 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 | 337.5 | 135 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 295796 | Delivery | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 | 187.5 | 75 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 296231 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 37.5 | 15 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 296762 | Delivery | Billable timecode | Standard Timecode | 90 | 4.75 | 4:45 | 427.5 | 712.5 | 285 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 297337 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 300 | 120 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-16 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 298126 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 37.5 | 15 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-17 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 298527 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 450 | 180 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-18 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 299113 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 | 600 | 240 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-19 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 299601 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 1050 | 420 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 300229 | Delivery | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 | 862.5 | 345 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-23 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 300824 | Delivery | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 750 | 300 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-24 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 301042 | Delivery | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 675 | 270 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-26 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 302000 | Delivery | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 | 525 | 210 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 302531 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 150 | 60 | IN08605 | GBP | Reviewed |  | Not submitted | 9 | September
2024-10-01 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 305286 | Delivery | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-03 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 305978 | Delivery | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 306903 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 309544 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-08 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 308703 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Project Intro | Not submitted | 10 | October
2024-10-09 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 308706 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Sprint Estimation | Not submitted | 10 | October
2024-10-10 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 308714 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed | Right to Rent Estimation #2 | Not submitted | 10 | October
2024-09-10 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 297512 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 150 | 60 | IN08605 | GBP | Reviewed | Kickoff call | Not submitted | 9 | September
2024-09-23 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 302552 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08605 | GBP | Reviewed | Design session with Nikki | Not submitted | 9 | September
2024-09-24 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 302555 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08605 | GBP | Reviewed | Design session with Nikki | Not submitted | 9 | September
2024-10-02 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 306787 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed | Brainstorm with Nikki (1 hour) | Not submitted | 10 | October
2024-10-07 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 309475 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed | Internal kickoff (30 mins) Final alignment (1 hour | Not submitted | 10 | October
2024-10-15 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 312316 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  | Scoping session with Nikki | Not submitted | 10 | October
2024-09-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 295853 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.25 | 1:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 295852 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 297013 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 297291 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-16 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 298099 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 298904 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 299339 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 299694 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 300199 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-10-01 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 305631 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-02 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 305633 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 306041 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-10-07 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000720 | Right to Rent - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 307311 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October