## Pivot
Sprint 0 |  |  |  |  | Project Phases | Duration | Lower Bound | Upper Bound | Lower Bound | Upper Bound
[5 empty] | Sprint 0 | 4-5 weeks | 80 | 120 | 12000 | 18000
Month | (All) |  | <- Filter By Month
Billable Timecode | Billable timecode
Sum of Hours | Column Labels
Row Labels | Delivery | Grand Total
Nikki Papenfus | 115.75 | 115.75 |  |  | Total | 4-5 weeks |  |  | 12000 | 18000
Sam Duncan | 8 | 8
Grand Total | 123.75 | 123.75
Delivery
Month | (All)
Billable Timecode | (All)
Sum of Hours | Column Labels
Row Labels | Delivery (Non-Billable) | Delivery | Sprint 0 Overrun | Grand Total
Shaun Barrett | 3.75 |  | 7.25 | 11
Jacob Smycz | 3.25 |  |  | 3.25
Khonani Davhana |  | 3.5 |  | 3.5
Nikki Papenfus |  |  | 12.5 | 12.5
Tafadzwa Toro | 3.25 |  |  | 3.25
Sam Duncan |  |  | 1.75 | 1.75
Grand Total | 10.25 | 3.5 | 21.5 | 35.25

## Sprint 0 Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-11-11 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 321638 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time report | Not submitted | 11 | November
2024-11-18 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 324722 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | time report | Not submitted | 11 | November
2024-11-25 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 327721 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 11 | November
2024-12-02 | Carami Viljoen | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 330799 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | time report | Not submitted | 12 | December
2024-11-04 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 318682 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 319648 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 321304 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 322607 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-13 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 322601 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 324564 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2.25 | 2:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 325531 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 326175 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 327415 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.75 | 1:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-27 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 328707 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Jacob Smycz | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Sam Duncan | Sprint 0 | 331407 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-11-01 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 318298 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 2.5 | 2:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 318619 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 | 337.5 | 135 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 319087 | Delivery | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 | 375 | 150 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 319663 | Delivery | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 225 | 90 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-07 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 320173 | Delivery | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 675 | 270 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 320704 | Delivery | Billable timecode | Standard Timecode | 90 | 7.25 | 7:15 | 652.5 | 1087.5 | 435 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 321468 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 | 600 | 240 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 322040 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 1050 | 420 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 322573 | Delivery | Billable timecode | Standard Timecode | 90 | 6.5 | 6:30 | 585 | 975 | 390 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-14 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 323022 | Delivery | Billable timecode | Standard Timecode | 90 | 4.25 | 4:15 | 382.5 | 637.5 | 255 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 323759 | Delivery | Billable timecode | Standard Timecode | 90 | 5.5 | 5:30 | 495 | 825 | 330 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 324526 | Delivery | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 750 | 300 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-19 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 325122 | Delivery | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 | 562.5 | 225 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 325597 | Delivery | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 | 1125 | 450 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 326108 | Delivery | Billable timecode | Standard Timecode | 90 | 7.25 | 7:15 | 652.5 | 1087.5 | 435 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-22 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 326754 | Delivery | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 675 | 270 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 327557 | Delivery | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 | 412.5 | 165 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-26 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 328066 | Delivery | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 750 | 300 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 328571 | Delivery | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 | 1125 | 450 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 330752 | Delivery | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-03 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 331283 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 331280 | Delivery | Billable timecode | Standard Timecode | 90 | 5.5 | 5:30 | 495 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 331947 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 332839 | Delivery | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 333066 | Delivery | Billable timecode | Standard Timecode | 90 | 5.5 | 5:30 | 495 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 333900 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan | Andrew Pollock | Sprint 0 | 333895 | Delivery | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-11-04 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323698 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323711 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323726 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 150 | 60 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323737 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed | Qube discussion | Not submitted | 11 | November
2024-11-13 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323739 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328859 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 300 | 120 | IN08887 | GBP | Reviewed | Internal refinement with Nikki (1 hour) External refinement session (1 hour) | Not submitted | 11 | November
2024-11-21 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328860 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 150 | 60 | IN08887 | GBP | Reviewed | Internal refinement with Nikki (1 hour) | Not submitted | 11 | November
2024-11-25 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328889 | Delivery | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 225 | 90 | IN08887 | GBP | Reviewed | Refinement with Nikki (1 hour) Refinement with Grainger (30 mins) | Not submitted | 11 | November
2024-11-27 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 328898 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 75 | 30 | IN08887 | GBP | Reviewed | Refinement session (30 mins) | Not submitted | 11 | November
2024-09-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 302333 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-09-30 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 304735 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 9 | September
2024-10-30 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 316721 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 10 | October
2024-11-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 318740 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 319240 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-06 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 319825 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-07 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 320319 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 320320 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 321660 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 322196 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 322738 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-14 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323217 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-15 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 323869 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 324582 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 325824 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-21 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 326248 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-22 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 327241 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-11-25 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 327234 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 11 | November
2024-12-02 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 331080 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 331090 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 331742 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP |  |  | Not submitted | 12 | December
2024-12-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000721 | Commercial Lead to Lease - Sprint 0 (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Sam Duncan |  | Sprint 0 | 332081 | Delivery (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP |  |  | Not submitted | 12 | December