## Slide 1
Sprint Review: SVOT & Renewals
Sprint 3
31 Mar – 25 Apr

## Slide 2
Sprint Overview
Work Items Delivered
Story Points Completed
Weeks
38
77,75
4
Sprint Numbers
Work Items To Still Test
Sprint work Items Delivered
Sprint Links
Update ”Grainger Testing” to “Yes” to confirm the work item has delivered the functionality detailed in the Acceptance Criteria
UAT Items Addressed
9
Dashboard Overview
Sprint 3 UAT Testing
Release 1 Go Live
Sprint 3 SIT Testing
28 Apr – 02 May
Key Dates
Sprint 2 UAT Testing
12 May – 23 May
07 Apr – 02 May
12 May

## Slide 3
Work Items Delivered

## Slide 4
Work Items Planned for Next Sprint

## Slide 5
General Items
Risk | Contributing factors | Impact | Decisions taken
New scope is being added | New insight from the Grainger team as to what is needed | To be determined | For discussion in the Program Management Review session
Issue | Contributing factors | Impact | Decisions taken
None |  |  | 
Items Carried over to next Sprint | Reasons
UAT Feedback Items | UAT was extended by an additional week, UAT feedback was received late in the last week of this sprint.
Decision | Description | Date

## Slide 6: Thank You