## Slide 1
Sprint Review: Salesforce BAU
Sprint 13
16 June – 14 July

## Slide 2
Sprint Overview
Work Items Delivered
Story Points Completed
Weeks
22
4
Sprint Numbers
Sprint work Items Delivered
Sprint Links
UAT Items Addressed
0
Enhancement Testing
BAU Go Live
Payment Apportionment Testing
14 July – 25 July
Key Dates
14 July – 18 July
21st July
23
4th August
Payment Apportionment Go Live

## Slide 3
Work Items Delivered

## Slide 4
Work Items Planned for Next Sprint

## Slide 5
General Items
Risk | Contributing factors | Impact | Decisions taken
None |  |  | 
Issue | Contributing factors | Impact | Decisions taken
reCAPTCHA on Form Assembly forms impacting form performance |  | Alters how the form can be submitted, with conditional formatting and date inputs not displaying correctly | Hold off on release of SFDC-834. SFDC-863, and SFDC-865
Items Carried over to next Sprint | Reasons
Create GREP Integration Permission Sets and Permission Set Group Create Own Backup Permission Set/PSG | RBAC Items of lower priority
Decision | Description | Date
Delay Payment Apportionment Release | Due to high impact nature of this change, as well as allowing time for TPT to adequately plan cut-over and align with workstreams, the date for the Payment Apportionment items will be pushed back to 4th August | 16th July 2025 – Jacob Smycz, Anita Masters, Clair Habgood

## Slide 6: Thank You