## 2025-06 SF BAU Jira Tickets Upd
Issue Type | Issue key | Summary | Status | Parent key | Parent summary | Sprint | Release Month
Story | SFDC-569 | Close future anonymised opportunities | Released | SFDC-433 | BAU Enhancement | 7 | January
Story | SFDC-568 | Anonymise Opp Names with Anonymised Contacts | Released | SFDC-433 | BAU Enhancement | 7 | January
Story | SFDC-287 | Building Page Layout Update | Released | SFDC-432 | Audit - UX | 7 | January
Story | SFDC-286 | Block Page Layout Update | Released | SFDC-432 | Audit - UX | 7 | January
Story | SFDC-656 | Create Operations User Perm Sets | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-653 | Create Resident Services/Portfolio Manager CRUD perm set | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-652 | Create Property Manager CRUD permset | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-650 | Create Operations CRUD perm Set | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-648 | Residential Senior Lettings CRUD perm set | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-647 | Resi Lettings Manager CRUD perm set | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-644 | Unit - Add 'Notes' back to page layout | Released | SFDC-433 | BAU Enhancement | 8 | February
Story | SFDC-641 | Lead - Waitlist Out Reasons | Released | SFDC-433 | BAU Enhancement | 8 | February
Story | SFDC-632 | Update PS_Residential_Lettings_CRUD | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-456 | PRS Team Permission Set Group | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-455 | Head of PRS Permission Set Group | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-454 | Resident Services Team Permission Set Group | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-453 | Head of Resident Services Permission Set Group | Released | SFDC-431 | RBAC | 8 | February
Story | SFDC-712 | Update All Resi Lettings CRUD perm sets | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-705 | Create Property Sales Permissions | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-702 | Property Sales User Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-701 | Update Residential Leasing User PS | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-699 | Add Touchpoint Survey Read PS to Ops PSGs | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-693 | Create PS_Credit_Control_CRUD permission Set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-692 | Update Operations PSGs with new Perm Sets (New Strategy Allignment) | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-689 | Identify 'Under Other Contract' Blocks | Released | SFDC-433 | BAU Enhancement | 9 | March
Story | SFDC-682 | System Support Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-681 | PS_Customer_Service_Advisor_CRUD update | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-679 | PS_Tenancy_Progression_CRUD update | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-651 | Add Custom Permission to Lettings Users Permissions PS | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-649 | Customer Service Associate CRUD perm set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-639 | Create Renewal Manager User Permissions perm set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-638 | Create Renewal Neg User Permissions Permset | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-636 | Update PS Renewals CRUD | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-635 | Create Renewal Admin User Permissions Permission Set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-634 | Create Tenancy Progression Manager User Permissions permset | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-630 | Create Tenancy Progression User Permissions permset | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-629 | Update PS Tenancy Progression CRUD | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-628 | GEN - Property Read perm set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-627 | Create Gen Contracts R permission Set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-626 | GEN - Lead R Perm Set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-625 | GEN - Contact R Perm Set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-624 | GEN - Account R Perm Set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-600 | Create GEN - OpportunityOffer R Permission Set | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-583 | Update Default Grainger Profile - Unit | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-563 | Conga Composer Permissions | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-458 | Credit Control Team Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-392 | TPT User Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-391 | TPT Manager Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-412 | Renewal Administrator Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-411 | Renewal Negotiator Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-421 | Renewal Manager Permission Set Group | Released | SFDC-431 | RBAC | 9 | March
Story | SFDC-760 | Update Renewals CRUD permset | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-749 | Update PS_Renewals_CRUD Perm Set | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-743 | Update PS_Renewals_CRUD perm set | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-742 | Update Residential Leasing User permset | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-741 | Update PS_Residential_Lettings_CRUD | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-735 | Update GEN_Contracts_Read Permission Set | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-732 | PS_Payment_Creation | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-698 | Prevent Agreements from Expiring | Released | SFDC-433 | BAU Enhancement | 10 | April
Story | SFDC-724 | Rent not reflecting on initial summary email | Released | SFDC-433 | BAU Enhancement | 10 | April
Story | SFDC-721 | Make PMS reference on Opp Searchable | Released | SFDC-433 | BAU Enhancement | 10 | April
Story | SFDC-720 | Use Type Picklist Values | Released | SFDC-433 | BAU Enhancement | 10 | April
Story | SFDC-723 | Remove Lease Completion Statement Validation | Released | SFDC-433 | BAU Enhancement | 10 | April
Story | SFDC-678 | Delete Commercial Leasing User and Commercial Lettings Team Permissions permission sets | Released | SFDC-431 | RBAC | 10 | April
Story | SFDC-722 | Rename 'Move In Date' field | Released | SFDC-433 | BAU Enhancement | 10 | April
Story | SFDC-719 | Update AFL Details on Opportunity | Released | SFDC-433 | BAU Enhancement | 10 | April
Story | SFDC-765 | Waitlist Op Conversion Flow | Done | SFDC-433 | Waitlist Opps Project | 11 | May
Story | SFDC-609 | Assign Record Type access | Done | SFDC-433 | Waitlist Opps Project | 11 | May
Story | SFDC-594 | Button to flip opportunity | Done | SFDC-433 | Waitlist Opps Project | 11 | May
Story | SFDC-589 | Create 'Waitlist' Record Type on Opp | Done | SFDC-433 | Waitlist Opps Project | 11 | May
Story | SFDC-795 | Update PS_GEN_Contracts_Read | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-770 | Add Create Reports and Dashboards PS to Lettings Manager PSG | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-764 | Update 'Closed Won Monthly Price' Opportunity Validation Rule | Released | SFDC-433 | BAU Enhancement | 11 | May
Story | SFDC-763 | Update Residential Opportunity Lightning Record Page | Released | SFDC-432 | Audit - UX | 11 | May
Story | SFDC-762 | Allow NHA for Welsh Properties | Released | SFDC-433 | BAU Enhancement | 11 | May
Story | SFDC-754 | Add Referencing Callout Permisisons to PermSetGroups | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-753 | Lead Tenant OCR Validation Rule | Released | SFDC-433 | BAU Enhancement | 11 | May
Story | SFDC-738 | Create PS_SYS_Edit_All_Fields permission Set | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-737 | Create PS_SYS_View_All_Fields permission set | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-654 | Create System Admin Permission Sets and Group | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-645 | System Support Perm Set | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-640 | Retrospectively remove excess COM - Object Permissions from Commercial Lettings Team PermSetGroup | Released | SFDC-431 | RBAC | 11 | May
Story | SFDC-284 | Opportunity Page Layout Update | Released | SFDC-432 | Audit - UX | 11 | May
Story | SFDC-835 | Viewing on Activity Timeline | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-828 | Add Viewing Tour field to Event | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-827 | Remove Delete Button on Event | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-826 | Move Related List on Opp | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-817 | Create Viewing Cancellation Email Template | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-809 | Home Page Component - Today's Viewings | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-808 | Remove Viewing Units from a Viewing Journey | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-807 | Add Viewing Units to a Viewing Tour | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-805 | Add Viewing Unit Related lists | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-804 | Complete a Viewing Journey | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-802 | Update/Cancel a Viewing Journey | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-801 | Create Viewing Event Record Type | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-800 | Viewing Journey Creation/Update Flow | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-799 | Create Viewing Unit Object | Released | SFDC-789 | Viewing Tours Project | 12 | June
Story | SFDC-786 | Update Agreement Types | Released | SFDC-433 | BAU Enhancement | 12 | June
Story | SFDC-785 | See Tenancy Contact Roles on an Account | Released | SFDC-433 | BAU Enhancement | 12 | June
Story | SFDC-461 | Create Viewing Tour Object | Released | SFDC-789 | Viewing Tours Project | 12 | June