## Deployment Issue
Object | Type | Reason for Failure | Solution
Contract-Commercial Contract Layout | Layout | In field: field - no CustomField named Contract.TDS_Reference__c found | Fields are related to CJR, need to be excluded
Opportunity-Opportunity Layout | Layout | In field: field - no CustomField named Opportunity.Tenancy__c found | Fields are related to CJR, need to be excluded
CMTD__EnhancedRelatedList.UnitPricebook | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to Install Unofficial Package
CMTD__EnhancedRelatedList.UnitPricebookEntry | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to Install Unofficial Package
CMTD__EnhancedRelatedList.UnitPricebook_ReasonForRentChange | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to Install Unofficial Package
CMTD__EnhancedRelatedList.UnitPricebook_RentPeriod | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to Install Unofficial Package
CMTD__EnhancedRelatedList.UnitPricebook_UnitPrice | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to Install Unofficial Package
Update_Commercial_Opportunity_Fields_Before_Save | Flow | field integrity exception: unknown (The element has an invalid reference to "$Record.Tenancy__c".) | Fields are related to CJR, need to be excluded, need to update the flow
LET_Opportunity_RE | PermissionSet | In field: field - no CustomField named Opportunity.Tenancy__c found | Fields are related to CJR, need to be excluded
PS_GEN_OpportunityOffer_Read | PermissionSet | In field: field - no CustomField named Opportunity.Tenancy__c found | Fields are related to CJR, need to be excluded
Customer_Service_Advisor | PermissionSetGroup | Cannot create permission set group components since the following permission set names are invalid: GEN_Property_R | Exclude PS GEN_Property_R
Lettings_Manager | PermissionSetGroup | Cannot create permission set group components since the following permission set names are invalid: GEN_Property_R | Exclude PS GEN_Property_R
Lettings_Senior_Negotiator | PermissionSetGroup | Cannot create permission set group components since the following permission set names are invalid: GEN_Property_R | Exclude PS GEN_Property_R
Lettings_User | PermissionSetGroup | Cannot create permission set group components since the following permission set names are invalid: GEN_Property_R | Exclude PS GEN_Property_R
Renewal_Administrator | PermissionSetGroup | Cannot create permission set group components since the following permission set names are invalid: PS_Renewal_Administrator_User_Permissions, PS_Renewals_CRUD | Exclude Renewals related PS (They belong to CJR)
Renewal_Manager | PermissionSetGroup | Cannot create permission set group components since the following permission set names are invalid: PS_Renewal_Manager_User_Permissions, PS_Renewals_CRUD | Exclude Renewals related PS (They belong to CJR)
Renewal_Negotiator | PermissionSetGroup | Cannot create permission set group components since the following permission set names are invalid: PS_Renewal_Negotiator_User_Permissions, PS_Renewals_CRUD | Exclude Renewals related PS (They belong to CJR)
Contract.Commercial_Contract | RecordType | invalid compact layout assigned: Commercial_Contract_Compact_Layout | Include compact layout in deployment
Contract.Residential_Contract | RecordType | invalid compact layout assigned: Residential_Contract_Compact_Layout | Include compact layout in deployment
Contract.Residential_Tenancy | RecordType | invalid compact layout assigned: Residential_Tenancy_Compact_Layout | Exclude from deployment
Commercial_Contract_Record_Page | FlexiPage | Component [lst:dynamicRelatedList] attribute [relatedListApiName]: Could not find related list [Tenancy_Contact_Roles__r] for entity [Contract] | remove the related list from commercial contract page - bug logged
Unit_Record_Page | FlexiPage | We couldn't retrieve the design time component information for component CMTD:EnhancedRelatedList. | Need to Install Unofficial Package
Copy_Commercial_Offer | Flow | Cant_copy_primary_offer (Action) - We can't find an action with the name and action type that you specified. | Need to install Salesforce Lab package
Create_Commercial_Offer | Flow | An unexpected error occurred. Please include this ErrorId if you contact support: 1883660419-317123 (1213966822)
Create_New_Task_On_Commercial_Opportunity | Flow | ShowTaskCreatedToast (Action) - We can't find an action with the name and action type that you specified. | Need to Install Unofficial Package
Create_Opportunity_Screen_Flow | Flow | show_Toast (Action) - We can't find an action with the name and action type that you specified. | Need to Install Unofficial Package

## Conflict Issues
CLTL UAT=>PROD
1) Quote.Term
Parking licence Oxford and "Occupation Contract" exist in UAT but does not exist in PROD
2) Quote.Agreement_Type
Commercial Lease, Commercial Let already deployed to PROD
3)Opportunity.Agreement_Type
| Remove "Mid Term Change Of Sharer" controlling field as "Decant Agreement Normal" | Cab Ticket - https://graingerplc.atlassian.net/browse/CAB-248 | Not to be deployed to PROD yet
4) Do we need "Mid Term Change of Sharer" in Commercial Lease and Licencese?
5) Does "Openbox" need to deploy Mid Term Change of Sharer to PROD , as these changes are not made by us ?
6) Opportunity.Lost Reason = Unit Sold Controllling Field not present in UAT and lower orgs
7) Unit Layout has values which are not present in lower environment, this applies to other Types of Unit as well
8) Dont need this field on this page layout
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current thinking: Open Box will not deploy Occupation Contract Should we deploy the change to make Decant Agreement correct capitalization?
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Open Box will deploy the values as active
Note on A40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Open Box won’t deploy any of these changes
Note on A64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Open Box won’t deploy this
Note on A85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Open Box won’t deploy
Note on A101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FYI only, Open Box will not delete the value from PROD. Confirmed that OB t needs sync back to lower environments.
Note on A116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FYI only, Open Box will not delete the value from PROD. Confirmed it doesn’t need ot be synced back
Note on A153: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Saji added field to page layout directly in UAT. We will remove from page layout and then deploy to PROD.

## Deployment Issue 12 March
Object | Type | Reason for Failure | Solution
Opportunity.Residential_Opportunity | RecordType | Picklist value: Mid Term Change Of Sharer in picklist: Tenancy_Type__c not found | Need to remove " Mid Term Change Of Sharer" from Residential Opportunity Record Type during deployment as shown in image
CMTD__EnhancedRelatedList.UnitPricebook | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to install Salesforce Lab package
CMTD__EnhancedRelatedList.UnitPricebookEntry | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to install Salesforce Lab package
CMTD__EnhancedRelatedList.UnitPricebook_ReasonForRentChange | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to install Salesforce Lab package
CMTD__EnhancedRelatedList.UnitPricebook_RentPeriod | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to install Salesforce Lab package
CMTD__EnhancedRelatedList.UnitPricebook_UnitPrice | CustomMetadata | Custom metadata type CMTD__EnhancedRelatedList__mdt is not available in this organization. | Need to install Salesforce Lab package
Unit_Record_Page | FlexiPage | We couldn't retrieve the design time component information for component CMTD:EnhancedRelatedList. | Need to install Salesforce Lab package
Copy_Commercial_Offer | Flow | Cant_copy_primary_offer (Action) - We can't find an action with the name and action type that you specified. | Need to install "Show Toast" from USF : this action uses it
Create_Commercial_Offer | Flow | An unexpected error occurred. Please include this ErrorId if you contact support: 2004899808-337666 (1213966822)
Create_New_Task_On_Commercial_Opportunity | Flow | ShowTaskCreatedToast (Action) - We can't find an action with the name and action type that you specified. | Need to install "Show Toast" from USF
Create_Opportunity_Screen_Flow | Flow | show_Toast (Action) - We can't find an action with the name and action type that you specified. | Need to install "Show Toast" from USF
Gear set package link https://app.gearset.com/reactive-compare/results?deployPackageId=c5cf50f6-e248-4453-a560-11e28e554228
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sam Duncan not sure what is the issue here

## Test Class Validation 12 March
Result | Class | Method name | Errors | Stack trace | Comment
Failed | OpportunityTriggerHandlerTest | testAcceptQuotes | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1 | Runs in DEV, QA and UAT as shown in ss
Failed | OpportunityTriggerHandlerTest | testCancelQuotes | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1 | Runs in DEV, QA and UAT as shown in ss
Failed | OpportunityTriggerHandlerTest | testInsertShadowOpportunities | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1 | Runs in DEV, QA and UAT as shown in ss
Failed | OpportunityTriggerHandlerTest | testSyncShadowOpportunities | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1 | Runs in DEV, QA and UAT as shown in ss
Failed | QuoteTriggerHandlerTest | testQuoteUpdate | System.AssertException: Assertion Failed: Unit status should be updated to - On Hold In Basket: Expected: On Hold - In Basket, Actual: Leased | Class.QuoteTriggerHandlerTest.testQuoteUpdate: line 144, column 1 | Runs in DEV as shown in ss | Need to add RecordTypeId =Residential Offer and Residential Oppty in existing functions Fix deployed DEV => QA, UAT, SIT, Renewal1
Failed | Renewals_OpportunityCloneTest | testBatch | System.QueryException: List has no rows for assignment to SObject | Class.Renewals_OpportunityCloneTest.setupData: line 25, column 1 | Runs in DEV as shown in ss | Turn Off Validation related to CJR in UAT: Ensure_Mid_Term_Opps_have_Tenancy and VR_Require_PMS_Ref_Audit_Stage
Failed | Renewals_OpportunityCloneTest | testBatchFailure | System.QueryException: List has no rows for assignment to SObject | Class.Renewals_OpportunityCloneTest.setupData: line 25, column 1 | Runs in DEV as shown in ss | Turn Off Validation related to CJR in UAT: Ensure_Mid_Term_Opps_have_Tenancy and VR_Require_PMS_Ref_Audit_Stage
Passed | Product2TriggerHandlerTest | testMaintainProductUnitConsistency | Passed
Passed | QuoteTriggerHandlerTest | testCheckPrimaryQuoteExistsValidation | Passed
Passed | TenancyPaymentScheduleUtilTest | testGenerateSchedules | Passed
Passed | UnitSearchControllerTest | createOfferFailedTest | Passed
Passed | UnitSearchControllerTest | createOfferTest | Passed
Passed | UnitSearchControllerTest | getFilterOptionsTest | Passed
Passed | UnitSearchControllerTest | unitSearschTest | Passed

## Test Class Validation 13 March
Result | Class | Method name | Errors | Stack trace | Comment
Failed | OpportunityTriggerHandlerTest | testAcceptQuotes | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1
Failed | OpportunityTriggerHandlerTest | testCancelQuotes | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1
Failed | OpportunityTriggerHandlerTest | testInsertShadowOpportunities | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1
Failed | OpportunityTriggerHandlerTest | testSyncShadowOpportunities | System.NullPointerException: Attempt to de-reference a null object | Class.OpportunityTriggerHandlerTest.initData: line 7, column 1
Failed | QuoteTriggerHandlerTest | testCheckPrimaryQuoteExistsValidation | System.NullPointerException: Attempt to de-reference a null object | Class.QuoteTriggerHandlerTest.initData: line 7, column 1
Failed | QuoteTriggerHandlerTest | testQuoteUpdate | System.NullPointerException: Attempt to de-reference a null object | Class.QuoteTriggerHandlerTest.initData: line 7, column 1
Failed | Renewals_OpportunityCloneTest | testBatch | System.QueryException: List has no rows for assignment to SObject | Class.Renewals_OpportunityCloneTest.setupData: line 25, column 1
Failed | Renewals_OpportunityCloneTest | testBatchFailure | System.QueryException: List has no rows for assignment to SObject | Class.Renewals_OpportunityCloneTest.setupData: line 25, column 1
Passed | Product2TriggerHandlerTest | testMaintainProductUnitConsistency | Passed
Passed | TenancyPaymentScheduleUtilTest | testGenerateSchedules | Passed
Passed | UnitSearchControllerTest | createOfferFailedTest | Passed
Passed | UnitSearchControllerTest | createOfferTest | Passed
Passed | UnitSearchControllerTest | getFilterOptionsTest | Passed
Passed | UnitSearchControllerTest | unitSearschTest | Passed