## CLTL User Stories
Issue Type | Issue key | Summary | Sprint | Status | Assignee | Reporter
Story | CLTL-91 | Capital Contributions (Months) - Calc & Field Format | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-16 | Capture Additional Account Information | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-20 | Capture Additional Unit Information | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-22 | Create a New Commercial Lease Opportunity | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-19 | Create Commercial Offers | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-59 | Easily View/Access Price Book Entry History from Unit | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-71 | Lost Reason should always display | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Mudzunga Khonani Davhana
Story | CLTL-10 | Manage Commercial New Lease Opportunities | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-74 | New Commercial Opportunity - Agreement Type Field | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-44 | Not Required | CLTL Sprint 1 | Done |  | Nikki
Story | CLTL-65 | Review Permission Sets & Permission Set Groups | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-4 | See History of Marketing Rent | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-21 | Update Offer Line Items | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-63 | Update Tenancy End Date | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-23 | Updating Opportunity Details from the Primary Offer | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Bug | CLTL-143 | For Decant agreement types both residential stages and Commercial stages are displayed | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Jaic George
Story | CLTL-159 | Add 'Commercial Contract' Record Type | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-39 | Add Agreement Type Validation | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-66 | Add Move In Date Validation | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-30 | Calculate Days Void & Days On Market | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-139 | Change "Rent Free Months" Field to an interger | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Mudzunga Khonani Davhana
Story | CLTL-67 | Change Flow Updated Fields to Reference Offer | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-2 | Commercial Leasing Activity Dashboard | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-28 | Copy an Offer | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-104 | Create LET - Opportunity RE Permission Set | CLTL Sprint 2 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-26 | Create Tenant, Tenant Contact & Guarantor Opportunity Contact Roles | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-133 | First Rent Review Date Calculated Upon Opportunity Creation | CLTL Sprint 2 | Done | Nikki | Sarah Jessiman
Story | CLTL-148 | Not Updated / Known Issue - Error when adding Agent Account fields as Tenant or Guarantor | CLTL Sprint 2 | Done | Nikki | Mudzunga Khonani Davhana
Story | CLTL-72 | Prepopulate Required Fields | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-117 | Remove Contact & Opportunity Related Lists | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-105 | Remove Read access from profiles | CLTL Sprint 2 | Done | Sarah Jessiman | Sachin Deshmukh
Story | CLTL-166 | Reorder Create Commercial Button on Account Screens | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-13 | Replace Commercial Live Offer Tracker | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-136 | Report: Stage Turnaround Times - Signings in Last 12 Months | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-7 | Save a History of Comments & Delays | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-89 | Stepped Rent - Records should not be automatically created | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-29 | UAT Feedback Placeholder - Sprint 2 | CLTL Sprint 2 | Done |  | Nikki
Story | CLTL-93 | Update 'First Rent Review Date' Logic | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-3 | Validate Opportunity & Prepopulate Dates on Changing Stage | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Bug | CLTL-191 | Cannot Create Duplicate Contacts | CLTL Sprint 3 | Done |  | Jacob Smycz
Bug | CLTL-257 | Commercial Licence on offer doesn't give option to enter term/payment periodicity/break clause | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Bug | CLTL-253 | Offer marked as DepositPaid_CreateFutureTenancy__c | CLTL Sprint 3 | Done | Sarah Jessiman | Jaic George
Bug | CLTL-285 | Opportunity stage not visible | CLTL Sprint 3 | Done | Jacob Smycz | Jaic George
Bug | CLTL-305 | The order of record creation in Opportunity contact Role | CLTL Sprint 3 | In Review | Jacob Smycz | Jaic George
Bug | CLTL-256 | UAT - GREP integration user doesn't have the Permission | CLTL Sprint 3 | Done | Jacob Smycz | Jaic George
Bug | CLTL-172 | UAT - Renewal opportunity showing Commercial work flow | CLTL Sprint 3 | Done | Sarah Jessiman | Jaic George
Bug | CLTL-287 | UAT - System support user doesn't have visibility | CLTL Sprint 3 | Done | Jacob Smycz | Jaic George
Bug | CLTL-255 | Unable to move to 'Lease Completion' or 'Audit' Stages | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-31 | Activate Commercial Tenancies in Qube [Grainger] | CLTL Sprint 3 | To Do | Jaic George | Nikki
Story | CLTL-11 | AM Approval | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-167 | Bulk Create Products & Price Book Entries for Commercial Units | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-251 | Bulk Update Price Book Entries for Commercial Units | CLTL Sprint 3 | Done | Matthew Cornfield | Jacob Smycz
Story | CLTL-14 | Commercial Opportunity List View | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-165 | Commercial Unit List View | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-9 | Create Commercial Contracts in Salesforce | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-194 | Create Commercial Permission Sets in line with new Perm Set Strategy | CLTL Sprint 3 | Done | Jacob Smycz | Jacob Smycz
Story | CLTL-1 | Create Future Commercial Tenancies in Qube [Grainger] | CLTL Sprint 3 | To Do | Jaic George | Nikki
Story | CLTL-25 | Create Shadow Opportunities for Additional Units | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-51 | Duplicate | CLTL Sprint 3 | Done |  | Nikki
Story | CLTL-69 | List Existing Metadata Configurations | CLTL Sprint 3 | Done | Sarah Jessiman | Anjali Salecha
Story | CLTL-138 | Not Required | CLTL Sprint 3 | Done | Nikki | Nikki
Story | CLTL-94 | Not Required | CLTL Sprint 3 | Done |  | Nikki
Story | CLTL-18 | Notify Credit Control to Update Qube | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-24 | Notify Internal Teams when Lease is Signed | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-33 | Pre/Post Deployment Step | CLTL Sprint 3 | To Do |  | Sachin Deshmukh
Story | CLTL-163 | Prevent users from selecting an Agent account as the Account Name or Guarantor on an Opportunity | CLTL Sprint 3 | Done | Sarah Jessiman | Sam Duncan
Story | CLTL-158 | QA - Update Contract Validation: Agreement Type for Welsh Properties | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-8 | See Additional Building Information | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-5 | See Agent Viewings, Enquiries & Feedback for a Unit | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-238 | SIT Deployment RTR/CLTL | CLTL Sprint 3 | In Review | Sachin Deshmukh | Sachin Deshmukh
Story | CLTL-213 | UAT - Capture Deposit Details on Offers | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-195 | UAT - Commercial Licence Agreement Type | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-300 | UAT - Deposit to be paid back | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-224 | UAT - Filter Agent Contact options | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-275 | UAT - Make Opportunity Editable while Pending AM Approval | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-212 | UAT - Offer Page Layout Update | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-290 | UAT - Remove Renewal Tenancy Type from Commercial Opportunity Record Type | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-274 | UAT - Set up AM's with 'Items to Approve' on Home page | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-278 | UAT - Stop users moving stage to AM Approved via the Chevron | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-286 | UAT - Update 'deposit to be paid back' on the offer & opportunity to text field | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-219 | UAT - Update 'Lease Plan Status' Picklist Values | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-209 | UAT - Update Company Account Page | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-271 | UAT - Update Email Recipients & include AM / FM | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-217 | UAT - Update First Break Clause Date on Offers | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-27 | UAT Feedback Placeholder - Sprint 3 | CLTL Sprint 3 | Done |  | Nikki
Story | CLTL-137 | Update Opportunity Details Layout (Cosmetic) | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-204 | User Guide | CLTL Sprint 3 | In Review | Jacob Smycz | Shaun Barrett
Bug | CLTL-294 | UAT - System throwing generic error | Grainger | To Do | Jaic George | Jaic George
Story | CLTL-282 | UAT - Units incorrectly set up in Salesforce as Commercial Units | Grainger | To Do | Deborah Stein | Deborah Stein
Story | CLTL-281 | UAT - Commercial Unit Types-Qube Data cleanse | Grainger | To Do | Deborah Stein | Deborah Stein
Story | CLTL-280 | UAT - Commercial Units - Potential Units for Salesforce leasing journey | Grainger | To Do | Deborah Stein | Deborah Stein
Story | CLTL-262 | UAT - Integration of master data from Qube to Salesforce-tenant address | Grainger | To Do | Deborah Stein | Deborah Stein
Story | CLTL-279 | UAT - Mapping of Commercial Units from Qube to Salesforce-update required | Grainger | To Do | Jaic George | Deborah Stein
Story | CLTL-265 | UAT - Residential/Amenity units listed as 'Commercial Unit' Record Types | Grainger | In Progress | Deborah Stein | Deborah Stein
Story | CLTL-318 | UAT- STEIN TESTING UAT TEST 5-Incorrect population of Billing address | Grainger | To Do | Jaic George | Deborah Stein
Bug | CLTL-283 | UAT - Residential Offer screen has been updated to mirror the Commercial Offer screen | Open Box Backlog | To Do |  | Deborah Stein
Story | CLTL-15 | Agent Inputs Viewings, Enquiries & Feedback | Open Box Backlog | To Do |  | Nikki
Story | CLTL-310 | Commercial Building Identifier | Open Box Backlog | To Do |  | Nikki
Story | CLTL-12 | Commercial Portfolio Dashboard | Open Box Backlog | To Do |  | Nikki
Story | CLTL-303 | Duplicate - Change Use Type to drop down | Open Box Backlog | To Do |  | Nikki
Story | CLTL-315 | Duplicate - Landlord & tenant Act Type is missing from Salesforce and interface to Qube | Open Box Backlog | To Do |  | Deborah Stein
Story | CLTL-6 | Investment Committee Report | Open Box Backlog | To Do |  | Nikki
Story | CLTL-284 | OUT OF SCOPE - Commercial lease renewal-no agreement type can be populated | Open Box Backlog | To Do |  | Deborah Stein
Story | CLTL-17 | Replace Tenancy Schedule | Open Box Backlog | To Do |  | Nikki
Story | CLTL-261 | UAT - Account Billing Address-New Field | Open Box Backlog | To Do |  | Deborah Stein
Story | CLTL-228 | UAT - Add additional Landlord and Tenant Act Details | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-260 | UAT - Agents-Accounts and contacts can be selected in the Local and National Agent fields on the Opportunity. | Open Box Backlog | To Do |  | Deborah Stein
Story | CLTL-223 | UAT - Auto Populate Agent Details on Opportunities | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-232 | UAT - Capture Agent Instruction details | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-220 | UAT - Capture Close Lost reasons more effectively | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-214 | UAT - Capture Rent Review Details on Offers | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-226 | UAT - Capture Stepped Rent Details as part of an offer | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-210 | UAT - Capture VAT details on Unit | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-211 | UAT - Commercial Agent Details on Unit - Maybe Deprecate ? | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-221 | UAT - Default Offer Line Item Quantity | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-222 | UAT - Easily Identify Commercial Buildings | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-259 | UAT - Multiple units across multiple buildings cannot be incorporated into One Opportunity/Offer | Open Box Backlog | To Do |  | Deborah Stein
Story | CLTL-276 | UAT - Remove Lease Completion Statement Validation | Open Box Backlog | To Do |  | Nikki
Story | CLTL-218 | UAT - Rename 'Move In Date' field | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-216 | UAT - Require updated AM/IC approvals if Offers change | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-299 | UAT - Send Approval Request to 2 AMs | Open Box Backlog | To Do |  | Nikki
Story | CLTL-230 | UAT - Send to Qube confirmation | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-227 | UAT - Update 'Tenancy Start Date' on Opps when Tenancy Signing Date is complete | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-215 | UAT - Update AFL Details on Opportunity | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-225 | UAT - Update Agent Account Record Type | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-316 | UAT - Use Type Picklist Values | Open Box Backlog | To Do |  | Jacob Smycz
Story | CLTL-322 | UAT- Reporting | Open Box Backlog | To Do | Jacob Smycz | Deborah Stein
Story | CLTL-317 | UAT-STEIN TESTING UAT TEST 5- tenancy start date can be edited after the opportunity has moved to AUDIT stage and tenancy has been created | Open Box Backlog | To Do |  | Deborah Stein