## Delivered
Issue Type | Issue key | Summary | Sprint | Status | Assignee | Reporter
Story | CLTL-91 | Capital Contributions (Months) - Calc & Field Format | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-16 | Capture Additional Account Information | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-20 | Capture Additional Unit Information | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-22 | Create a New Commercial Lease Opportunity | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-19 | Create Commercial Offers | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-59 | Easily View/Access Price Book Entry History from Unit | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-71 | Lost Reason should always display | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Mudzunga Khonani Davhana
Story | CLTL-10 | Manage Commercial New Lease Opportunities | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-74 | New Commercial Opportunity - Agreement Type Field | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-65 | Review Permission Sets & Permission Set Groups | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-4 | See History of Marketing Rent | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-21 | Update Offer Line Items | CLTL Sprint 1 | Done | Sarah Jessiman | Nikki
Story | CLTL-63 | Update Tenancy End Date | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-23 | Updating Opportunity Details from the Primary Offer | CLTL Sprint 1 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-159 | Add 'Commercial Contract' Record Type | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-39 | Add Agreement Type Validation | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-66 | Add Move In Date Validation | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-30 | Calculate Days Void & Days On Market | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-139 | Change "Rent Free Months" Field to an interger | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Mudzunga Khonani Davhana
Story | CLTL-67 | Change Flow Updated Fields to Reference Offer | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-2 | Commercial Leasing Activity Dashboard | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-28 | Copy an Offer | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-104 | Create LET - Opportunity RE Permission Set | CLTL Sprint 2 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-26 | Create Tenant, Tenant Contact & Guarantor Opportunity Contact Roles | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-133 | First Rent Review Date Calculated Upon Opportunity Creation | CLTL Sprint 2 | Done | Nikki | Sarah Jessiman
Story | CLTL-148 | Not Updated / Known Issue - Error when adding Agent Account fields as Tenant or Guarantor | CLTL Sprint 2 | Done | Nikki | Mudzunga Khonani Davhana
Story | CLTL-72 | Prepopulate Required Fields | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-117 | Remove Contact & Opportunity Related Lists | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-105 | Remove Read access from profiles | CLTL Sprint 2 | Done | Sarah Jessiman | Sachin Deshmukh
Story | CLTL-166 | Reorder Create Commercial Button on Account Screens | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-13 | Replace Commercial Live Offer Tracker | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-136 | Report: Stage Turnaround Times - Signings in Last 12 Months | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-7 | Save a History of Comments & Delays | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Nikki
Story | CLTL-89 | Stepped Rent - Records should not be automatically created | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-93 | Update 'First Rent Review Date' Logic | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Story | CLTL-3 | Validate Opportunity & Prepopulate Dates on Changing Stage | CLTL Sprint 2 | Done | Sarah Jessiman | Nikki
Bug | CLTL-143 | For Decant agreement types both residential stages and Commercial stages are displayed | CLTL Sprint 2 | Done | Mudzunga Khonani Davhana | Jaic George
Task | CLTL-264 | UAT - Create New Commercial Unit is allowed from Opportunity | CLTL Sprint 3 | Done | Sarah Jessiman | Deborah Stein
Story | CLTL-31 | Activate Commercial Tenancies in Qube [Grainger] | CLTL Sprint 3 | Testing | Jaic George | Nikki
Story | CLTL-11 | AM Approval | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-167 | Bulk Create Products & Price Book Entries for Commercial Units | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-251 | Bulk Update Price Book Entries for Commercial Units | CLTL Sprint 3 | Done | Matthew Cornfield | Jacob Smycz
Story | CLTL-14 | Commercial Opportunity List View | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-165 | Commercial Unit List View | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-9 | Create Commercial Contracts in Salesforce | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-194 | Create Commercial Permission Sets in line with new Perm Set Strategy | CLTL Sprint 3 | Done | Jacob Smycz | Jacob Smycz
Story | CLTL-25 | Create Shadow Opportunities for Additional Units | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-311 | Data migration - Update - Populate ‘Facilities Management Team' on existing units [Logic changed - revert back to 271] | CLTL Sprint 3 | Done | Jacob Smycz | Matthew Cornfield
Story | CLTL-69 | List Existing Metadata Configurations | CLTL Sprint 3 | Done | Sarah Jessiman | Anjali Salecha
Story | CLTL-18 | Notify Credit Control to Update Qube | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-24 | Notify Internal Teams when Lease is Signed | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-163 | Prevent users from selecting an Agent account as the Account Name or Guarantor on an Opportunity | CLTL Sprint 3 | Done | Sarah Jessiman | Sam Duncan
Story | CLTL-158 | QA - Update Contract Validation: Agreement Type for Welsh Properties | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-8 | See Additional Building Information | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-5 | See Agent Viewings, Enquiries & Feedback for a Unit | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-353 | SIT - Missing Offer Fields | CLTL Sprint 3 | Done | Sarah Jessiman | Sarah Jessiman
Story | CLTL-213 | UAT - Capture Deposit Details on Offers | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-195 | UAT - Commercial Licence Agreement Type | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-300 | UAT - Deposit to be paid back | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-224 | UAT - Filter Agent Contact options | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-275 | UAT - Make Opportunity Editable while Pending AM Approval | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-212 | UAT - Offer Page Layout Update | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-369 | UAT - R DAY - Specify IC Approval Date | CLTL Sprint 3 | Done | Sachin Deshmukh | Patricia Buck
Story | CLTL-290 | UAT - Remove Renewal Tenancy Type from Commercial Opportunity Record Type | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-274 | UAT - Set up AM's with 'Items to Approve' on Home page | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-278 | UAT - Stop users moving stage to AM Approved via the Chevron | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-286 | UAT - Update 'deposit to be paid back' on the offer & opportunity to text field | CLTL Sprint 3 | Done | Nadia Swarts | Nikki
Story | CLTL-219 | UAT - Update 'Lease Plan Status' Picklist Values | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-209 | UAT - Update Company Account Page | CLTL Sprint 3 | Done | Nadia Swarts | Jacob Smycz
Story | CLTL-271 | UAT - Update Email Recipients & include AM / FM | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Story | CLTL-217 | UAT - Update First Break Clause Date on Offers | CLTL Sprint 3 | Done | Sarah Jessiman | Jacob Smycz
Story | CLTL-137 | Update Opportunity Details Layout (Cosmetic) | CLTL Sprint 3 | Done | Sarah Jessiman | Nikki
Bug | CLTL-327 | Flow error when creating a commercial opportunity | CLTL Sprint 3 | Done | Jacob Smycz | Jaic George
Bug | CLTL-349 | LR TEST - Email with lease information not showing rent value | CLTL Sprint 3 | Done | Lesley Richardson | Lesley Richardson
Bug | CLTL-253 | Offer marked as DepositPaid_CreateFutureTenancy__c | CLTL Sprint 3 | Done | Sarah Jessiman | Jaic George
Bug | CLTL-285 | Opportunity stage not visible | CLTL Sprint 3 | Done | Jacob Smycz | Jaic George
Bug | CLTL-305 | The order of record creation in Opportunity contact Role | CLTL Sprint 3 | Done | Jaic George | Jaic George
Bug | CLTL-256 | UAT - GREP integration user doesn't have the Permission | CLTL Sprint 3 | Done | Jacob Smycz | Jaic George
Bug | CLTL-370 | UAT - R DAY - Leap year term incorrect | CLTL Sprint 3 | Done | Sarah Jessiman | Patricia Buck
Bug | CLTL-172 | UAT - Renewal opportunity showing Commercial work flow | CLTL Sprint 3 | Done | Sarah Jessiman | Jaic George
Bug | CLTL-287 | UAT - System support user doesn't have visibility | CLTL Sprint 3 | Done | Jacob Smycz | Jaic George
Bug | CLTL-362 | UAT TESTING-REGRESSION TESTING-Unable to Create DECANT OFFER | CLTL Sprint 3 | Done | Sarah Jessiman | Deborah Stein
Bug | CLTL-358 | UAT-STEINTESTING-UAT Test 2 RETEST- Tenant end date is before start date | CLTL Sprint 3 | Done | Sarah Jessiman | Deborah Stein
Story | CLTL-368 | UAT-STEINTESTING-No option to process a payment via salesforce for Commercial tenants |  | To Do |  | Deborah Stein
Task | CLTL-324 | Account added to Qube as a current tenant even though there is already/still a current tenant. |  | Done | Lesley Richardson | Lesley Richardson
Task | CLTL-315 | Duplicate - Landlord & tenant Act Type is missing from Salesforce and interface to Qube |  | Done | Jacob Smycz | Deborah Stein
Task | CLTL-283 | UAT - Residential Offer screen has been updated to mirror the Commercial Offer screen |  | Done | Jacob Smycz | Deborah Stein
Task | CLTL-322 | UAT- AM Reports and Dashboards |  | Done |  | Deborah Stein
Task | CLTL-328 | UAT- STEIN TESTING- UAT Test 5- Qube Parent record Tenant Data Tab not populated |  | Done | Deborah Stein | Deborah Stein
Task | CLTL-367 | UAT- STEINTESTING-UAT R2-Regression Testing |  | Done |  | Deborah Stein
Task | CLTL-317 | UAT-STEIN TESTING UAT TEST 5- tenancy start date can be edited after the opportunity has moved to AUDIT stage and tenancy has been created |  | Done |  | Deborah Stein
Task | CLTL-326 | UAT-STEINTESTING UAT Test 5- Contact created without e mail address |  | Done |  | Deborah Stein
Task | CLTL-360 | UAT-STEINTESTING-UAT 12 retest 2- Multiple Units on Offer-tenancy agreement shows only the main unit |  | Done | Jacob Smycz | Deborah Stein
Task | CLTL-333 | UAT-STEINTESTING-UAT TEST 4 - Opportunity has been re named by GREP |  | Done | Deborah Stein | Deborah Stein
Task | CLTL-347 | UAT-STEINTESTING-UAT TEST 6 - Commercial Agreement on a non Commercial unit |  | Done |  | Deborah Stein
Task | CLTL-325 | Commercial tenant created on integration | CLTL GREP / Qube Changes | To Do | Jaic George | Lesley Richardson
Task | CLTL-350 | LR TEST of STEIN Testing-UAT Test 5 - Email address not populated on parent account | CLTL GREP / Qube Changes | Testing | Lesley Richardson | Lesley Richardson
Task | CLTL-363 | PMS not updating when future tenant created | CLTL GREP / Qube Changes | To Do | Lesley Richardson | Lesley Richardson
Task | CLTL-282 | UAT - Units incorrectly set up in Salesforce as Commercial Units | CLTL GREP / Qube Changes | To Do | Deborah Stein | Deborah Stein
Task | CLTL-281 | UAT - Commercial Unit Types-Qube Data cleanse | CLTL GREP / Qube Changes | To Do | Deborah Stein | Deborah Stein
Task | CLTL-262 | UAT - Integration of master data from Qube to Salesforce-tenant address | CLTL GREP / Qube Changes | To Do | Deborah Stein | Deborah Stein
Task | CLTL-279 | UAT - Mapping of Commercial Units from Qube to Salesforce-update required | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-265 | UAT - Residential/Amenity units listed as 'Commercial Unit' Record Types | CLTL GREP / Qube Changes | In Progress | Deborah Stein | Deborah Stein
Task | CLTL-355 | UAT - STEIN TESTING- UAT Test 5- Demand suite and Payment Method default is incorrect | CLTL GREP / Qube Changes | To Do | Venkat Ag | Deborah Stein
Task | CLTL-339 | UAT - STEINTESTING-UAT TEST 4-Qube Unit Data - No Lease End Diary is created | CLTL GREP / Qube Changes | In Review | Patricia Buck | Deborah Stein
Task | CLTL-343 | UAT -STEIN TESTING-UAT Test 4-Lease History not updated in Qube | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-361 | UAT TESTING-UAT Test 5 Re test- GREP Mapping Issue: Salesforce Data is not passing to Qube correctly | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-318 | UAT- STEIN TESTING UAT TEST 5-Incorrect population of Billing address | CLTL GREP / Qube Changes | To Do | Patricia Buck | Deborah Stein
Task | CLTL-351 | UAT- STEINTESTING- UAT Test 19 Guarantor in Qube | CLTL GREP / Qube Changes | To Do | Venkat Ag | Deborah Stein
Task | CLTL-331 | UAT- System GREP message | CLTL GREP / Qube Changes | To Do | Jaic George | Deborah Stein
Task | CLTL-345 | UAT- Tenancy failed to create in Qube because a Person account was selected as the tenant in Salesforce | CLTL GREP / Qube Changes | To Do | Deborah Stein | Deborah Stein
Task | CLTL-352 | UAT-STEINTESTING - UAT Test 19- Unit has not updated in Qube when lease is activated | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-337 | UAT-STEINTESTING UAT 2- Parent tenant Correspondence-Suppress demands should be NO | CLTL GREP / Qube Changes | In Progress | Deborah Stein | Deborah Stein
Task | CLTL-338 | UAT-STEINTESTING UAT TEST 4- Creation of Tenant records from Salesforce contacts | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-359 | UAT-STEINTESTING-UAT Test 12 Retest-GREP Mapping Issue- Multiple Units on One opportunity = | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-346 | UAT-STEINTESTING-UAT Test 12-GREP Mapping Issue-Company Name populating Qube Surname | CLTL GREP / Qube Changes | In Progress | Deborah Stein | Deborah Stein
Task | CLTL-366 | UAT-STEINTESTING-UAT TEST 18-Licence -PMS reference failed to update in SF and no dummy tenant created in Qube | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-364 | UAT-STEINTESTING-UAT Test 30-Update tenant details in Qube | CLTL GREP / Qube Changes | To Do | Phil Cullum | Deborah Stein
Task | CLTL-341 | UAT-STEINTESTING-UAT Test 4 - Unit- Break Clause data incorrectly not updated and Break Clause Diary is not created | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-340 | UAT-STEINTESTING-UAT Test 4- Unit-Next Rent Review date is incorrect | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Task | CLTL-354 | UAT-STEInTESTING-UAT Test 5-Unit is not updated in Qube | CLTL GREP / Qube Changes | In Review | Deborah Stein | Deborah Stein
Subtask | CLTL-196 | GREP Mapping for new Value - Commercial Licence Agreement Type | CLTL GREP / Qube Changes | To Do | Phil Cullum | Jacob Smycz
Subtask | CLTL-268 | Mapping changes for Opportunities | CLTL GREP / Qube Changes | In Progress | Venkat Ag | Venkat Ag
Subtask | CLTL-249 | New OffRamp Function App CommercialFutureTenancyQubeOffRamp | CLTL GREP / Qube Changes | Done | Venkat Ag | Venkat Ag
Subtask | CLTL-247 | New Offramp Logic Apps grep-la-commercialfuturetenancy-qube | CLTL GREP / Qube Changes | Done | Venkat Ag | Venkat Ag
Subtask | CLTL-248 | New Onramp Function App SalesforceCommercialFutureTenancyOnRamp | CLTL GREP / Qube Changes | Done | Venkat Ag | Venkat Ag
Subtask | CLTL-246 | New Onramp Logic Apps grep-la-salesforce-commercialfuturetenancy | CLTL GREP / Qube Changes | Done | Venkat Ag | Venkat Ag
Story | CLTL-280 | UAT - Commercial Units - Potential Units for Salesforce leasing journey | CLTL GREP / Qube Changes | To Do | Deborah Stein | Deborah Stein
Story | CLTL-1 | Create Future Commercial Tenancies in Qube [Grainger] | CLTL GREP / Qube Changes | Testing | Jaic George | Nikki
Bug | CLTL-334 | UAT - STEINTEST UAT Test 4- Tenant address is not populated in Qube if the Bill To address is blank in Salesforce | CLTL GREP / Qube Changes | Testing | Deborah Stein | Deborah Stein
Bug | CLTL-294 | UAT - System throwing generic error | CLTL GREP / Qube Changes | Done | Jaic George | Jaic George

## Backlog
Issue Type | Issue key | Summary | Sprint | Status | Assignee | Reporter
Story | CLTL-15 | Agent Inputs Viewings, Enquiries & Feedback [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-310 | Commercial Building Identifier - Duplicate [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-12 | Commercial Portfolio Dashboard [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-32 | Contact Billing Address - Not Required | Backlog | Done |  | Nikki
Story | CLTL-254 | Contracts related list for commercial opportunities - Addressed in CJR-143 | Backlog | Done | Jacob Smycz | Nikki
Story | CLTL-51 | Duplicate | Backlog | Done |  | Nikki
Story | CLTL-303 | Duplicate - Change Use Type to drop down [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-6 | Investment Committee Report [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-284 | OUT OF SCOPE - Commercial lease renewal-no agreement type can be populated [Future Release] | Backlog | To Do |  | Deborah Stein
Story | CLTL-80 | Remove RTR Fields from Company Account screen (Nice to Have) | Backlog | Done |  | Nikki
Story | CLTL-17 | Replace Tenancy Schedule [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-261 | UAT - Account Billing Address-New Field [Future Release] | Backlog | To Do |  | Deborah Stein
Story | CLTL-228 | UAT - Add additional Landlord and Tenant Act Details [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-260 | UAT - Agents-Accounts and contacts can be selected in the Local and National Agent fields on the Opportunity. [Future Release] | Backlog | To Do |  | Deborah Stein
Story | CLTL-223 | UAT - Auto Populate Agent Details on Opportunities [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-232 | UAT - Capture Agent Instruction details [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-220 | UAT - Capture Close Lost reasons more effectively [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-214 | UAT - Capture Rent Review Details on Offers [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-226 | UAT - Capture Stepped Rent Details as part of an offer [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-210 | UAT - Capture VAT details on Unit [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-211 | UAT - Commercial Agent Details on Unit - Maybe Deprecate ? [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-221 | UAT - Default Offer Line Item Quantity [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-222 | UAT - Easily Identify Commercial Buildings [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-375 | UAT - ELISABETA - Able to re-let a tenanted unit [Future Release] | Backlog | To Do |  | Patricia Buck
Story | CLTL-259 | UAT - Multiple units across multiple buildings cannot be incorporated into One Opportunity/Offer [Future Release] | Backlog | To Do |  | Deborah Stein
Story | CLTL-376 | UAT - RDay - Clear IC Approval Date on reverting stage [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-276 | UAT - Remove Lease Completion Statement Validation [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-218 | UAT - Rename 'Move In Date' field [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-216 | UAT - Require updated AM/IC approvals if Offers change [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-365 | UAT - S BLACKFORD - Closed Lost needs more reasons in dropdown [Future Release] | Backlog | To Do |  | Patricia Buck
Story | CLTL-299 | UAT - Send Approval Request to 2 AMs [Future Release] | Backlog | To Do |  | Nikki
Story | CLTL-230 | UAT - Send to Qube confirmation [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-227 | UAT - Update 'Tenancy Start Date' on Opps when Tenancy Signing Date is complete [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-215 | UAT - Update AFL Details on Opportunity [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-225 | UAT - Update Agent Account Record Type [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-316 | UAT - Use Type Picklist Values [Future Release] | Backlog | To Do |  | Jacob Smycz
Story | CLTL-336 | UAT- Commercial Contract created twice on same opportunity | Backlog | Done | Jacob Smycz | Deborah Stein
Story | CLTL-356 | UAT-STEINTESTING - UAT Test 17 - prevent changes to opps in Audit or Closed Won stages [Future Release] | Backlog | To Do |  | Deborah Stein
Story | CLTL-357 | UAT-STEINTESTING - UAT Test 25- Prevent moving to Audit Stage when previous steps are not complete [Future Release] | Backlog | To Do |  | Deborah Stein