## Debs Email
Ref | Action/Query | Responsibility | Status
2 | Remove Commercial-Let Agreement type from Salesforce as it is meaningless and not required | Open Box | Done https://graingerplc.atlassian.net/browse/CLTL-195
6 | First Break Clause Date-this is manually entered by users. Is it possible to amend this to calculate based on lease start date = number of months/years? | Open Box | Captured by Rebecca on her sheet
7 | Asset manager approval not yet built for testing-have all the fields been identified for inclusion in the notification to Asset managers? This includes calculations fields which will rely on all data required for the calculation being held in Salesforce. | Open Box | https://graingerplc.atlassian.net/browse/CLTL-11 being delivered in this sprint
8 | Stepped rents: There is no option to store the stepped rents on the opportunity or offer for commercial leases. E.g. . First 6m of lease at £1k pm, next 12 m at £1.5k, Next 12m at £2k etc.
Stepped rent functionality would be required to remove the dependency on the PV form (note however that not all commercial leases have stepped rents).
9 | What is the CLOSED DATE used for? Its currently populating as lease start date (move in date) = 1 month. Grainger never use this field. Should they be ? | Open Box | Required field in Salesforce. Defaulted to 1m. Updated when Opp is closed.
10 | Agreement for Lease: not all Commercial leases are subject to Agreement for Lease. AT the start of the Opportunity, user ticks Agreement for Lease if this is relevant. If this box is NOT ticked, user must still progress through AFL Workflow and Tab still appears at the top of the screen. If AFL is NOT ticked, can the AFL workflow and tab be hidden on screen as not relevant? | Open Box | Can add functionality re: marking if the AFL is needed or not. Removing from the path at the top is more complicated
11 | Rename the MOVE IN date on the Opportunity user Interface to “Tenancy Start Date” to avoid confusion (tenant move in date can differ from Lease start date). Do not rename the field in database as it will have been used in existing integrations and mapping etc. | Open Box | Makes sense and can do
12 | The Commercial MOVE in (Tenancy start date) is not always known at the start of the journey. The tenancy start date is usually the same as the Tenancy signing date on the Lease Completion section of the opportunity (much later in the process). user has to remember to go back and amend the original estimated Move in (Tenancy start date). Is it possible to auto populate/overwrite the Move In Date (Tenancy start date) with the Tenancy signing date? Or alternatively generate an alert/remind to the user when the Tenancy signing date is entered to remind user to amend the Move in (Tenancy start date)? | Open Box | Logged as an improvement
13 | FIT OUT : Fit out can occur before or after the Tenancy signing date but there is only area on the Opportunity to manage both scenarios. Further discussion required to establish how this will work and if additional fields are workflows ae required depending on the fit-out stage of the process. | Commercial Team/Open Box | Not started
14 | Local Agents are managed at a unit level. Is it possible to hold the agent on the unit so that it auto populates the opportunity rather than having to select the local agent on every opportunity. | Open Box | Captured by Rebecca on her sheet - agents should be accounts with contacts and agent account can be linked to a unit

## New Account
| Field | Request | Reason | JS Notes
1 | Pets | Field to be removed | Field not relevant for Commercial Accounts | OK
2 | RTR Expiry Date | Text to be removed | Nothing to fill out | OK
3 | RTR Time Limited | Text to be removed | Nothing to fill out | OK
4 | Leasing Agents - Minimum Fee | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Account level | Leasing Agents can/should be captured as Accounts/Companies - Maybe need an Agent type where these are shown. When an agent is listed on a unit (Something that is raised elsewhere) then the relevant fees can pull through to the opp etc
5 | Leasing Agents - Terms of Engagement | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Account level | See above
6 | QUERY - required information | Query | I thought we were told there were other fields other than Account Name that needed to be filled in before an account could be created? Email address in a certain format? If that's the case then can other fields be made required as appropriate. | Need to check impact - Email is required for the integrations but not necessarily to create. If the integration is wanting to make an account without an email, this could fail
7
8
9
10
11
12
13
14

## New Commercial Opportunity
| Field | Request | Reason | JS Notes
1 | Local Agent | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated
2 | Local Agent Contact | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated
3 | National Agent | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated
4 | National Agent Contact | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit, not relevant at the Opportunity level | Mentioned elsewhere - pull through from the unit. Issues are that if the unit is updated and changed to have different agents, then all records will be updated
5 | Agreement Type | Amend to drop-down list | Too many options, we should provide a list of what Commercial team are likely to use. Possible list: 1. Commercial Lease (need to find out why we have Commercial Lease AND Commercial Let, not sure what the diff is?) - Ideally auto-filled as this 2. Parking Licence 3. Tenancy at Will | Have removed Commercial Let already, added in Commercial Licence. Tenancy at will is new, but can be added
6 | Use Type | QUERY | Where does this info go, where does it get reported. Need consensus on what should be input here - e.g. E class or 'Retail' or 'Café' | Up to Grainger to decide on their business rules here
7 | Move In Date | QUERY | What happens with this date? Can we add text to advise e.g. 'Input estimated move-in date'# | This field is shared with resi so any help text will be seen by all people. Might be best to know in a commercial context that this can move.
8
9
10
11
12
13
14

## Create Commercial Offer
| Field | Request | Reason | JS Notes
1 | Select Building | Limit drop-down list to only show commercial buildings | For creating commercial offers we only need to see commercial buildings. | Buildings currently are not differentiated by their use type ie. Commercial or residential. Can be done
2 | Agreement Type | Amend drop-down list | Drop-down list to be amended/ shortened if we also amend this on 'New Commercial Opportunity' page. | Yes should be just the commercail ones
3 | Tenant Incentives - First Break Clause Date | To be number of months until the first break | Allows the break date to be automatically recalcualted as the estimated lease completion date moves. We also negotiate based on 'break at year 5' so is quicker to understand the offer if we can see the offer in this format. Months required to allow for breaks at 18m or other non whole-year negotiations. | OK
4 | Tenant Incentives - First Break Clause Date | Add a calculation of months into years | If 18m is input then will state '1.5 years', if 36m is input then will state '3 years'. Gives clarity as to what terms have been negotiated. | What does this mean/what is the benefit?
5 | n/a | Break Clause to be its own section | Break clauses are not incentives so should be in own section, separate to Capital Contribution. | OK
6 | Rent Free Months | To be added to Tenant Incentives Section | Rent free periods are tenant incentives, so we might want to move this field in to the Tenant Incentives section - Commercial Team to review and confirm. | OK
7 | Rent Review fields | To be added into the Offers page | Rent Reviews will be negotiated at the offer level. | Add to offer and then fill on opp from selected primary offer
8 | Agent Fee Information | Field to be removed | We should be catching Agent information at the Unit level as the agent will be instructed on the unit. | Mentined elsewhere
9 | Deposit | Field to be added | The deposit may change between offers. Happy for this to be a field we input the agree deposit in £ (could be complicated to calculate 3 or 6m deposit if there are stepped rents or if VAT is due on some properties but not others) | OK - for OpenBox, do we put the Security Deposit (Override) field on the offer here

## Amend Offer Line Item
| Field | Request | Reason | JS Notes
1 | Quantity | Make this uneditable/ remove field | If this always has to be '1' then no requirement to have this as an editable field. Ensures this is not overwritten with another number. | Makes sense - need to remove from lighning page layout and ensure that it always set to one. This makes sense for all offer line items, there can only ever be one of a unit

## Amend Opportunity Details
| Field | Request | Reason | JS Notes
1 | Sub Stage | Remove this field | Nothing to select | There are 3 values for Sub stage when opp is closed lost - these should be moved to lost reason. Then can remove this substage field
2 | Landlord Solicitor | Make a free text field | We don't need to hold this information in Qube following completion, can we just type this in as a reference field for the Commercial Team. No need to create a whole contact entry. | The solicitor should be an account as this is a relationship that grainger will want to track.
3 | Solicitor Contact | Make a free text field | We don't need to hold this information in Qube following completion, can we just type this in as a reference field for the Commercial Team. No need to create a whole contact entry. | This should be a contact as it will be a specific agent, eg Bob Smith, and is a relationship grainger will want to track
4 | Status | QUERY | Will this auto-update to 'accepted' and 'rejected' as the deal progresses? | Which status?
5 | Rent Review | Require addtiional fields? | • Tick box for 'upwards only' • How do we record cap and collar on RPI? • Do we need to include a % field for indexed rent e.g. RPI + 2% Commercial team to review and advise. | Grainger to review and update
6 | First Rent Review Date | To be in years from lease start | Allows the RR date to be automatically recalcualted as the estimated lease completion date moves. We also negotiate based on 'RR at year 5' so is quicker to understand the offer if we can see the offer in this format. | Should this be on the offer? Calculated on the actual move in date?
7 | n/a | New tick box 'no Rent Review' | If no rent review then box to be checked - makes it clear field hasn't been missed if left empty. | Should this be on the offer?
8 | Additional Offer Details ' Required Notice (Months) | QUERY | Not sure what this relates to, could be removed?
9 | Security Deposit (Override) | To be removed | To be included in the Offer section, rather than the opportunity. | mentioned on the offer tab - OK
10 | Deposit to be Paid Back | To be removed | To be included in the Offer section, rather than the opportunity. | OK
11 | VAT | Auto-populated | VAT is due depending on whether the property is opted for tax, this should be updated at the property or unit level by our finance team and just pull through to show us whether VAT is applicable or not. | This needs to be captured on the unit. Currently not a place for this to be stored, and then to be mass uploaded/integrated from qube?
12 | Other notes | QUERY | Commercial team to review - do we want a field specifically about parking spaces or rights to park. Might help for future reporting?
13 | Agent Fee | QUERY | Where is this pulling from? We should hold information at the unit level on: agents appointed, date of appointment, the % basis of instruction and their minimum fee. | This is set by default as 10% when the offer is created. It can be manually changed. A fee percentage could be held at a unit level (if this is set unit by unit) but there is nowhere to store this right now. For openbox, this would need to be a flow that defaults the value to what is on the unit at the time of the offer being created, but allow for it to be manuallt changed if needed.
14 | Approval | QUERY | How will this record where IC approve one offer but then we renegotiate a new offer from the same tenant and the second offer goes for IC sign off? Which IC approval date will be shown, how will the date get updated? | Why would an offer get accepted by IC then be renegotiated? Would it not then need to be AM and IC approved again?
15 | Lease plan Status | Change drop-down options | Blank, Requested, Received | OK
16 | Tenant Planning & Licensng | QUERY | We may want to add a tick box for both licensing and planning to tick when these have been approved - difficult to tell if the approval date is an estimated date that has passed without receiving planning, or if the date has passed and planning was received on that date.
17 | Technical Informaiton' section | QUERY | This whole section needs review - how are we reporting on this info. Not sure this is best way to track it as it currently stands. | Grainger to review and update
18 | Agreement for Lease | Add 'AFL signed' field | Need a date field for when AFL completes. | OK