## Task Setup - NTQ
Workflow | Phase | Task Name | Queue Type | Expected Duration (Days) | Custom Start Date Type | Preceding Tasks | Works Type | Relet / Sell | Information | Screen flow: Fields Required on Task Completion | Screen flow: EOT Fields Updated on Task Completion
Tenant Gives NTQ | Receive Notice | Validate Notice | Centralized PM | 1 | Void Start Date |  |  |  | In order to complete this task: • Check Tenancy to confirm notice is allowed. • Check if there is parking that needs to be processed at the same time. | Unit to be Relet; Unit to be Sold
Tenant Gives NTQ | Receive Notice | Confirm Notice | Centralized PM | 1 |  | Validate Notice |  |  | In order to complete this task: • Notify residents that notice has been accepted or denied via phone call and email. • Send DRI and Steps to Vacating forms to tenant for them to complete. • Update key location on Unit. • Update Qube. | Reason for Vacancy; FV Date; FV Date is Confirmed; PVI Date; PVI Time
Tenant Gives NTQ | Notify Stakeholders | Notify Stakeholders | Centralized PM | 1 |  | Confirm Notice |  |  | In order to complete this task: • Update Qube details. • Create MiMo tasks. • Create Work Order in Evolution for external inventory clerks. • Update British Gas Portal.
Tenant Gives NTQ | Notify Stakeholders | Check Compliance | Centralized PM | 7 |  | Confirm Notice |  |  | In order to complete this task: • Ensure all required documents are in date. • Get up-to-date documents if required. • Save documents in correct folder. | EPC Status; EPC Expiry Date; EICR Status; EICR Expiry Date; CP12 Status; CP12 Expiry Date.
Tenant Gives NTQ | Notify Stakeholders | Confirm PVI Date | Onsite PM | 1 |  | Confirm Notice Check Compliance |  |  |  | PVI Date; PVI Time; PVI Notes for Axis; Key Location - Axis Voids; Works Type | PVI Date & Time is Confirmed = True
Tenant Gives NTQ | Notify Stakeholders | Amend Direct Debit | Finance | 2 |  | Confirm Notice |  |  | In order to complete this task: • Apportion final rent collection.
Tenant Gives NTQ | Notify Stakeholders | Set Rent | Letting | 3 |  | Confirm Notice |  | Relet |  | Unit Marketing Status; Picklist: • On the Market Available to View • On the Market - No Access
Tenant Gives NTQ | PVI | PVI | Onsite PM | 1 | PVI Date |  |  |  | In order to complete this task: • Complete PVI. • Follow up contact with tenant with details of repairs, information and deposit release. | Works Type | PVI Completed Date = Task's Actual End Date
Tenant Gives NTQ | Book Works | Approve CapEx | Asset Management | 3 |  | PVI | Refresh, Refurb
Tenant Gives NTQ | Book Works | Book Works | Centralized PM | 4 |  | PVI |  |  | In order to complete this task: • Confirm works required after PVI. • Collect quotes for works and repairs. • Book works in FSI and arrange contractor’s access for Vacate Date. • Book cleaning.
Tenant Gives NTQ | Move Out | Check Out | Onsite PM | 1 | FV Date |  |  |  | In order to complete this task: • Keys have been handed back. • Final inspection completed. • Update Qube details. • Confirm access with inventory clerk (if required). | Actual Vacant Date; Key Location - Axis Voids
Tenant Gives NTQ | Move Out | Check Unit Condition | Onsite PM | 1 | FV Date |  |  |  | In order to complete this task: • Compare PVI and final inspection, and adjust works if needed. • Save checkout report to EoT. • Compare Move-in and Move-out inventory. • Complete ROD and notify Credit Control. |  | Works Start Date = Task's Actual End Date
Tenant Gives NTQ | Move Out | Close Down Tenancy | Finance | 5 |  | Check Out |  |  | In order to complete this task: • Close tenancy and mark relet status on Qube.
Tenant Gives NTQ | Move Out | Cancel Direct Debit | Finance | 2 |  | Check Out |  |  | In order to complete this task: • Cancel DDM after move out confirmation.
Tenant Gives NTQ | Refurb/Refresh | Review Check Out Report | Centralized PM | 3 |  | Check Unit Condition
Tenant Gives NTQ | Refurb/Refresh | Finalize Check Out | Centralized PM | 4 |  | Check Unit Condition |  |  | In order to complete this task: • Send checkout report to Tenant. • Notify Council Tax. • Notify any remaining utilities. • Diarise flushing for void unit.
Tenant Gives NTQ | Refurb/Refresh | Refresh | Onsite PM | 5 |  | Check Unit Condition | Refresh
Tenant Gives NTQ | Refurb/Refresh | Refurb | Onsite PM | 15 |  | Check Unit Condition | Refurb
Tenant Gives NTQ | Refurb/Refresh | Clean Unit | Onsite PM | 1 |  | Check Unit Condition, Refurb, Refresh | Refresh, Refurb, Clean Only |  |  | Works End Date
Tenant Gives NTQ | Release Deposit | Deposit Release | Finance | 3 |  | Finalize Check Out |  |  | When RTA gets emailed to process refund, this task can be marked off as complete. | Deposit Stoppage Type, Deposit Stoppage Amount | Deposit Return Date = Task's Actual End Date
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was 2
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was 7

## Task Setup - GT
Workflow | Phase | Task Name | Queue Type | Expected Duration (Days) | Custom Start Date Type | Preceding Tasks | Works Type | Relet / Sell | Information Displayed to User in Task
Grainger Trust NTQ | Receive Notice | Validate Notice | Centralized PM | 1 | Void Start Date |  |  |  | In order to complete this task: • Check Tenancy to confirm notice is allowed. • Check if there is parking that needs to be processed at the same time.
Grainger Trust NTQ | Receive Notice | Confirm Notice | Centralized PM | 1 |  | Validate Notice |  |  | In order to complete this task: • Notify residents that notice has been accepted or denied via phone call and email. • Update key location on Unit. • Update Qube.
Grainger Trust NTQ | Notify Stakeholders | Notify Stakeholders | Centralized PM | 1 |  | Confirm Notice |  |  | In order to complete this task: • Update Finance to amend Qube • Update British Gas Portal.
Grainger Trust NTQ | Notify Stakeholders | Check Compliance | Centralized PM | 7 |  | Confirm Notice |  |  | In order to complete this task: • Ensure all required documents are in date. • Get up-to-date documents if required. • Save documents in correct folder.
Grainger Trust NTQ | Notify Stakeholders | Confirm PVI Date | Onsite PM | 1 |  | Check Compliance
Grainger Trust NTQ | Notify Stakeholders | Amend Direct Debit | Finance | 2 |  | Confirm Notice |  |  | In order to complete this task: • Apportion final rent collection.
Grainger Trust NTQ | Notify Stakeholders | Set Rent | Letting | 3 |  | Confirm Notice |  | Relet
Grainger Trust NTQ | PVI | PVI | Onsite PM | 1 | PVI Date |  |  |  | In order to complete this task: • Complete PVI. • Follow up contact with tenant with details of repairs, information and deposit release.
Grainger Trust NTQ | Book Works | Approve CapEx | Asset Management | 3 |  | PVI | Refresh, Refurb
Grainger Trust NTQ | Book Works | Book Works | Centralized PM | 4 |  | PVI |  |  | In order to complete this task: • Confirm works required after PVI. • Book cleaning.
Grainger Trust NTQ | Move Out | Check Out | Onsite PM | 1 | FV Date |  |  |  | In order to complete this task: • Keys have been handed back. • Final inspection completed. • Update Finance to amend Qube
Grainger Trust NTQ | Move Out | Close Down Tenancy | Finance | 5 |  | Check Out |  |  | In order to complete this task: • Close tenancy and mark relet status on Qube.
Grainger Trust NTQ | Move Out | Cancel Direct Debit | Finance | 2 |  | Check Out |  |  | In order to complete this task: • Cancel DDM after move out confirmation.
Grainger Trust NTQ | Refurb/Refresh | Review Check Out Report | Centralized PM | 3 |  | Check Out
Grainger Trust NTQ | Refurb/Refresh | Finalize Check Out | Centralized PM | 4 |  | Check Out |  |  | In order to complete this task: • Notify any remaining utilities. • Diarise flushing for void unit.
Grainger Trust NTQ | Refurb/Refresh | Refresh | Onsite PM | 5 |  | Check Out | Refresh
Grainger Trust NTQ | Refurb/Refresh | Refurb | Onsite PM | 15 |  | Check Out | Refurb
Grainger Trust NTQ | Refurb/Refresh | Clean Unit | Onsite PM | 1 |  | Check Out, Refurb, Refresh | Refresh, Refurb, Clean Only
Grainger Trust NTQ | Refurb/Refresh | Check Unit Condition | Onsite PM | 1 |  | Clean Unit |  |  | In order to complete this task: • Compare PVI and final inspection, and adjust works if needed. • Complete ROD and notify Credit Control.
Grainger Trust NTQ | Release Deposit | Deposit Release | Finance | 3 |  | Finalize Check Out |  |  | When RTA gets emailed to process refund, this task can be marked off as complete.

## Task Setup - Grainger Trust (hidden)
Workflow | Phase | Task Name | Queue Type | Expected Duration (Days) | Custom Start Date Type | Preceding Tasks | Works Type | Relet / Sell | Information | Screen flow: Fields Required on Task Completion | Screen flow: EOT Fields Updated on Task Completion
Grainger Trust EOT | Receive Notice | Validate Notice | Centralized PM | 1 | Void Start Date |  |  |  | In order to complete this task: • Check Tenancy to confirm notice is allowed. • Check if there is parking that needs to be processed at the same time. | Unit to be Relet; Unit to be Sold
Grainger Trust EOT | Receive Notice | Confirm Notice | Centralized PM | 1 |  | Validate Notice |  |  | In order to complete this task: • Notify residents that notice has been accepted or denied via phone call and email. • Send DRI and Steps to Vacating forms to tenant for them to complete. • Update key location on Unit. • Update Qube. | Reason for Vacancy; FV Date; FV Date is Confirmed; PVI Date; PVI Time
Grainger Trust EOT | Notify Stakeholders | Notify Stakeholders | Centralized PM | 1 |  | Confirm Notice |  |  | In order to complete this task: • Update Qube details. • Create MiMo tasks. • Create Work Order in Evolution for external inventory clerks. • Update British Gas Portal.
Grainger Trust EOT | Notify Stakeholders | Check Compliance | Centralized PM | 7 |  | Confirm Notice |  |  | In order to complete this task: • Ensure all required documents are in date. • Get up-to-date documents if required. • Save documents in correct folder. | EPC Status; EPC Expiry Date; EICR Status; EICR Expiry Date; CP12 Status; CP12 Expiry Date.
Grainger Trust EOT | Notify Stakeholders | Confirm PVI Date | Onsite PM | 1 |  | Check Compliance |  |  |  | PVI Date; PVI Time; PVI Notes for Axis; Works Type | PVI Date & Time is Confirmed = True
Grainger Trust EOT | Notify Stakeholders | Amend Direct Debit | Finance | 2 |  | Confirm Notice |  |  | In order to complete this task: • Apportion final rent collection.
Grainger Trust EOT | Notify Stakeholders | Set Rent | Letting | 3 |  | Confirm Notice |  | Relet |  | Unit Marketing Status; Picklist: • On the Market Available to View • On the Market - No Access
Grainger Trust EOT | PVI | PVI | Onsite PM | 1 | PVI Date |  |  |  | In order to complete this task: • Complete PVI. • Follow up contact with tenant with details of repairs, information and deposit release. | Works Type | PVI Completed Date = Task's Actual End Date
Grainger Trust EOT | Book Works | Approve CapEx | Asset Management | 3 |  | PVI | Refresh, Refurb
Grainger Trust EOT | Book Works | Book Works | Centralized PM | 4 |  | PVI |  |  | In order to complete this task: • Confirm works required after PVI. • Collect quotes for works and repairs. • Book works in FSI and arrange contractor’s access for Vacate Date. • Book cleaning.
Grainger Trust EOT | Move Out | Check Out | Onsite PM | 1 | FV Date |  |  |  | In order to complete this task: • Keys have been handed back. • Final inspection completed. • Update Qube details. • Confirm access with inventory clerk (if required). | Actual Vacant Date; AXIS KEY LOC |  | Updates Tenancy Status & Actual Move Out Date
Grainger Trust EOT | Move Out | Check Unit Condition | Onsite PM | 2 | FV Date |  |  |  | In order to complete this task: • Compare PVI and final inspection, and adjust works if needed. • Save checkout report to EoT. • Compare Move-in and Move-out inventory. • Complete ROD and notify Credit Control. |  | Works Start Date = Task's Actual End Date
Grainger Trust EOT | Move Out | Close Down Tenancy | Finance | 5 |  | Check Out |  |  | In order to complete this task: • Close tenancy and mark relet status on Qube.
Grainger Trust EOT | Move Out | Cancel Direct Debit | Finance | 2 |  | Check Out |  |  | In order to complete this task: • Cancel DDM after move out confirmation.
Grainger Trust EOT | Refurb/Refresh | Review Check Out Report | Centralized PM | 3 |  | Check Unit Condition
Grainger Trust EOT | Refurb/Refresh | Finalize Check Out | Centralized PM | 4 |  | Check Unit Condition |  |  | In order to complete this task: • Send checkout report to Tenant. • Notify Council Tax. • Notify any remaining utilities. • Diarise flushing for void unit.
Grainger Trust EOT | Refurb/Refresh | Refresh | Onsite PM | 7 |  | Check Unit Condition | Refresh
Grainger Trust EOT | Refurb/Refresh | Refurb | Onsite PM | 15 |  | Check Unit Condition | Refurb
Grainger Trust EOT | Refurb/Refresh | Clean Unit | Onsite PM | 1 |  | Check Unit Condition, Refurb, Refresh | Refresh, Refurb, Clean Only
Grainger Trust EOT | Release Deposit | Deposit Release | Finance | 3 |  | Finalize Check Out |  |  | When RTA gets emailed to process refund, this task can be marked off as complete. | Deposit Stoppage Type, Deposit Stoppage Amount | Deposit Return Date = Task's Actual End Date

## EOT Fields
Field Name | Editable on EOT Details Screen? | Field Type & Content | Required? | Default Value on Creation | Validations | Business Rules & Automated Updates
EOT Name | No | Text | Required | EOT - [Unit's Plot No.]
EOT Number | No | Text | Required | System generated
Tenancy | No | FK to Tenancy Object | Required | Selected tenancy
Status | No - Editable via Close / Cancel screen flow | Picklist: • Active • Complete • Cancelled • Closed - Tenant Retained • Closed - NTQ Denied • Pending Cancel/Close | Required | Active |  | Status updates from 'Active' to 'Complete' when the last EOT phase is complete. When Closing/Cancelling an EOT: If first EOT phase is complete & the user is not EOT Owner => Close / Cancel approval request is created & EOT status is set to 'Pending Cancel/Close'. Status updates from 'Active' to 'Pending Cancel / Close' when cancel/close approval request is created. Status updates from 'Pending Cancel/Close' to 'Active' when cancel/close approval request is rejected.
EOT Template | No | Picklist: • Tenant Gives NTQ | Required
Owner | Yes | User list | Required | Unit's unit manager (if active & they have a full Salesforce license)
Unit | No | FK to Unit Object | Required | Unit linked to tenancy | Cannot create an EOT if there is already an EOT for the unit in Active or Pending Cancel/Close status.
Building | No | FK to Building Object | Required | Building linked to tenancy
Notes | Yes | Long text | Optional
Start Date | No | Date | Required | Date EOT is created
Notice to Quit Date | Yes | Date | Required | Date EOT is created
PVI Date | Yes | Date | Required | If FV Date is more than 32 days after today = [FV Date - 28 days] If FV Date is between 4 and 32 days after today = [Current Date + 4 days] If FV Date is less than 4 days after today = [FV Date] | Must be after Start Date | Default value may be edited. Only defaults on initial Create EOT screen.
PVI Time | Yes | Time | Optional | Null | Required where "PVI Date & Time Is Confirmed" is true.
PVI Date & Time Is Confirmed | Yes | Boolean | Optional | False |  | Flagged as true when the user completes the 'Confirm PVI Date' task.
PVI Completed Date | No | Date | Optional |  |  | Automatically populated with PVI task's actual end date.
Future Vacant Date | Yes | Date | Required |  | Must be after Start Date | Where FV Date is edited and the 'Amend Direct Debit' task is in the 'Complete' or 'N/A' status, the task will be automatically set back to an 'Active' status.
Future Vacant Date Is Confirmed | Yes | Boolean | Optional | False
Actual Vacant Date | No | Date | Optional |  |  | Defaults to Future Vacant date when closing 'Check Out' task; may be edited.
Works Start Date | No | Date | Optional |  |  | Automatically populated with Check Unit Condition task's actual end date.
Works End Date | No | Date | Optional |  |  | Captured on closing Clean Unit task
Available Date | No | Date | Optional | = [Max [Actual End Date, else Target End Date] of all tasks with a Works Type that are not in 'N/A' status] + 1 day |  | Recalculated automatically as timelines change.
Completion Date | No | Date | Optional | = Max Target End Date of all tasks not in 'N/A' status. |  | Recalculated automatically as timelines change. Updates to the date the EOT status updates to 'Complete'.
Next Move In Date | No | Date | Optional |  |  | Automatically populated with the next Tenancy Start Date - • When a Tenancy with Tenancy Type ‘New’ has Tenancy Status changed to 'Activated': Updates the EOT for the same Unit that is in ‘Active’ or ‘Complete’ Status & has the greatest Start Date. • When the Tenancy Start Date is edited for a Tenancy with Tenancy Type ‘New’ & Tenancy Status 'Activated': Updates the EOT with the same Unit that is in ‘Active’ or ‘Complete’ Status & has the greatest Start Date.
Passing Monthly Rent | No | Currency | Optional | = [Tenancy’s Monthly Rent] x (1 + [Tenancy's Uplift]) ^ [Number of full years between Tenancy Start Date & current date]
Reason for Vacancy | Yes | Single-select Picklist | Optional
Unit to be Relet | Yes | Boolean | Optional | True
Unit to be Sold | Yes | Boolean | Optional | False
EOT Works Type | Yes | Picklist: • Clean Only • Refresh • Refurbishment | Optional | Clean Only
Deposit Deduction Type | No | Picklist: • No Deductions • Deductions - Agreed with Resident • Deductions - Disputed | Optional
Deposit Deduction Amount | No | Currency | A non-zero value is required when the Deposit Deduction Type is either ‘Deductions - Agreed with Resident’ or ‘Deductions - Disputed’.
Deposit Return Date | No | Date | Optional |  |  | Automatically populated with Deposit Return task's actual end date.
PVI Notes for Axis | Yes | Long text | Optional |  |  | Only displays where a unit is Under Full Axis Contract
Current Phase | No | FK to EOT Phase object | Required | First Phase per the task template. |  | Automatically updates to the first phase not in a 'Complete' status.
Close Reason | No - Editable via Close / Cancel screen flow | Picklist - Options are dependent on the EOT Status | Required where EOT Status is changed to a Closed or Cancelled status or to Pending Cancel/Close.
Close Detail | No - Editable via Close / Cancel screen flow | Text | Optional
EOT Status for Axis | Calculated Field | Text | Required | Active |  | = If Unit to be Sold = True → Unit to be Sold Otherwise, the value will be determined by the EOT Status: Active OR Pending Cancel/Close → Active Cancelled OR Closed - Tenant Retained OR Close - NTQ Denied → Cancelled Complete → Complete
PVI Completed to Vacant (Days) | Calculated Field | Integer | Optional | # of days from [PVI Completed Date] to [Actual Vacant Date]
Vacant Date to Deposit Returned (Days) | Calculated Field | Integer | Optional | # of days from [Actual Vacant Date] to [Deposit Return Date]
Vacant Date to Ready to Let (Days) | Calculated Field | Integer | Optional | # of days from [Actual Vacant Date] to [Available Date]
Vacant Date to Move In (Days) | Calculated Field | Integer | Optional | # of days from [Actual Vacant Date] to [Next Move-In Date]
Total Rent Loss | Calculated Field | Currency | Optional | = [Monthly Passing Rent] x 12 ÷ 365 x [Vacant Date to Move In (Days)]
Axis Fields Last Modified | Updated via Trigger | Date & Time | Optional |  |  | Set to current date when EOT created & update when any of the following fields on the EOT are updated: Unit to be Sold, EOT Status, EOT Owner, Works Type, PVI Date, PVI Time, PVI Date & Time is Confirmed, Future Vacant Date, Notes for Axis.
Axis Fields Modified | Updated via Trigger | Text | Optional |  |  | GIVEN none of the above fields have been updated on an EOT since the Axis report was scheduled to last send THEN save the field name(s) AND overwrite any existing value. GIVEN one or more of the above fields has already been updated on an EOT since the Axis report was scheduled to last send WHEN one or more of the above fields is updated THEN the field name(s) will be appended to any existing values already saved in Axis Fields Modified
Note on C26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: • Relocation within City • Relocation - UK • Purchased Own Property • Rent Too High • Relocation - Overseas • Lack of Service - Grainger/Agent • Transfer to Grainger Property • Tenant Evicted • Abandoned • Rehoused by Local Authority • Tenant Deceased
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Options for ‘Close - NTQ Denied’: - No Break Clause - Poor Timing Options for ‘Cancel’: - Created by Mistake - Testing Options for ‘Close - Tenant Retained’: - Repair/Improvement Offered - Customer Changed Mind

## Phase Fields
Field Name | Editable? | Field Type & Content | Required? | Default Value | Business Rules
EOT Phase Name | No | Text | Required | Per task template.
Status | No | • Pending • In Progress • Complete | Required | First phase is 'In Progress', all other phases default to 'Pending'. | If any task in a phase is moved to In Progress, OR one of multiple incomplete tasks is set to Complete: The Phase status is updated to 'In Progress' (regardless of whether the preceding phase is complete). When the final open task in a phase is updated to a status of ‘N/A’ or ‘Complete’, the phase status is updated to 'Complete'.
Sequence | No | Integer | Required | Per task template.

## Task Fields
Field Name | Editable on Task Details Screen? | Field Type & Content | Required? | Default Value on Task Creation | Business Rules & Automated Updates
Task Name | Yes | Short Text | Required | Per Task Setup
EOT | No | FK to EOT object | Required | EOT
EOT Phase | No | FK to EOT Phase object | Required | Per Task Setup
Unit | No | FK to Unit object | Required | Tenancy's unit
Owner | Yes | User / Queue | Required | Queue configured as the EOT Team for the EOT's Building and the tasks' Queue Type per the task setup. | If Owner is a queue, this is updated to the current user when the user clicks the ‘Start Task’ button.
Task Team | No | Queue | Required | Queue configured as the EOT Team for the EOT's Building and the tasks' Queue Type per the task setup. | When the task Owner is updated from an individual to a queue OR from one queue to another queue, the Task Team will be updated to the same queue.
Task Status | No | Picklist: • Pending • Active • In Progress • Complete • N/A | Required | Pending | If configured with preceding task(s): When 'Pending' & the final, open preceding task’s status changes to ‘N/A’ or ‘Complete’ => ‘Active’. When 'Active' and a preceding task is re-opened => ‘Pending’. Tasks flagged as relet tasks are updated to 'N/A' if Unit to be Relet is updated to false, and are updated to 'Active' or 'Pending' if Unit to be Relet is updated to true. Tasks with a Works Type are updated to/from 'N/A' when the EOT Works Type changes. If Start Date Type is FV Date: When ‘FV Date is Confirmed’ is updated to true => ‘Active’. When ‘FV Date is Confirmed’ is updated to false => 'Pending’. If Start Date Type is PVI Date: When ‘PVI Date is Confirmed’ is updated to true => ‘Active’. When ‘PVI Date is Confirmed’ is updated to false => ‘Pending’. When user selects 'Start Task' button => 'In Progress' When the EOT Status changes to a cancelled or closed status & a task is open => 'N/A'
Start Date Type | No | Picklist: • Predecessor Task • EOT Start Date • PVI Date • Future Vacant Date | Required | Per Task Setup
Start Date | No | Date | Required | = FV Date, PVI Date or EOT Start Date where the tasks' Start Date Type is one of those, otherwise = Last [Actual End Date, or if none then Target End Date] for each preceding task that is not in a ‘N/A’ status. | Automatically updates until the task is complete.
Target End Date | No | Date | Required | = [Start Date] + [Expected Duration] | Automatically updates until the task is complete.
Actual Start Date | No | Date | Optional |  | When a task with Status 'Pending', 'Active' or 'N/A' changes to 'In Progress' or 'Complete', then the current date is saved as Actual Start Date. If task Status is updated to 'Pending', 'Active' or 'N/A' => Actual Start Date is deleted.
Actual End Date | No | Date | Optional |  | Automatically populated with the date that the as Task Status is updated to Complete. If task Status is updated to 'Pending', 'Active' or 'N/A' => Actual End Date is deleted.
Expected Duration | No - Updated via the Adjust Task Timeline screen flow | Integer | Required | Per Task Setup | Updated to 'KPI Duration' where user elects to 'Reset Task Timeline'
KPI Duration | No | Integer | Required | Per Task Setup
Actual Duration | Calculated | Integer | Optional | Where task status is 'Complete': = # of days between task [Start Date] and [Actual End Date]
Expected Delay Days | Calculated | Integer | Optional | Where the task status is not ‘N/A’: = [Expected Duration] - [KPI Duration]
Delay Reason | No - Updated via the Adjust Task Timeline or Close Task screen flows | Picklist: • Contractor Delays • Bank Holiday • Task Owner Sick • Resource Unavailable • Other | Required where Actual End Date is 2 or more days after Target End Date AND/OR Expected Duration> KPI Duration |  | Deleted where user elects to 'Reset Task Timeline'
Delay Detail | No - Updated via the Adjust Task Timeline or Close Task screen flows | Text (max 255) | Required where Delay Reason is 'Other' |  | Deleted where user elects to 'Reset Task Timeline'
Overdue Days | Calculated | Integer | Optional | Where the task status is 'Pending', 'In Progress' or 'Active' AND Target End Date < current date = # of days from [Target End Date] to [Current Date] Where the task status is ‘Complete’ = [Actual Duration] - [Expected Duration]
Task Overdue | Calculated | Boolean | Optional | True where Overdue Days > 0
Notes | Yes | Long Text | Optional
Information | No | Long Text | Optional | Per Task Setup
Closure Reason | No - Updated via Close Task screen flow. | Text | Required when task status is updated to 'N/A'
Relet/Resell | No |  | Optional |  | Backend configuration. Determines whether the task is applicable when the unit is flagged for relet or sale.
Works Type | No |  | Optional |  | Backend configuration. Determines whether the task is applicable for the works type & is used to calculate Available Date.

## Updates to Other Objects
Object Updated | Field Updated | Trigger | Update to
Unit | Future Vacant Date | WHEN the first End of Tenancy phase is completed | EOT's Future Vacant Date
GIVEN an EOT is no longer in the first phase WHEN a user edits the EOT’s Future Vacant Date
Unit | Available Date | WHEN the first End of Tenancy phase is completed | EOT's Available Date
GIVEN an EOT is no longer in the first phase WHEN the EOT’s Available Date is recalculated
Unit | Unit Status | WHEN the first End of Tenancy phase is completed | "Future Vacant"
|  | WHEN the EOT's 'Unit Marketing Status' is selected on closing the 'Set Rent' task. | EOT's Unit Marketing Status
Tenancy | Tenancy Status | GIVEN an Opportunity has (only) one associated Agreement that is: In a ‘Signed’ Agreement Status, and Is linked to a Tenancy with a Tenancy Type ‘New’ WHEN the Opportunity’s Current Stage is updated to ‘Audit’ | 'Activated'
| Status |  | 'Activated'
Tenancy | Tenancy Status | WHEN the EOT Check Out task is completed (i.e. the Actual Vacant Date is populated). | 'Ended'
| Actual Move Out Date |  | EOT's Actual Vacant Date
Unit | EPC Status; EPC Expiry Date; EICR Status; EICR Expiry Date; CP12 Status; CP12 Expiry Date. | WHEN the EOT Check Compliance task is completed | EPC Status; EPC Expiry Date; EICR Status; EICR Expiry Date; CP12 Status; CP12 Expiry Date.

## Axis Report
Report Column | End Of Tenancy Number | Axis Fields Last Modified | Axis Fields Modified | EOT Status for Axis | Block | Unit Address | Portfolio | End of Tenancy Works Type | PVI Date | PVI Time | Future Vacant Date | Key Location - Axis Voids | PVI Notes for Axis | EPC Status | EPC Expiry Date | EICR Status | EICR Expiry Date | CP12 Status | CP12 Expiry Date | Unit Manager | Unit Manager Email | Unit Manager Phone Number | Unit Manager Mobile Number | Customer | Customer Email | Customer Phone Number | Customer Mobile Number
Sample Data | EoT-00344 | 15/03/2024 13:31 | PVI Time; PVI Date & Time is Confirmed; Works Type | Active | Tilt Core | 50 The Gardens, LGF, Flat 1 London SE22 9QQ | PRS-London & SE | Clean Only | 15/04/2024 | 13:30 | 15/05/2024 | Foxtons Upper Street Islington |  | Certificate Obtained | 05/05/2025 | Certificate Obtained | 05/05/2025 | No Gas at Property |  | Joe Bloggs | jbloggs@graingerplc.co.uk | 01234567899 | +447821234567 | Jane Bloggs | jane.bloggs@gmail.com | 07877713123 | 07877713123
| EoT-00345 | 15/03/2024 13:32 | Unit to be Sold; Works Type | Unit to be Sold | Tilt Core | 50 The Gardens, LGF, Flat 15 London SE22 9QQ | PRS-London & SE | Refurb | 25/04/2024 | 8:30 | 05/05/2024 | Foxtons Upper Street Islington | Tenant has a large dog. | Certificate Obtained | 05/05/2025 | Certificate Obtained | 05/05/2023 | Certificate Obtained | 05/05/2025 | Joe Bloggs | jbloggs@graingerplc.co.uk | 01234567899 | +447821234567 | Jane Bloggs | jane.bloggs@gmail.com | 07877713123 | 07877713123
| EoT-00346 | 15/03/2024 13:33 | EOT Status | Cancelled | Tilt Core | 50 The Gardens, LGF, Flat 30 London SE22 9QQ | PRS-London & SE | Refresh | 30/04/2024 | 13:30 | 30/05/2024 | Foxtons Upper Street Islington |  | No Certificate |  | Certificate Obtained | 31/12/2024 | Certificate Obtained | 05/05/2025 | Joe Bloggs | jbloggs@graingerplc.co.uk | 01234567899 | +447821234567 | Jane Bloggs | jane.bloggs@gmail.com | 07877713123 | 07877713123
Salesforce Object | EOT | EOT | EOT Status | EOT | Block | Unit | Unit | EOT | EOT | EOT | EOT | Unit | EOT | Unit | Unit | Unit | Unit | Unit | Unit | EOT | User | User | User | Tenancy | Account | Account | Account
Salesforce Field | End of Tenancy Number | Axis Fields Last Modified | Axis Fields Modified | EOT Status for Axis | Block Name | Plot No. | Portfolio | End of Tenancy Works Type | PVI Date | PVI Time | Future Vacant Date | Key_location_Check_in_c__c | Notes for Axis | EPC Status | EPC Expiry Date | EICR Status | EICR Expiry Date | CP12 Status | CP12 Expiry Date | Owner | Email | Phone | Mobile Phone | Account Name | Email | Phone | Mobile
Comments |  |  |  | Calculated from Unit to be Sold & EOT Status | Unit's building's block |  | Text field on the unit |  |  |  | Aka void Date | TBD | [7 empty] | currently defaults to the unit manager (if active & have a full Salesforce license) | Sourced from EOT Owner's user profile | Text field | Text field |  | Lead tenant | Text field | Text field
Updates Axis Mod Stamp? | N |  |  | Unit to be Sold & EOT Status = Y | N | N | N | Y | PVI Date; PVI Date & Time is Confirmed = Y | Y | Y | N | Y | N | N | N | N | N | N | Y | N | N | N | N | N

## Audit History (hidden)
Task |  | EOT
1 | Task Name | 1 | EOT Owner
2 | Task Status | 2 | FV Date & Time
3 | Task Owner | 3 | FV Date is Confirmed
4 | Notes | 4 | PVI Date & Time
5 | Late Completion Reason | 5 | PVI Date is Confirmed
6 | Late Completion Detail | 6 | Unit to be Relet
7 | Closure Reason | 7 | Unit to be Sold
8 | Target End Date | 8 | Works Type
9 | Delay Reason | 9 | Reason for Vacancy
10 | Delay Detail | 10 | NTQ Date
11 | Expected Duration | 11 | Notes
12 | Actual End Date | 12 | Closure Reason
13 |  | 13 | EOT Status
14 |  | 14 | Deposit Stoppage Type
15 |  | 15 | Deposit Stoppage Amount
16 |  | 16 | Actual Vacate Date
17 |  | 17 | Monthly Passing Rent
18 |  | 18
19 |  | 19
20 |  | 20