## Task Setup
Workflow | Phase | Task Name | Queue Type | Expected Duration (Days) | Custom Start Date Type | Preceding Tasks | Works Type | Relet / Sell | Information | Screen flow: Fields Required on Task Completion | Screen flow: EOT Fields Updated on Task Completion
Tenant Gives NTQ | Receive Notice | Validate Notice | Centralized PM | 1 | Void Start Date |  |  |  | In order to complete this task: • Check Tenancy to confirm notice is allowed. • Check if there is parking that needs to be processed at the same time. | Unit to be Relet; Unit to be Sold
Tenant Gives NTQ | Receive Notice | Confirm Notice | Centralized PM | 1 |  | Validate Notice |  |  | In order to complete this task: • Notify residents that notice has been accepted or denied via phone call and email. • Send DRI and Steps to Vacating forms to tenant for them to complete. • Update key location on Unit. • Update Qube. | Reason for Vacancy; FV Date; FV Date is Confirmed; PVI Date
Tenant Gives NTQ | Notify Stakeholders | Notify Stakeholders | Centralized PM | 1 |  | Confirm Notice |  |  | In order to complete this task: • Update Qube details. • Create MiMo tasks. • Create Work Order in Evolution for external inventory clerks. • Update British Gas Portal.
Tenant Gives NTQ | Notify Stakeholders | Confirm PVI Date | Onsite PM | 1 |  | Confirm Notice |  |  |  | PVI Date | PVI Date is Confirmed = True
Tenant Gives NTQ | Notify Stakeholders | Amend Direct Debit | Finance | 2 |  | Confirm Notice |  |  | In order to complete this task: • Apportion final rent collection.
Tenant Gives NTQ | Notify Stakeholders | Set Rent | Letting | 3 |  | Confirm Notice |  | Relet |  | Unit Marketing Status; Picklist: • On the Market Available to View • On the Market - No Access
Tenant Gives NTQ | Notify Stakeholders | Check Compliance | Centralized PM | 7 |  | Confirm Notice |  |  | In order to complete this task: • Ensure all required documents are in date. • Get up-to-date documents if required. • Save documents in correct folder.
Tenant Gives NTQ | PVI | PVI | Onsite PM | 1 | PVI Date |  |  |  | In order to complete this task: • Complete PVI. • Follow up contact with tenant with details of repairs, information and deposit release. | Works Type | PVI Completed Date = Task's Actual End Date
Tenant Gives NTQ | Book Works | Approve CapEx | Asset Management | 3 |  | PVI | Refresh, Refurb
Tenant Gives NTQ | Book Works | Book Works | Centralized PM | 4 |  | PVI |  |  | In order to complete this task: • Confirm works required after PVI. • Collect quotes for works and repairs. • Book works in FSI and arrange contractor’s access for Vacate Date. • Book cleaning.
Tenant Gives NTQ | Move Out | Check Out | Onsite PM | 1 | FV Date |  |  |  | In order to complete this task: • Keys have been handed back. • Final inspection completed. • Update Qube details. • Confirm access with inventory clerk (if required). | Actual Vacant Date
Tenant Gives NTQ | Move Out | Check Unit Condition | Onsite PM | 2 | FV Date |  |  |  | In order to complete this task: • Compare PVI and final inspection, and adjust works if needed. • Save checkout report to EoT. • Compare Move-in and Move-out inventory. • Complete ROD and notify Credit Control. |  | Works Start Date = Task's Actual End Date
Tenant Gives NTQ | Move Out | Close Down Tenancy | Finance | 5 |  | Check Out |  |  | In order to complete this task: • Close tenancy and mark relet status on Qube.
Tenant Gives NTQ | Move Out | Cancel Direct Debit | Finance | 2 |  | Check Out |  |  | In order to complete this task: • Cancel DDM after move out confirmation.
Tenant Gives NTQ | Refurb/Refresh | Review Check Out Report | Centralized PM | 3 |  | Check Unit Condition
Tenant Gives NTQ | Refurb/Refresh | Finalize Check Out | Centralized PM | 4 |  | Check Unit Condition |  |  | In order to complete this task: • Send checkout report to Tenant. • Notify Council Tax. • Notify any remaining utilities. • Diarise flushing for void unit.
Tenant Gives NTQ | Refurb/Refresh | Refresh | Onsite PM | 7 |  | Check Unit Condition | Refresh
Tenant Gives NTQ | Refurb/Refresh | Refurb | Onsite PM | 15 |  | Check Unit Condition | Refurb
Tenant Gives NTQ | Refurb/Refresh | Clean Unit | Onsite PM | 1 |  | Check Unit Condition, Refurb, Refresh | Refresh, Refurb, Clean Only
Tenant Gives NTQ | Release Deposit | Deposit Release | Finance | 3 |  | Finalize Check Out |  |  | When RTA gets emailed to process refund, this task can be marked off as complete. | Deposit Stoppage Type, Deposit Stoppage Amount | Deposit Return Date = Task's Actual End Date

## EOT Fields
Field Name | Editable on EOT Details Screen? | Field Type & Content | Required? | Default Value on Creation | Validations | Business Rules & Automated Updates
EOT Name | No | Text | Required | EOT - [Unit's Plot No.]
EOT Number | No | Text | Required | System generated
Tenancy | No | FK to Tenancy Object | Required | Selected tenancy
Status | No - Editable via Close / Cancel screen flow | Picklist: • Active • Complete • Cancelled • Closed - Tenant Retained • Closed - NTQ Denied • Pending Cancel/Close | Required | Active |  | Status updates from 'Active' to 'Complete' when the last EOT phase is complete. When Closing/Cancelling an EOT: If first EOT phase is complete & the user is not EOT Owner => Close / Cancel approval request is created & EOT status is set to 'Pending Cancel/Close'. Status updates from 'Active' to 'Pending Cancel / Close' when cancel/close approval request is created. Status updates from 'Pending Cancel/Close' to 'Active' when cancel/close approval request is rejected.
EOT Template | No | Picklist: • Tenant Gives NTQ | Required
Owner | Yes | User list | Required | Unit's unit manager (if active & they have a full Salesforce license)
Unit | No | FK to Unit Object | Required | Unit linked to tenancy | Cannot create an EOT if there is already an EOT for the unit in Active or Pending Cancel/Close status.
Building | No | FK to Building Object | Required | Building linked to tenancy
Notes | Yes | Long text | Optional
Start Date | No | Date | Required | Date EOT is created
Notice to Quit Date | Yes | Date | Required | Date EOT is created
PVI Date | Yes | Date | Required | If FV Date is more than 32 days after today = [FV Date - 28 days] If FV Date is between 4 and 32 days after today = [Current Date + 4 days] If FV Date is less than 4 days after today = [FV Date] | Must be after Start Date | Default value may be edited. Only defaults on initial Create EOT screen.
PVI Date Is Confirmed | Yes | Boolean | Optional | False |  | Flagged as true when the user completes the 'Confirm PVI Date' task.
PVI Completed Date | No | Date | Optional |  |  | Automatically populated with PVI task's actual end date.
Future Vacant Date | Yes | Date | Required |  | Must be after Start Date | Where FV Date is edited and the 'Amend Direct Debit' task is in the 'Complete' or 'N/A' status, the task will be automatically set back to an 'Active' status.
Future Vacant Date Is Confirmed | Yes | Boolean | Optional | False
Actual Vacant Date | No | Date | Optional |  |  | Defaults to Future Vacant date when closing 'Check Out' task; may be edited.
Works Start Date | No | Date | Optional |  |  | Automatically populated with Check Unit Condition task's actual end date.
Available Date | No | Date | Optional | = [Max [Actual End Date, else Target End Date] of all tasks with a Works Type that are not in 'N/A' status] + 1 day |  | Recalculated automatically as timelines change.
Completion Date | No | Date | Optional | = Max Target End Date of all tasks not in 'N/A' status. |  | Recalculated automatically as timelines change. Updates to the date the EOT status updates to 'Complete'.
Next Move In Date | No | Date | Optional |  |  | Automatically populated with Tenancy Start Date - • When a Tenancy with Tenancy Type ‘New’ has Tenancy Status changed to 'Activated': Updates the EOT for the same Unit that is in ‘Active’ or ‘Complete’ Status & has the greatest Start Date. • When the Tenancy Start Date is edited for a Tenancy with Tenancy Type ‘New’ & Tenancy Status 'Activated': Updates the EOT with the same Unit that is in ‘Active’ or ‘Complete’ Status & has the greatest Start Date.
Passing Monthly Rent | No | Currency | Optional | = [Tenancy’s Monthly Rent] x (1 + [Tenancy's Uplift]) ^ [Number of full years between Tenancy Start Date & current date]
Reason for Vacancy | Yes | Single-select Picklist | Optional
Unit to be Relet | Yes | Boolean | Optional | True
Unit to be Sold | Yes | Boolean | Optional | False
EOT Works Type | Yes | Picklist: • Clean Only • Refresh • Refurbishment | Optional | Clean Only
Deposit Deduction Type | No | Picklist: • No Deductions • Deductions - Agreed with Resident • Deductions - Disputed | Optional
Deposit Deduction Amount | No | Currency | A non-zero value is required when the Deposit Deduction Type is either ‘Deductions - Agreed with Resident’ or ‘Deductions - Disputed’.
Deposit Return Date | No | Date | Optional |  |  | Automatically populated with Deposit Return task's actual end date.
Current Phase | No | FK to EOT Phase object | Required | First Phase per the task template. |  | Automatically updates to the first phase not in a 'Complete' status.
Close Reason | No - Editable via Close / Cancel screen flow | Picklist - Options are dependent on the EOT Status | Required where EOT Status is changed to a Closed or Cancelled status or to Pending Cancel/Close.
Close Detail | No - Editable via Close / Cancel screen flow | Text | Optional
PVI Completed to Vacant (Days) | Calculated Field | Integer | Optional | # of days from [PVI Completed Date] to [Actual Vacant Date]
Vacant Date to Deposit Returned (Days) | Calculated Field | Integer | Optional | # of days from [Actual Vacant Date] to [Deposit Return Date]
Vacant Date to Ready to Let (Days) | Calculated Field | Integer | Optional | # of days from [Actual Vacant Date] to [Available Date]
Vacant Date to Move In (Days) | Calculated Field | Integer | Optional | # of days from [Actual Vacant Date] to [Next Move-In Date]
Total Rent Loss | Calculated Field | Currency | Optional | = [Monthly Passing Rent] x 12 ÷ 365 x [Vacant Date to Move In (Days)]
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: • Relocation within City • Relocation - UK • Purchased Own Property • Rent Too High • Relocation - Overseas • Lack of Service - Grainger/Agent • Transfer to Grainger Property • Tenant Evicted • Abandoned • Rehoused by Local Authority • Tenant Deceased
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Options for ‘Close - NTQ Denied’: - No Break Clause - Poor Timing Options for ‘Cancel’: - Created by Mistake - Testing Options for ‘Close - Tenant Retained’: - Repair/Improvement Offered - Customer Changed Mind

## Phase Fields
Field Name | Editable? | Field Type & Content | Required? | Default Value | Business Rules
EOT Phase Name | No | Text | Required | Per task template.
Status | No | • Pending • In Progress • Complete | Required | First phase is 'In Progress', all other phases default to 'Pending'. | If any task in a phase is moved to In Progress, OR one of multiple incomplete tasks is set to Complete: The Phase status is updated to 'In Progress' (regardless of whether the preceding phase is complete). When the final open task in a phase is updated to a status of ‘N/A’ or ‘Complete’, the phase status is updated to 'Complete'.
Sequence | No | Integer | Required | Per task template.

## Task Fields
Field Name | Editable on Task Details Screen? | Field Type & Content | Required? | Default Value on Task Creation | Business Rules & Automated Updates
Task Name | Yes | Short Text | Required | Per Task Setup
EOT | No | FK to EOT object | Required | EOT
EOT Phase | No | FK to EOT Phase object | Required | Per Task Setup
Unit | No | FK to Unit object | Required | Tenancy's unit
Owner | Yes | User / Queue | Required | Queue configured as the EOT Team for the EOT's Building and the tasks' Queue Type per the task setup. | If Owner is a queue, this is updated to the current user when the user clicks the ‘Start Task’ button.
Task Team | No | Queue | Required | Queue configured as the EOT Team for the EOT's Building and the tasks' Queue Type per the task setup. | When the task Owner is updated from an individual to a queue OR from one queue to another queue, the Task Team will be updated to the same queue.
Task Status | No | Picklist: • Pending • Active • In Progress • Complete • N/A | Required | Pending | If configured with preceding task(s): When 'Pending' & the final, open preceding task’s status changes to ‘N/A’ or ‘Complete’ => ‘Active’. When 'Active' and a preceding task is re-opened => ‘Pending’. Tasks flagged as relet tasks are updated to 'N/A' if Unit to be Relet is updated to false, and are updated to 'Active' or 'Pending' if Unit to be Relet is updated to true. Tasks with a Works Type are updated to/from 'N/A' when the EOT Works Type changes. If Start Date Type is FV Date: When ‘FV Date is Confirmed’ is updated to true => ‘Active’. When ‘FV Date is Confirmed’ is updated to false => 'Pending’. If Start Date Type is PVI Date: When ‘PVI Date is Confirmed’ is updated to true => ‘Active’. When ‘PVI Date is Confirmed’ is updated to false => ‘Pending’. When user selects 'Start Task' button => 'In Progress' When the EOT Status changes to a cancelled or closed status & a task is open => 'N/A'
Start Date Type | No | Picklist: • Predecessor Task • EOT Start Date • PVI Date • Future Vacant Date | Required | Per Task Setup
Start Date | No | Date | Required | = FV Date, PVI Date or EOT Start Date where the tasks' Start Date Type is one of those, otherwise = Last [Actual End Date, or if none then Target End Date] for each preceding task that is not in a ‘N/A’ status. | Automatically updates until the task is complete.
Target End Date | No | Date | Required | = [Start Date] + [Expected Duration] | Automatically updates until the task is complete.
Actual Start Date | No | Date | Optional |  | When a task with Status 'Pending', 'Active' or 'N/A' changes to 'In Progress' or 'Complete', then the current date is saved as Actual Start Date. If task Status is updated to 'Pending', 'Active' or 'N/A' => Actual Start Date is deleted.
Actual End Date | No | Date | Optional |  | Automatically populated with the date that the as Task Status is updated to Complete. If task Status is updated to 'Pending', 'Active' or 'N/A' => Actual End Date is deleted.
Expected Duration | No - Updated via the Adjust Task Timeline screen flow | Integer | Required | Per Task Setup | Updated to 'KPI Duration' where user elects to 'Reset Task Timeline'
KPI Duration | No | Integer | Required | Per Task Setup
Actual Duration | Calculated | Integer | Optional | Where task status is 'Complete': = # of days between task [Start Date] and [Actual End Date]
Expected Delay Days | Calculated | Integer | Optional | Where the task status is not ‘N/A’: = [Expected Duration] - [KPI Duration]
Delay Reason | No - Updated via the Adjust Task Timeline or Close Task screen flows | Picklist: • Contractor Delays • Bank Holiday • Task Owner Sick • Resource Unavailable • Other | Required where Actual End Date is 2 or more days after Target End Date AND/OR Expected Duration> KPI Duration |  | Deleted where user elects to 'Reset Task Timeline'
Delay Detail | No - Updated via the Adjust Task Timeline or Close Task screen flows | Text (max 255) | Required where Delay Reason is 'Other' |  | Deleted where user elects to 'Reset Task Timeline'
Overdue Days | Calculated | Integer | Optional | Where the task status is 'Pending', 'In Progress' or 'Active' AND Target End Date < current date = # of days from [Target End Date] to [Current Date] Where the task status is ‘Complete’ = [Actual Duration] - [Expected Duration]
Task Overdue | Calculated | Boolean | Optional | True where Overdue Days > 0
Notes | Yes | Long Text | Optional
Information | No | Long Text | Optional | Per Task Setup
Closure Reason | No - Updated via Close Task screen flow. | Text | Required when task status is updated to 'N/A'
Relet/Resell | No |  | Optional |  | Backend configuration. Determines whether the task is applicable when the unit is flagged for relet or sale.
Works Type | No |  | Optional |  | Backend configuration. Determines whether the task is applicable for the works type & is used to calculate Available Date.

## Updates to Other Objects
Object Updated | Field Updated | Trigger | Update to
Unit | Future Vacant Date | WHEN the first End of Tenancy phase is completed | EOT's Future Vacant Date
GIVEN an EOT is no longer in the first phase WHEN a user edits the EOT’s Future Vacant Date
Unit | Available Date | WHEN the first End of Tenancy phase is completed | EOT's Available Date
GIVEN an EOT is no longer in the first phase WHEN the EOT’s Available Date is recalculated
Unit | Unit Status | WHEN the first End of Tenancy phase is completed | "Future Vacant"
|  | WHEN the EOT's 'Unit Marketing Status' is selected on closing the 'Set Rent' task. | EOT's Unit Marketing Status
Tenancy | Tenancy Status | GIVEN an Opportunity has (only) one associated Agreement that is: In a ‘Signed’ Agreement Status, and Is linked to a Tenancy with a Tenancy Type ‘New’ WHEN the Opportunity’s Current Stage is updated to ‘Audit’ | 'Activated'
| Status |  | 'Activated'
Tenancy | Tenancy Status | WHEN the EOT Check Out task is completed (i.e. the Actual Vacant Date is populated). | 'Ended'
| Actual Move Out Date |  | EOT's Actual Vacant Date

## Audit History (hidden)
Task |  | EOT
1 | Task Name | 1 | EOT Owner
2 | Task Status | 2 | FV Date & Time
3 | Task Owner | 3 | FV Date is Confirmed
4 | Notes | 4 | PVI Date & Time
5 | Late Completion Reason | 5 | PVI Date is Confirmed
6 | Late Completion Detail | 6 | Unit to be Relet
7 | Closure Reason | 7 | Unit to be Sold
8 | Target End Date | 8 | Works Type
9 | Delay Reason | 9 | Reason for Vacancy
10 | Delay Detail | 10 | NTQ Date
11 | Expected Duration | 11 | Notes
12 | Actual End Date | 12 | Closure Reason
13 |  | 13 | EOT Status
14 |  | 14 | Deposit Stoppage Type
15 |  | 15 | Deposit Stoppage Amount
16 |  | 16 | Actual Vacate Date
17 |  | 17 | Monthly Passing Rent
18 |  | 18
19 |  | 19
20 |  | 20