## Sheet1
Sprint 1 UAT Session |  |  | OB Feedback | Assigned to | Link
what if someone leaves early | they give notice, we allow them to howver they will be liable for rent until a new person is found. | feeling that this should be a new template and not addressed in this first release | New story added to backlog | Future release | https://graingerplc.atlassian.net/browse/FVVP-57
some units have random furniture | at the moment, property manager tells lettigns manager what is in each unit at the point of FV email being sent | it changes at each notice, not sure why. This should really be captured and populated on the unit by the PM | New story added to backlog (unit details enhancement) | Future release | https://graingerplc.atlassian.net/browse/FVVP-123
refresh should be 7 days instad of 5 |  | Rob Hoad / Procurement are looking at FY23 data to understand turn around times | Added a story to update the task template; to be confirmed by Grainger. Story assigned to Jacob. | 1 | https://graingerplc.atlassian.net/browse/FVVP-114
refurbs, typically 60 days. | need to decide on how this is best managed, because this will be part of the repairs and maintenanc stories that we are looking at at the moment with centralised repairs work.# |  | Added a story to update the task template; to be confirmed by Grainger. Story assigned to Jacob. | 1 | https://graingerplc.atlassian.net/browse/FVVP-114
given I have access to the EoT and the notice is accepted, as a user, when I confirm notice, I want an email to be sent to all tenants confirming their notice automatically with appropriate attachments, so that I do not have to complete this manually outside of the system |  |  | Already on backlog to automate move out email | Future release | https://graingerplc.atlassian.net/browse/FVVP-152
given I have access to the EoT and the notice is not accepted, as a user, when I deny notice, I want an email to be sent to all tenants confirming that we are not accepting their NTQ with reasons why, so I do not have to complete this manulally outside of the system |  |  | New story added to backlog; will be trigged on closing the EOT | Future release | https://graingerplc.atlassian.net/browse/FVVP-137
|  |  | Add another EOT status 'Closed - NTQ Denied'. |  | https://graingerplc.atlassian.net/browse/FVVP-112
Tasks that ned more information |  |  | We have a placeholder story to break out tasks (with some initial suggestions) but need confirmed list | 1 | https://graingerplc.atlassian.net/browse/FVVP-104
briefly spoke with Sam about screenflows for each task, which would allow flexibility for additional details etc. |  |  | We have a placeholder story to prompt users to capture certain info on completion of tasks (with some initial suggestions) but need confirmed list | 1 | https://graingerplc.atlassian.net/browse/FVVP-106
for the above email stories, screenflow to capture yes/no with reasons that could be used to email? |  |  | Automate a NTQ Denied Email where an EOT is closed with that reason. | Future release | https://graingerplc.atlassian.net/browse/FVVP-137
New task - PVI date confirmation | pvi date gets pencilled in, however the date should be confirmed by the person doing the PVI |  | Added a story to update the task template; to be reviewed with Grainger | 1 | https://graingerplc.atlassian.net/browse/FVVP-129
| once pvi date and time is confirmed, email to all tenants advising of the appointment - template email |  | Updated existing story on backlog to automate move out email that includes PVI date. | Future release | https://graingerplc.atlassian.net/browse/FVVP-152
New task - ammend DD | this should be where cancel DDM is now, and cancel DDM should be at the end, once it has been confirmed that the tenant has actually vacated |  | Added a story to update the task template; to be reviewed with Grainger | 1 | https://graingerplc.atlassian.net/browse/FVVP-126
New queue - Credit Control | will confirm this, need to discuss with finance and see if this can be grouped or should be separate |  | Added a story to update the task template; to be reviewed with Grainger. Rename Finance Queue | 1 | https://graingerplc.atlassian.net/browse/FVVP-182
question for Jon/Grainger/Nikki | the refurb team - what was the idea behind this? |  | Refurb/ refresh / clean will all be done by an external contractor. These tasks should be assigned to Onsite PM Queue | 1 | https://graingerplc.atlassian.net/browse/FVVP-182
every single EoT should have a clean, regardless of any other works. The clean should then be placed after the complettion of any refurb/refresh works to ensure that it has been booked and done |  | Rob / Procurement are reviewing if the main contractor will also be doing all the cleans. This needs to be confirmed and then agree the process. | Added a story to update the task template; to be confirmed by Grainger. Story assigned to Jacob. | 1 | https://graingerplc.atlassian.net/browse/FVVP-114
further requirement: if the actual completed day is after the target date, have a reason why so that this can be reported on. Not sure if best to have picklist and free text to capture more information for easier reportability |  |  | Enter a reason where any task is completed more than 2 days late. | 1 | https://graingerplc.atlassian.net/browse/FVVP-168
Further requirement: Shouldn't have more than one active EOT for a unit at any point in time.