## SB_Sprint 1 User Stories & Bugs
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Column1
Bug | FVVP-220 | 34486 | All Task status updated to Pending or Active when "PVI Date is Confirmed" and "Future Vacate Date is Confirmed" is updated | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-09-23 19:30 | 2002-10-23 11:09
Bug | FVVP-218 | 34483 | Incorrect End of Tenancy Spelling | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-09-23 12:28 | 2029-09-23 13:03
Bug | FVVP-217 | 34481 | End Of Tenancy Tab missing in SIT | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-09-23 10:46 | 2029-09-23 16:16
Bug | FVVP-216 | 34480 | EoT phase status is not default to pending in not completed | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-09-23 10:44 | 2029-09-23 12:11
Bug | FVVP-215 | 34478 | EoT phases are not updating when Tasks are completed | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2028-09-23 16:16 | 2029-09-23 10:44
Bug | FVVP-213 | 34462 | Change EoT Phase and EoT Task label | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2027-09-23 10:34 | 2028-09-23 13:56
Bug | FVVP-212 | 34461 | EoT Task Name and EoT Phases are editable | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2027-09-23 10:28 | 2028-09-23 16:06
Bug | FVVP-205 | 34396 | Missing End of Tenancy Field requirements and EoT error | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2019-09-23 17:56 | 2029-09-23 17:19
Story | FVVP-190 | 34213 | See Tasks for an End of Tenancy | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-08-23 17:32 | 2022-11-23 14:34 |  | 8.0 | 8
Story | FVVP-189 | 34211 | View / Update Task Details | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-08-23 16:46 | 2028-10-23 19:59 |  | 3.0 | 3
Story | FVVP-98 | 33349 | Upload EoT Documents | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2022-09-23 11:02 |  | 1.0 | 1
Story | FVVP-89 | 33340 | Create a Void with Refurb / Refresh / Clean Only-Specific Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2003-10-23 12:21 |  | 5.0 | 5
Story | FVVP-71 | 33322 | Complete a Phase | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2012-10-23 15:24 |  | 5.0 | 5
Story | FVVP-66 | 33317 | Update Timelines - Tasks Dependent on a Void Date | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2004-10-23 15:54 |  | 8.0 | 8
Story | FVVP-62 | 33313 | Rename "Void" Terminology |  |  | Priority 3 | Done | Done | 2001-06-23 14:00 | 2003-10-23 09:49
Story | FVVP-58 | 33309 | New End of Tenancy - Capture End of Tenancy Details | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2024-10-23 16:34 |  | 3.0 | 3
Story | FVVP-53 | 33304 | New End of Tenancy - Assign Tasks to Responsible Queues | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2001-06-23 14:00 | 2017-10-23 09:20 |  | 5.0 | 5
Story | FVVP-50 | 33301 | Calculate Estimated Timelines - Tasks Tied to an EOT Date | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2029-09-23 18:17 |  | 5.0 | 5
Story | FVVP-49 | 33300 | New End of Tenancy - Generate Phases & Tasks from a Template | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2003-10-23 09:30 |  | 13.0 | 13
Story | FVVP-48 | 33299 | New End of Tenancy - Create an End of Tenancy | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2011-10-23 16:19 |  | 5.0 | 5
61