## SB_Sprint 2 User Stories & Bugs
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Priority | Status | Resolution | Created | Updated | Due date | Labels | Labels_1 | Labels_2 | Labels_3 | Labels_4 | Custom field (Story Points) | Story | UAT
Bug | FVVP-263 | 34589 | "Available Date" not updating correctly when "Actual End Date" is updated | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2020-10-23 10:55 | 2020-10-23 13:12
Bug | FVVP-262 | 34583 | EoT status is set to "Complete" when an EoT is cancelled | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2019-10-23 17:15 | 2019-10-23 17:49
Bug | FVVP-261 | 34575 | "Cancellation Reason" Field not required | Anjali Salecha | 712020:f0633aca-0b2d-46f7-bcdd-62101a55aaec | Priority 3 | Done | Done | 2019-10-23 14:22 | 2020-10-23 10:18
Bug | FVVP-254 | 34556 | Error when updating last Task status | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2013-10-23 16:07 | 2019-10-23 17:50
Bug | FVVP-249 | 34549 | Phases are not moving along when all related tasks are set to N/A | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2012-10-23 15:24 | 2017-10-23 12:50
Bug | FVVP-247 | 34542 | EoT status not updated to "cancelled" or "closed" when EoT is cancelled or closed | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2011-10-23 18:06 | 2019-10-23 17:12
Bug | FVVP-241 | 34520 | Task Not Updated where FV Date & FV Confirmed are both updated - Not a bug |  |  | Priority 3 | Done | Done | 2004-10-23 15:54 | 2017-10-23 12:23
Story | FVVP-239 | 34517 | Remove Activity Widget | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2004-10-23 15:10 | 2018-10-23 15:15 |  | No_Video | Show_Me_Complete |  |  |  | 1.0 | 1
Bug | FVVP-238 | 34516 | Change Outstanding Task List Heading | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2004-10-23 14:39 | 2011-10-23 10:12
Bug | FVVP-236 | 34514 | EOT Owner field not displayed on creation screen & not defaulting correctly | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2004-10-23 14:20 | 2027-10-23 15:35 |  | Dev_Reviewed | Show_Me_Complete |  |  |  | 1.0 | 1
Bug | FVVP-235 | 34513 | Change Template control to a picklist | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2004-10-23 14:12 | 2011-10-23 10:19 |  | Dev_Reviewed | Show_Me_Complete |  |  |  | 1.0 | 1
Bug | FVVP-226 | 34501 | Object and field help & description updates | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2003-10-23 09:30 | 2027-10-23 15:05 | [6 empty] | 1.0 | 1
Story | FVVP-225 | 34491 | Update status of first End of Tenancy Phase when EoT is first created | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-10-23 20:45 | 2023-10-23 11:31 |  | No_Video |  |  |  |  | 2.0 | 2
Bug | FVVP-224 | 34490 | EoT tasks don't display for system administrator | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2030-09-23 15:33 | 2003-10-23 16:59
Story | FVVP-223 | 34489 | Set EoT Phase status to In Progress/Pending based on task status | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2030-09-23 01:34 | 2026-10-23 17:28 |  | Dev_Reviewed | REFINED | Show_Me_Complete | Video_Recorded |  | 3.0 | 3
Bug | FVVP-222 | 34488 | Make template mandatory when creating new EoT | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2030-09-23 01:29 | 2010-10-23 11:18 | [6 empty] | 1.0 | 1
Story | FVVP-214 | 34467 | Prevent creation of new End Of Tenancy when Task Teams are not completed on related building | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2027-09-23 12:21 | 2030-10-23 10:46 |  | Dev_Reviewed | REFINED | Show_Me_Complete | Video_Recorded |  | 2.0 | 2
Story | FVVP-181 | 33432 | Prevent Duplicate EOTs for a Unit | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 2 | Done | Done | 2001-06-23 14:01 | 2019-10-23 15:16 |  | Dev_Reviewed | No_Video | REFINED | Show_Me_Complete | UAT_Feedback | 2.0 | 2 | 2
Story | FVVP-180 | 33431 | Information Required on Completing Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2023-10-23 11:47 |  | REFINED | Show_Me_Complete | Sizing_Done | Video_Recorded |  | 3.0 | 3
Story | FVVP-128 | 33379 | Complete Task Screen Flow | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2023-10-23 11:51 |  | REFINED | Show_Me_Complete | Sizing_Done | Video_Recorded |  | 8.0 | 8
Story | FVVP-126 | 33377 | Update Task Template - New Task - Amend DD | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2018-10-23 15:14 |  | Dev_Reviewed | No_Video | REFINED | Show_Me_Complete | UAT_Feedback | 1.0 | 1 | 1
Story | FVVP-106 | 33357 | Not Required |  |  | Priority 3 | Done | Done | 2001-06-23 14:00 | 2019-10-23 14:32 |  | No_Video |  |  |  |  | 0.0 | 0
Story | FVVP-100 | 33351 | See History of EOTs for a Unit | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 1 | Done | Done | 2001-06-23 14:00 | 2024-10-23 15:14 |  | Dev_Reviewed | No_Video | REFINED |  |  | 1.0 | 1
Story | FVVP-99 | 33350 | See Audit History | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 1 | Done | Done | 2001-06-23 14:00 | 2020-10-23 16:38 |  | No_Video | REFINED | Show_Me_Complete |  |  | 2.0 | 2
Story | FVVP-92 | 33343 | Update Salesforce Unit Details | Avi Purohit | 712020:c193d1c9-a74f-4827-9308-4a6fbb0cf731 | Priority 1 | Done | Done | 2001-06-23 14:00 | 2023-10-23 15:09 |  | Dev_Reviewed | No_Video | REFINED | Show_Me_Complete |  | 3.0 | 3
Story | FVVP-91 | 33342 | Track Task Team as well as Task Owner | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2001-06-23 14:00 | 2027-10-23 16:16 |  | Dev_Reviewed | No_Video | REFINED | Show_Me_Complete | Sizing_Done | 3.0 | 3
Story | FVVP-90 | 33341 | See Available Date & EoT Completion Date | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2001-06-23 14:00 | 2020-11-23 18:24 |  | No_Video | REFINED | Show_Me_Complete |  |  | 5.0 | 5
Story | FVVP-87 | 33338 | Update Relet Status - Update Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2023-10-23 15:29 |  | Dev_Reviewed | REFINED | Show_Me_Complete | Video_Recorded |  | 5.0 | 5
Story | FVVP-86 | 33337 | Create a Void with Relet Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2023-10-23 15:29 |  | Dev_Reviewed | No_Video | REFINED | Show_Me_Complete |  | 5.0 | 5
Story | FVVP-78 | 33329 | Cancel an EoT | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2023-10-23 15:33 |  | Dev_Reviewed | REFINED | Show_Me_Complete | Video_Recorded |  | 3.0 | 3
Story | FVVP-77 | 33328 | Close an End of Tenancy | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2025-10-23 09:20 |  | Dev_Reviewed | REFINED | Show_Me_Complete | Video_Recorded |  | 3.0 | 3
Story | FVVP-75 | 33326 | Users Cannot Edit Completed EoT | Avi Purohit | 712020:c193d1c9-a74f-4827-9308-4a6fbb0cf731 | Priority 3 | Done | Done | 2001-06-23 14:00 | 2009-11-23 17:27 |  | Dev_Reviewed | No_Video | REFINED | Show_Me_Complete |  | 1.0 | 1
Story | FVVP-65 | 33316 | Update Works Type - Update Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2023-10-23 15:36 |  | Dev_Reviewed | No_Video | REFINED | Show_Me_Complete |  | 2.0 | 2
Story | FVVP-52 | 33303 | Not Required |  |  | Priority 3 | Done | Done | 2001-06-23 14:00 | 2019-10-23 14:32 |  | No_Video | Scope_Creep |  |  |  | 0.0
Story | FVVP-51 | 33302 | Calculate & Update Estimated Timelines - Tasks Dependent on Completion of Prior Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2027-10-23 12:35 |  | Dev_Reviewed | REFINED | Show_Me_Complete | Video_Recorded |  | 20.0 | 20
[18 empty] | 79 | 3