## SB_Sprint 4 User Stories & Bugs
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Priority | Status | Resolution | Created | Updated | Due date | Labels | Labels_1 | Labels_2 | Labels_3 | Labels_4 | Labels_5 | Labels_6 | Labels_7 | Custom field (Story Points) | Column1 | UAT | Scope Creep
Bug | FVVP-400 | 35398 | Cost of void report - Incorrect FV Date | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2030-11-23 15:25 | 2001-12-23 13:37
Bug | FVVP-399 | 35397 | EOTs at Risk - Report displays EOT start date, not task start date | Nikki | 70121:af6196ff-0b2f-4ade-9d2a-c625be89a01c | Priority 3 | Done | Done | 2030-11-23 14:17 | 2030-11-23 14:40
Bug | FVVP-398 | 35389 | [Not a bug] |  |  | Priority 3 | Done | Done | 2029-11-23 17:53 | 2029-11-23 17:55
Bug | FVVP-397 | 35378 | Deposits Due/Overdue - Months ordered backwards | Nikki | 70121:af6196ff-0b2f-4ade-9d2a-c625be89a01c | Priority 3 | Done | Done | 2029-11-23 16:31 | 2029-11-23 17:17
Bug | FVVP-395 | 35371 | Deposits Due / Overdue - Chart not stacked by Task Overdue | Nikki | 70121:af6196ff-0b2f-4ade-9d2a-c625be89a01c | Priority 3 | Done | Done | 2029-11-23 14:39 | 2029-11-23 15:09
Story | FVVP-394 | 35370 | Update Overdue Calculated Field | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-11-23 14:13 | 2004-12-23 12:51 |  | No_Video | OB_Internal | REFINED | [5 empty] | 1.0
Bug | FVVP-393 | 35369 | Deposits Completed - Not displayed by month | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-11-23 13:43 | 2029-11-23 15:29
Story | FVVP-391 | 35359 | Void Report - Additional columns | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-11-23 12:35 | 2030-11-23 12:34 |  | No_Video | OB_Internal | [6 empty] | 1.0
Bug | FVVP-386 | 35353 | Error when assigning tasks from "My Team's Unassigned EoT Tasks for Today" list where EOT is pending cancellation | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2029-11-23 08:56 | 2029-11-23 11:18
Story | FVVP-385 | 35347 | Void Report - Add EOT Number column | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2028-11-23 17:25 | 2030-11-23 12:35 |  | No_Video | [7 empty] | 1.0
Bug | FVVP-383 | 35343 | [Not a bug] Tenancy Status/Move Out Date not tracked in Tenancy History |  |  | Priority 3 | Done | Done | 2028-11-23 14:57 | 2028-11-23 16:00
Bug | FVVP-382 | 35342 | "Average" row is not included in the report and dashboard component not in staging | Matthew Pitcairn | 712020:6138a31f-37e3-441e-8e84-e7b774920bdc | Priority 3 | Done | Done | 2028-11-23 12:50 | 2028-11-23 15:30
Bug | FVVP-381 | 35341 | [Not a bug] New button in Mobile app |  |  | Priority 3 | Done | Done | 2028-11-23 12:10 | 2028-11-23 13:25
Bug | FVVP-378 | 35327 | Activating a Tenancy does not save Next Move In Date | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2027-11-23 16:19 | 2029-11-23 08:24
Bug | FVVP-377 | 35325 | Task Information - Remove testing text | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2027-11-23 14:58 | 2027-11-23 17:16
Bug | FVVP-376 | 35324 | Confirm Notice Task Setup | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2027-11-23 14:49 | 2027-11-23 16:00
Bug | FVVP-375 | 35323 | Task Template Setup - Close Down Tenancy Preceding Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2027-11-23 14:42 | 2027-11-23 16:01
Bug | FVVP-373 | 35320 | FVVP-167 - Update Task Template - Confirm Notice after Validate Notice | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2027-11-23 13:26 | 2027-11-23 17:36
Bug | FVVP-372 | 35319 | FVVP-167 - Update Task Template - Confirm Notice after Validate Notice | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2027-11-23 12:55 | 2027-11-23 17:36
Bug | FVVP-371 | 35315 | More than 5 columns are displaying in Tenancies preview | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2027-11-23 09:28 | 2027-11-23 13:07
Bug | FVVP-370 | 35310 | Validation error message does not make sense when EOT team fields are blank | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2024-11-23 18:14 | 2028-11-23 11:19
Bug | FVVP-369 | 35304 | Only EOT Owner can Cancel/Close EOT after Notice Confirmed | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2024-11-23 15:47 | 2027-11-23 15:55
Bug | FVVP-367 | 35290 | (Not A bug) Tasks not assigned to Queues after EOT is created | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2023-11-23 18:07 | 2024-11-23 09:24
Story | FVVP-366 | 35272 | Overdue Tasks - Include pending overdue tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2022-11-23 18:01 | 2004-12-23 14:55 |  | IA_Done | No_Video | REFINED | [5 empty] | 1.0 | 1
Bug | FVVP-365 | 35270 | {Not a bug} Next Move-In Date Not Populating When Opportunity Stage Changes to "Audit" | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2022-11-23 16:45 | 2023-11-23 09:50
Bug | FVVP-364 | 35267 | EOTs at Risk - Report doesn't display Task Owner | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2022-11-23 14:46 | 2022-11-23 17:44
Bug | FVVP-363 | 35266 | [Not a bug] Outstanding Tasks Component - Not showing Pending tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2022-11-23 14:34 | 2023-11-23 16:00
Story | FVVP-362 | 35264 | User Setup - Assign Unit Manager permission on Staging & Production | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2022-11-23 14:02 | 2030-11-23 12:25 |  | IA_Done | No_Video | Refinment_Internal | [5 empty] | 1.0 | 1
Bug | FVVP-361 | 35260 | EOT's at risk not filtered by EOT owner | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2022-11-23 08:59 | 2022-11-23 09:49
Bug | FVVP-359 | 35243 | Completion Date for a complete EOT is incorrect | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2020-11-23 18:24 | 2028-11-23 09:22
Story | FVVP-358 | 35238 | My Tasks for Today | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2020-11-23 16:10 | 2030-11-23 12:27 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  |  | 1.0 | 1
Bug | FVVP-357 | 35235 | EOT Recently Viewed list view is not as per the requirements | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2020-11-23 13:09 | 2020-11-23 13:25
Bug | FVVP-355 | 35233 | Adjust Task Timeline - Delay Detail is duplicated in screen flow | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2020-11-23 12:05 | 2023-11-23 15:15
Bug | FVVP-344 | 35121 | [Remove] |  |  | Priority 3 | Done | Done | 2015-11-23 11:46 | 2020-11-23 10:11 |  | OB_Internal
Story | FVVP-343 | 35113 | [Internal] Ensure all EoT Flows run in System Context with Sharing | Matthew Pitcairn | 712020:6138a31f-37e3-441e-8e84-e7b774920bdc | Priority 3 | Done | Done | 2014-11-23 16:19 | 2030-11-23 12:31 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  |  | 1.0 | 1
Bug | FVVP-342 | 35110 | [Not a bug] Error Adjusting Task Timeline |  |  | Priority 3 | Done | Done | 2014-11-23 15:44 | 2014-11-23 15:47
Bug | FVVP-340 | 35100 | Cancel/Close options change depending on phase |  |  | Priority 3 | Done | Done | 2014-11-23 11:01 | 2014-11-23 13:08
Bug | FVVP-339 | 35096 | Error Completing Set Rent | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 2 | Done | Done | 2013-11-23 15:53 | 2014-11-23 16:32 |  | UAT_Feedback
Bug | FVVP-338 | 34983 | Expected duration validation message | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2013-11-23 12:05 | 2017-11-23 16:20 |  | Deployment_Ready
Story | FVVP-337 | 34974 | Streamline Process of Searching for Tenancy | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2010-11-23 14:41 | 2027-11-23 13:07 |  | IA_Done | OB_Internal | Planning2_Completed | REFINED |  |  |  |  | 2.0 | 2
Bug | FVVP-336 | 34928 | Remove 'My Overdue EOT Tasks' from the EOT Dashboards | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2009-11-23 17:49 | 2020-11-23 14:05 |  | Deployment_Ready | Show_Me_Complete
Story | FVVP-335 | 34927 | Hide Open Task Button if EOT Status is not 'Active' | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2009-11-23 17:27 | 2004-12-23 14:54 |  | IA_Done | OB_Internal | Planning2_Completed | REFINED | Show_Me_Complete | Video_Recorded |  |  | 1.0 | 1
Story | FVVP-332 | 34923 | [Internal - Cosmetic] Adjust Task Timeline | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2009-11-23 16:28 | 2030-11-23 12:34 |  | Deployment_Ready | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  | 1.0 | 1
Bug | FVVP-331 | 34922 | Adjust Task Timeline - Screen layout | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2009-11-23 16:23 | 2021-11-23 12:42 |  | Deployment_Ready | [7 empty] | 1.0
Bug | FVVP-330 | 34921 | Adjust Task Timeline - Expected Duration / End Date not required | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2009-11-23 16:20 | 2017-11-23 16:42 |  | Deployment_Ready | [7 empty] | 0.0
Bug | FVVP-329 | 34920 | [Delete] |  |  | Priority 3 | Done | Done | 2009-11-23 15:46 | 2009-11-23 15:56
Bug | FVVP-318 | 34900 | [Not a bug] Delay Reason required when Expected Duration < KPI Duration | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2008-11-23 12:31 | 2023-11-23 09:52 | [9 empty] | 0.0
Story | FVVP-305 | 34865 | [Internal - Cosmetic] Task Details: Help Text | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2006-11-23 12:13 | 2030-11-23 12:29 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED | Show_Me_Complete |  |  | 1.0 | 1
Story | FVVP-231 | 34506 | [Not Required] Report of Task Times |  |  | Priority 1 | Done | Done | 2003-10-23 16:38 | 2030-11-23 12:31 |  | No_Video | [7 empty] | 0.0
Story | FVVP-197 | 34328 | Update Tenancy Object after Move Out | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2014-09-23 16:29 | 2028-11-23 14:57 |  | IA_Done | Planning2_Completed | REFINED | Scope_Creep | Show_Me_Complete |  |  |  | 2.0 | 2 |  | 2
Story | FVVP-182 | 33433 | [Not Required] Update Task Template - Rename Credit Control Queue |  |  | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:31 |  | IA_Done | No_Video | Planning2_Completed | Sizing_Done | UAT_Feedback |  |  |  | 0.0
Story | FVVP-177 | 33428 | Update Task Template - Close Tenancy | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 2 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:26 |  | Dev_Reviewed | IA_Done | No_Video | Planning2_Completed | REFINED | UAT_Feedback |  |  | 3.0 | 3 | 3
Story | FVVP-174 | 33425 | [Internal - Cosmetic] Remove New EOT Confirmation Screen | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:29 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  |  | 1.0 | 1
Story | FVVP-173 | 33424 | [Internal - Cosmetic] Remove Duplicate Task Name from Outstanding Tasks List | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 4 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:35 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  |  | 1.0 | 1
Story | FVVP-172 | 33423 | Save Next Move In Date on EOT | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2029-11-23 17:53 |  | Dev_Reviewed | IA_Done | Planning2_Completed | REFINED | Scope_Creep | Show_Me_Complete |  |  | 8.0 | 8 |  | 8
Story | FVVP-170 | 33421 | [Internal - Cosmetic] EOTs in Progress Report | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:28 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED | Show_Me_Complete |  |  | 1.0 | 1
Story | FVVP-167 | 33418 | Update Task Template - Confirm Notice after Validate Notice | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:26 |  | Dev_Reviewed | IA_Done | No_Video | REFINED | UAT_Feedback |  |  |  | 1.0 | 1 | 1
Story | FVVP-163 | 33414 | Setup - Delay/Late Completion Reasons | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:28 |  | IA_Done | No_Video | Planning2_Completed | REFINED | Show_Me_Complete |  |  |  | 1.0 | 1
Story | FVVP-150 | 33401 | Reporting - Tasks per Team Report | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 1 | Done | Done | 2001-06-23 14:01 | 2004-12-23 12:51 |  | IA_Done | No_Video | Planning2_Completed | REFINED |  |  |  |  | 2.0 | 2
Story | FVVP-148 | 33399 | My Team's Tasks for Today | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2004-12-23 12:50 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  |  | 4.0 | 4
Story | FVVP-146 | 33397 | Update EOT Lists - All, Recently Viewed | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:28 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED | Show_Me_Complete |  |  | 1.0 | 1
Story | FVVP-145 | 33396 | Dashboard - EOT Owners can monitor EOTs at risk | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 14:17 |  | IA_Done | No_Video | Planning2_Completed | REFINED | Show_Me_Complete | Sizing_Done |  |  | 1.0 | 1
Story | FVVP-143 | 33394 | [Replaced by 358] Dashboard - Users can see their Overdue EoT Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 1 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:28 |  | Deployment_Ready | IA_Done | No_Video | Planning2_Completed | REFINED | Show_Me_Complete | Sizing_Done |  | 1.0 | 1
Story | FVVP-139 | 33390 | Only EOT Owner can Cancel/Close EOT after Notice Confirmed | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 2 | Done | Done | 2001-06-23 14:01 | 2030-11-23 13:44 |  | Dev_Reviewed | IA_Done | Planning2_Completed | REFINED | Scope_Creep | Sizing_Done |  |  | 8.0 | 8 |  | 8
Story | FVVP-134 | 33385 | Remove New Buttons | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:35 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  |  | 1.0 | 1
Story | FVVP-127 | 33378 | Dashboard - Teams with High Number of Tasks | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 1 | Done | Done | 2001-06-23 14:01 | 2004-12-23 12:50 |  | IA_Done | No_Video | Planning2_Completed | REFINED |  |  |  |  | 3.0 | 3
Story | FVVP-125 | 33376 | [Not Required] Minor / Cosmetic Internal Items |  |  | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:25 |  | No_Video | OB_Internal | [6 empty] | 1.0 | 1
Story | FVVP-121 | 33372 | [Internal - Cosmetic] Units Confirmed to be Sold | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:01 | 2030-11-23 12:35 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED | Show_Me_Complete |  |  | 1.0 | 1
Story | FVVP-115 | 33366 | Reopen Amend Direct Debit task if FV Date changes | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 2 | Done | Done | 2001-06-23 14:00 | 2004-12-23 14:47 |  | Dev_Reviewed | IA_Done | Planning2_Completed | REFINED | Scope_Creep | Show_Me_Complete | UAT_Feedback | Video_Recorded | 3.0 | 3 | 3 | 3
Story | FVVP-111 | 33362 | Update EOT Task Lists - All, Recently Viewed | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:29 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED | Show_Me_Complete |  |  | 1.0 | 1
Story | FVVP-109 | 33360 | EOT Timeline Testing - Complex Scenarios | Nikki | 70121:af6196ff-0b2f-4ade-9d2a-c625be89a01c | Priority 3 | Done | Done | 2001-06-23 14:00 | 2021-11-23 13:54 |  | IA_Done | OB_Internal | Planning2_Completed | REFINED |  |  |  |  | 3.0 | 3
Story | FVVP-108 | 33359 | EOT - Incorporate Uplifts into Passing Rent | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2001-06-23 14:00 | 2029-11-23 09:40 |  | IA_Done | Planning2_Completed | REFINED | UAT_Feedback |  |  |  |  | 1.0 | 1 | 1
Story | FVVP-107 | 33358 | Validate EOT Team Names on Building Setup | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:30 |  | Dev_Reviewed | IA_Done | No_Video | Planning2_Completed | REFINED | Show_Me_Complete | UAT_Feedback |  | 2.0 | 2 | 2
Story | FVVP-105 | 33356 | [Internal - Cosmetic] Onsite EOT Tasks Due this Week/Month | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:29 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED | Show_Me_Complete |  |  | 1.0 | 1
Story | FVVP-104 | 33355 | Update Task Template - Task Information | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:34 |  | IA_Done | No_Video | Planning2_Completed | REFINED |  |  |  |  | 1.0 | 1
Story | FVVP-97 | 33348 | Update Stoppage Terminology | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:28 |  | IA_Done | No_Video | REFINED | Show_Me_Complete | UAT_Feedback |  |  |  | 1.0 | 1 | 1
Story | FVVP-82 | 33333 | Data Migration - EOT Queues | Matthew Pitcairn | 712020:6138a31f-37e3-441e-8e84-e7b774920bdc | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:30 |  | IA_Done | No_Video | Planning2_Completed | REFINED | Sizing_Done |  |  |  | 3.0 | 3
Story | FVVP-76 | 33327 | [Internal - Cosmetic] Close/Cancel EOT - Change Screen Order | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:29 |  | IA_Done | No_Video | OB_Internal | Planning2_Completed | REFINED |  |  |  | 1.0 | 1
Story | FVVP-73 | 33324 | Setup - Reasons for Cancelling/Closing an EOT | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:28 |  | IA_Done | No_Video | Planning2_Completed | REFINED | Show_Me_Complete |  |  |  | 1.0 | 1
Story | FVVP-72 | 33323 | Reporting - Cost of Void Report | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 1 | Done | Done | 2001-06-23 14:00 | 2004-12-23 12:49 |  | IA_Done | No_Video | Planning2_Completed | REFINED | Show_Me_Complete |  |  |  | 5.0 | 5
Story | FVVP-63 | 33314 | Update EOT Task List Views with Final Queues | Dillan Landsberg | 712020:bbb8d7bf-a355-4a7c-971f-ee5598a156c1 | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:25 |  | IA_Done | No_Video | Planning2_Completed | REFINED |  |  |  |  | 2.0 | 2
Story | FVVP-56 | 33307 | New EoT - Calculate Estimated PVI Date | Mudzunga Khonani Davhana | 712020:eb63548d-26e3-453b-a750-b0bc694c0f4e | Priority 4 | Done | Done | 2001-06-23 14:00 | 2004-12-23 15:10 |  | Deployment_Ready | IA_Done | Planning2_Completed | REFINED | Show_Me_Complete | Video_Recorded | Scope_Creep |  | 2.0 | 2 |  | 2
Story | FVVP-54 | 33305 | [Not Required] STAGING Data Migration - EOT Queues |  |  | Priority 3 | Done | Done | 2001-06-23 14:00 | 2030-11-23 12:30 |  | IA_Done | No_Video | Planning2_Completed | REFINED | Sizing_Done |  |  |  | 0.0
[21 empty] | 77 | 11 | 23