## Pre-Deployment Steps
S. No. | Story | Summary | Detailed Steps to be performed | Responsible Team Member | Comments
1 | FVVP-99 | Activate Histroy Tracking for Owner On End Of Tenancy and End Of Tenancy Task Object | 1. Sign in as Sys Admin 2. Goto Step->Object Manager->End of Tenancy Object -> Detail -> Click Edit -> Set Track Field History to true for the Object | Avi Purohit

## Post Deployment Steps
S. No. | Story | Summary | Detailed Steps to be performed | Responsible Team Member | Comments
1 | FVVP-49 | Load template data | 1. Login as admin 2. Go to Developer Console --> Debug --> Open Execute Annonymous --> execute the script below to load template data: EoT_CreateTemplateData.setUpData(); | Anjali Salecha | Nothing can be tested before this step is completed successfully.
2 | FVVP-190 | Create Timeline Record and Assign its ID to the custom label | 1. Login with EoT Admin or EoT Sys Admin PS 2. Search for Timeline Application in App Launcher 3. Click on the “Timeline Configuration” Tab 4. Click New, Add End_Of_Tenancy__c in object 5. Click Add Child Object and follow the flow 6. Copy the record Id of the Timeline_Configuration__c record -> Go to Setup -> Search for “Custom Labels” -> EoT_Tasks_Activity_Timeline_Configuration_Id -> Click Edit -> Paste the record Id in the Value -> Save 7. Open any End of Tenancy record page to see the End of Tenancy Task component. 8. Select the component in the Lighting App Builder and enter “Outstanding Tasks” in “Title to display on header” and check the “Check to display the header” and all remaining checkbox | Sachin Deshmukh | Detail steps with screenshot can be found on: https://openboxsoftwareweb.sharepoint.com/:w:/r/sites/Salesforce/Shared%20Documents/Grainger/Grainger%20FVVP%20Deployment%20Document.docx?d=wad95616485de4cd588bdb752fabf0211&csf=1&web=1&e=bAxhtz https://teams.microsoft.com/_#/apps/d7958adf-f419-46fa-941b-1b946497ef84/sections/MyNotebook
3 | FVVP-71 | DLRS | POST DEPLOYMENT: 1. Sign in as SysAdmin 2. Navigate to "Declarative Lookup Rollup Summaries" App -> Navigate to Tab "Manage Lookup Rollup Summaries" 3. Select "Outstanding Require Tasks" picklist item 4. Click "Manage Child Trigger" 5. Select Deploy, wait for confirmation of successful install 6. Repeat for "Total Required Tasks" | Matthew Pitcairn | Deployment items found under the "Custom Metadata" section of Gearset 1. dlrs__LookupRollupSummary2.Outstanding_Required_Tasks 2. dlrs__LookupRollupSummary2.Total_Required_Tasks
4 | FVVP-90 | DLRS | Deploy following two rollup summaries: 1. End_of_Tenancy_Available_Date 2. End_of_Tenancy_Completion_Date Make sure child trigger is deployed and rule active. | Anjali Salecha | Custom metadata types can be used for deployment
5 | FVVP-99 | Activate Histroy Tracking for Owner On End Of Tenancy and End Of Tenancy Task Object | 1. Sign in as Sys Admin 2. Goto Step->Object Manager->End of Tenancy Object ->Fields & Relationships -> Set History Tracking 3. Select Owner field and Save 4. Same For End Of Tenancy Task Object | Avi Purohit
6 | FVVP-94 | Need to update Set Rent Task Template | Goto Set Rent Task Template -> Update the Completion_Flow__c field to the flow API name EoT_Confirm_PVI_Date_Task_Subflow | Avi Purohit | First Check if Task Templates are already, if yes then update task template else skpi this step.
7 | FVVP-129 | Create a New Task Template for "Confirm PVI Date" and Preceding task | Create a new task template with name "Confirm PVI Date" and also create Preceding Task (task ) [Preceding Task is 'Confirm Notice' as per the FVVP-129 and also update Completion_Flow__c field to flow api value EoT_Confirm_PVI_Date_Task_Subflow | Avi Purohit | First Check if Task Templates are already, if yes then update task template else skpi this step.
8 | FVVP-159 | Update Check Unit Condition Task Template | Goto Check Unit Condition Task Template -> Update the Completion_Flow__c field to the flow API name EoT_Check_Unit_Condition_Task_Subflow | Sachin Deshmukh | First Check if Task Templates are present , if yes then update task template else skip this step.
9 | FVVP-140 | Update Check Out Task Template | Goto Check Out Task Template -> Update the Completion_Flow__c field to the flow API name EoT_Check_Out_Task_Subflow | Sachin Deshmukh | First Check if Task Templates are present , if yes then update task template else skip this step.
10 | FVVP-116 | Update Clean Unit Task Template | Goto Clean Unit Task Template -> Update the Preceding Tasks field: Refurb Task, Refresh Task -> Update Works Type field: Refurb, Refresh | Sachin Deshmukh | First Check if Preceding Tasks and Works Type are present , if yes then update else skip this step.
11 | FVVP-183 | Update Deposit Release Task Template | Goto Deposit Release Task Template -> Update the Completion_Flow__c field to the flow API name EoT_Deposit_Release_Task_Subflow | Sachin Deshmukh | First Check if Task Templates Completion_Flow__c field are present , if yes then update task template else skip this step.
12 | FVVP-82 | Create and Assign Team Queues | NB: This story requires the use of the attached Excel doc with this story. Excel document found here: https://openboxsoftwareweb.sharepoint.com/:x:/r/sites/GraingerPLC/Project%20Documents/Salesforce%20-%20End%20of%20Tenancy/4.%20Development/EoT%20Queue%20Post%20Deployment%20Document.xlsx?d=w3bb560d081ee4fcaa3230f24f4efcef5&csf=1&web=1&e=ap61Xh 1. Using Salesforce Inspector, from the 'Distinct Queues' sheet insert Table 1 to create a list of Queues as a Group type object. 2. Then on the same sheet, insert the Table 2 as a 'QueueSobject' object to set the Queue type to EoT Task. 3. Update the 'User Extract' tab to use user infomation from PROD as this populates the 'GroupMember Insert' sheet. 4. Following up, insert the 'GroupMember Insert' sheet as a GroupMember object to add users to the various Queues. 5. Update Buildings based on the second table of the 'Building Queue' to populate the various team fields with the created Queues. | Matthew Pitcairn
13 | FVVP-63 | Update List Views for Queues | NB: This post deployment step is accomplished using Salesforce DX to pull the Queue List View metadata, make manual changes and then push to PROD. NB2: This step has to be complete AFTER FVVP - 82 as that is where the Queues are created. 1. Ensure Salesforce DX is working with your installation of VS Code. 2. Use the VS Code command palette to run the "Create Project" command and follow the dialog to create a standard project with an appropriate name. 3. Run the "Authorize an Org" command and follow the steps to sign into and grant permission for access of the Grainger PROD Org. 4. Run this command: "sfdx force:source:retrieve -m CustomObject:End_Of_Tenancy_Task__c" to pull all the metadata related to the 'End_of_Tenancy_Task__c' object. 5. A file tree will be created and a folder called listViews should be visible under the EoT Task object folder, here you can find all the XML config files. 6. Make use of the find and replace across files tool (Ctrl + Shift + H) to insert XML snippets from the 'My_Open_Tasks' list view file to add column names and filters to all the Queues for the Task object. It is helpful to know Queue List Views have a <FilterScope/> Queue. </> element 7. With the required changes made, save all files and then right click on the listViews folder and select 'SFDX: Deploy Source to Org'. | Matthew Pitcairn