## Instructions
Welcome to the Project Closure Checklist Template
A few key notes before you start working on this template:
1. The intention for this checklist is to serve as a guide for the tasks that need to be completed when a project is closed. Each project should have a completed checklist saved in the Project Documents library on SharePoint.
2. Tasks are labelled as "Mandatory" or "Optional". Manadatory tasks are tasks that need to be completed, however, "Optional" tasks have been added but can be excluded if it's not being used or not applicable to your project.
Should you not complete a "Mandatory" task, it is encouraged to add a short reason in the Notes/Comments column for future reference.
3. Some columns have comments with instructions or additional information. These are marked with a purple flag in the corner.
4. The Status column's drop down is controlled by the list on the "Lists" tab. To add/ remove items from the drop down, make the changes on the "Lists" tab.
5. Links to the relevant Template / URL have been included but are very "general". You can update these links to the project-specific links as you go.
Here's a link to the available User Guides:
Application |  | URL | User Guide
Open Box CRM - MS Dynamics 365 |  | Open Box CRM - Dynamics 365 | CRM User Guide
Project Works |  | Project Works | PW Cheat Sheet

## Closure Checklist
Project Size | Requirement Level | Status | Task | Application | Template / URL | Division/Area/Role Specific | Additional Information | Notes / Comments | Phase
All Size | Mandatory | Done | Communicate project closure with the client | Outlook / MS Teams |  |  | We need a written confirmation sent to the client to communicate the project closure. This step is meant to "close the loop" & communicate the next steps in terms of support. If using PM docs for tracking, ensure status on those docs are "Project closed" on your last PM doc. If using an agile approach, the last Sprint Review can be sent to communicate the project closure. |  | Project Close
All Size | Mandatory | N/A | Project retro with the internal project team | SharePoint & MS Teams | Team Project Retrospective Template |  | General template structure provided, but has been hosted & documented on various online platforms. Whatever works for the team can be used here. | Mainly Sam and one onther team member. We are very aware of how things went as we had detailed sprint retros | Project Close
All Size | Optional | N/A | Project retro with external stakeholders / Capture client sentiment on how the project went | SharePoint & MS Teams | Team Project Retrospective Template |  | Get client sentiment that we can include in the close out report. If it is not a formal retro, could we potentially get their views on how the project went, etc. Judgement call for PM on approach - will they respond better to a discussion / survey / email? Written feedback is preferable, but the approach can be decided on a case-by-case. |  | Project Close
All Size | Mandatory | Done | Complete the Project Register | SharePoint | Project Register
$25k+ Projects | Optional | N/A | Complete a Project Closure report | SharePoint |  |  | Internally focused document that we can save as a reference point for future projects of a similar nature and to aid in updating the live Case Studies presentation. |  | Project Close
All Size | Mandatory | N/A | Update the Case Studies presentation | SharePoint | Open Box Service and Case study Overview |  | Mandatory if this has been identified as a case study. Add a comment if this is not applicable to provide context. Please ensure that where possible, you capture a comment from the business sponsor that we can quote and use in our case study and marketing material. It would also be great to include any key results / metrics achieved for the client in the case study (which the client is happy to share) | Link does not work | Project Close
All Size | Optional | Done | Security & access cleanup / removing accounts from client environments |  |  |  | Serves as a reminder to do some housekeeping where necessary (e.g. if any OB people have left since we started the project / if any access to the client environment needs to be changed/removed). |  | Project Close
All Size | Optional | Done | Complete any outstanding tasks on the work management tool | DevOps, Jira, Asana, Monday.com |  |  | Opportunity for the team to do housekeeping on the backlog (where necessary) or clean up the taskboards & get the code repository in a good place. |  | Project Close
All Size | Optional | Done | Sharing the code & licensing with the client |  |  |  | If this project was completed in our environment, we need to share the code and licensing with the client as they should be the owners. |  | Project Close
All Size | Optional | N/A | Mark Budgets as Inactive on PW (disables timecodes) | Project Works (PW) | Project Works |  | Under the project Settings, navigate to Budget to set the respective budgets as Inactive, by clicking on the Active toggle next to the budget. This is a preventative measure to ensure no further time is logged to a project that is closed, but not archived yet. |  | Project Close
All Size | Mandatory | Done | Ensure all forecasts are accurate and no open future forecasts | Project Works (PW) | Project Works |  |  |  | Project Close
All Size | Mandatory | Done | Ensure all time entries have been reviewed | Project Works (PW) | Project Works |  | Review the final time entries for the project and ensure all billable time has been logged so it can be included in invoicing. |  | Project Close
All Size | Mandatory | Done | Generate & Submit the final invoice on PW | Project Works (PW) | Project Works |  |  |  | Project Close
All Size | Mandatory | Done | Invoice approval (Manager & Finance) on PW | Project Works (PW) | Project Works |  |  |  | Project Close
All Size | Mandatory | Done | Invoice is exported to Xero | Project Works (PW) | Project Works |  | Final invoice needs to be exported to Xero by the finance team before we archive a project. |  | Project Close
All Size | Mandatory | Done | Archive project on PW | Project Works (PW) | Project Works |  | Archive the project on PW once project is fully closed and last invoices paid. Alternatively, archive the project 1 month after completion. |  | Project Close
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: General Templates & URLs included, but can be updated with project-specific links
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This space can be used to comment on why certain checklist items were not actioned (i.e. a mandatory items not done) or just some additional insight for future reference

## Lists
Status
To Do
In Progress
Done
N/A