## v1
Phase | Hours | Lower Bound | Upper Bound | £/hour | # Sprints | Lower Bound | Upper Bound | £/sprint
Analysis | 140 - 160 | 21000 | 24000 | 150 | 3 - 4 | 105300 | 140400 | 35100
Build | 200 - 260 | 24000 | 31200
Project Management | 12 - 15.6 | 1440 | 1872
UAT | 40 - 52 | 4800 | 6240
Production | 5 - 6.5 | 600 | 780
Total | 397 - 494 | 51840 | 64092
| 140 | 160 |  |  | 3 | 4
| 200 | 260 |  |  | #VALUE! | #VALUE!
| 12 | 15.6 |  |  | #VALUE! | #VALUE!
| 40 | 52 |  |  | #VALUE! | #VALUE!
| 5 | 6.5 |  |  | #VALUE! | #VALUE!
| 397 | 494.1 |  |  | #VALUE! | #VALUE!
[5 empty] | 11700 |  |  | 240
2340
780

## v1
Project Phases | Duration | Lower Bound | Upper Bound
Sprint 0 | 6 weeks | 21000 | 24000
Sprint 1 - 4 | 9-12 weeks | 105300 | 140400
UAT | 2 weeks | 3600 | 3600
Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
Sub Total |  | 133500 | 171600
Data Migration |  | 4800 | 19200
Total | 19-22 weeks | 138300 | 190800

## v2
Phase | Hours | Lower Bound | Upper Bound | £/hour |  | # Sprints | Lower Bound | Upper Bound | £/sprint
Analysis | 100 - 120 | 15000 | 18000 | 150 |  | 3 - 4 | 56700 | 75600 | 18900
Build | 140 - 182 | 16800 | 21840
Project Management | 12 - 15.6 | 1440 | 1872
UAT | 40 - 52 | 4800 | 6240
Production | 5 - 6.5 | 600 | 780
Total | 297 - 376 | 38640 | 48732
| 100 | 120 |  |  |  | 3 | 4
| 140 | 182 |  |  |  | #VALUE! | #VALUE!
| 12 | 15.6 |  |  |  | #VALUE! | #VALUE!
| 40 | 52 |  |  |  | #VALUE! | #VALUE!
| 5 | 6.5 |  |  |  | #VALUE! | #VALUE!
| 297 | 376.1 |  |  |  | #VALUE! | #VALUE!
80
|  | 240 |  |  |  | 11700
2340
780
98
112
140
182
| 93 000 | 120 000

## v2 1
Phase | Hours | Lower Bound | Upper Bound | £/hour | # Sprints | Lower Bound | Upper Bound | £/sprint
Analysis | 140 - 160 | 21000 | 24000 | 150 | 3 - 4 | 105300 | 140400 | 35100
Build | 200 - 260 | 24000 | 31200
Project Management | 12 - 15.6 | 1440 | 1872
UAT | 40 - 52 | 4800 | 6240
Production | 5 - 6.5 | 600 | 780
Total | 397 - 494 | 51840 | 64092
| 140 | 160 |  |  | 3 | 4
| 200 | 260 |  |  | #VALUE! | #VALUE!
| 12 | 15.6 |  |  | #VALUE! | #VALUE!
| 40 | 52 |  |  | #VALUE! | #VALUE!
| 5 | 6.5 |  |  | #VALUE! | #VALUE!
| 397 | 494.1 |  |  | #VALUE! | #VALUE!
11700
2340
780

## Latest cost
Project Phases | Duration | Lower Bound | Upper Bound
Sprint 0 | 6 weeks | 15000 | 18000
Sprint 1 - 4 | 9-12 weeks | 70200 | 93600
UAT | 2 weeks | 3600 | 3600
Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
User guide creation | 1 week | 3150 | 3150
Sub Total | 20-23 weeks | 95550 | 121950
Data Migration | Run in parallel with sprints | 4800 | 19200
Total | 20-23 weeks | 100350 | 141150
Cost per sprint
|  |  |  | 6300 | 23400 | 2 x FTE @ GBP780/day
1260
630

## Latest cost 2024-10-28
Project Phases | Duration | Lower | Upper
Grainger Trust Leasing Journey
Sprint 0 | 3-4 weeks | 9000 | 12000
2-3 Sprints | 6-9 weeks | 46800 | 70200
UAT | 2 weeks | 3600 | 3600
Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
Sub Total | 13-17 weeks | 63000 | 89400
Data Migration
Data Migration - extract, transform & load | 6-12 weeks | 4800 | 19200
Sub Total | Run in parallel with sprints | 4800 | 19200
KYC Functionality
KYC analysis and solution design for sharing model changes | 2-3 weeks | 4500 | 6000
KYC implementation | 1 week | 3900 | 3900
KYC UAT - Open Box led UAT to verify sharing changes | 2 weeks | 3600 | 4800 |  | Cost per sprint
Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
|  |  |  | 6300 | 23400 | 2 x FTE @ GBP780/day
Sub Total | 7-8 weeks | 15600 | 18300 | 1260
630

## 2024-10-23
Phase | Hours | Lower Bound | Upper Bound | £/hour |  | # Sprints | Lower Bound | Upper Bound | £/sprint
Analysis | 60-80 | 9000 | 12000 | 150 |  | 3 - 4 | 56700 | 75600 | 18900
KYC analysis | 30-40 | 4500 | 6000 | 150
KYC UAT | 24-32 | 3600 | 4800 | 150
| 60 | 80 |  |  |  | 3 | 4
| 30 | 40 |  |  |  | #VALUE! | #VALUE!
| 24 | 32 |  |  |  | #VALUE! | #VALUE!
| #VALUE! | #VALUE! |  |  |  | #VALUE! | #VALUE!
| #VALUE! | #VALUE! |  |  |  | #VALUE! | #VALUE!
| #VALUE! | #VALUE! |  |  |  | #VALUE! | #VALUE!
80
|  | 240 |  |  |  | 11700
2340
780
98
112
140
182
| 93 000 | 120 000