## Workshops
# | Worksop | Duration | Suggested Date/week | Date | Status | Required | Optional
1 | Renewals Workshop (Renewals Team #1) | 1 Hr |  | 2024-07-22 | Complete | Helen Douglas-Teggart <HDouglas-Teggart@graingerplc.co.uk>; sfarr@graingerplc.co.uk; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> | Jonathan Pitt <JPitt@graingerplc.co.uk>; Yvonne Dargavel <ydargavel@graingerplc.co.uk>
2 | Renewals Workshop (Renewals Team #2) | 1 Hr |  | 2024-07-24 | Complete | Helen Douglas-Teggart <HDouglas-Teggart@graingerplc.co.uk>; sfarr@graingerplc.co.uk; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> | Jonathan Pitt <JPitt@graingerplc.co.uk>; Yvonne Dargavel <ydargavel@graingerplc.co.uk>
3 | Renewals Workshop (Prop Man & Resi Services #1) | 1 Hr |  | 2024-07-29 | Complete | Anita Masters <AMasters2@graingerplc.co.uk>; SLancaster@graingerplc.co.uk; LLakomski@GraingerPlc.co.uk; jpitt <jpitt@graingerplc.co.uk>; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> | Yvonne Dargavel <ydargavel@graingerplc.co.uk>
4 | Renewals Workshop (Asset Management #1) | 1 Hr |  | 2024-07-30 | Complete | VTurnbull@graingerplc.co.uk; jpitt <jpitt@graingerplc.co.uk>; Helen Douglas-Teggart <HDouglas-Teggart@graingerplc.co.uk>; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> | Yvonne Dargavel <ydargavel@graingerplc.co.uk>; Harriet Shaw <HShaw@graingerplc.co.uk>; Daisy Stuckey <DStuckey@graingerplc.co.uk>
5 | Renewals Workshop (Accounts Receivable - Credit Control #1) | 1 Hr |  | 2024-07-31 | Complete | Anne Stephenson <AnneStephenson@graingerplc.co.uk>; HThompson@graingerplc.co.uk; chunter@graingerplc.co.uk; Helen Douglas-Teggart <HDouglas-Teggart@graingerplc.co.uk>; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> | Yvonne Dargavel <ydargavel@graingerplc.co.uk>; Deborah Stein <DStein@graingerplc.co.uk>
6 | Workshop (Complaints Process #1) | 1 Hr |  | 2024-08-06 | Complete | Jenny Lorimer <JLorimer@graingerplc.co.uk> | Yvonne Dargavel <ydargavel@graingerplc.co.uk> Jonathan Pitt <JPitt@graingerplc.co.uk>;
7 | Renewals Workshop (Accounts Receivable - Credit Control # 2) | 1 Hr |  | 2024-08-08 | Complete | Anne Stephenson <AnneStephenson@graingerplc.co.uk>; HThompson@graingerplc.co.uk; chunter@graingerplc.co.uk; Helen Douglas-Teggart <HDouglas-Teggart@graingerplc.co.uk>; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> Jon | Yvonne Dargavel <ydargavel@graingerplc.co.uk>; Deborah Stein <DStein@graingerplc.co.uk>
8 | Renewals Workshop (Renewals Team #3) Agenda: 1) Review the process for non-standard renewals in more detail. (Live Work, Company Lets, Copperworks, DMR & Affordable Rent). 2) Review opportunity screens in Salesforce. 3) Additional questions. | 1 Hr |  | 2024-08-16 | Complete | Helen Douglas-Teggart <HDouglas-Teggart@graingerplc.co.uk>; sfarr@graingerplc.co.uk; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> | Jonathan Pitt <JPitt@graingerplc.co.uk>; Yvonne Dargavel <ydargavel@graingerplc.co.uk>
9 | Demo of MRI Evolution: Complaints Functionality, Work Orders, PVIs (Complaints Process #2) | 1 Hr | 2024-09-09 | 2024-09-10 | Complete | Mike Jones <MJones@graingerplc.co.uk>; Jenny Lorimer <JLorimer@graingerplc.co.uk>; Irina Rose <irina.rose@graingerplc.co.uk>; Sam Duncan <sduncan@openboxsoftware.com>; Nikki Papenfus <npapenfus@openboxsoftware.com>; Jacob Smycz <jsmycz@openboxsoftware.com> | Yvonne Dargavel <ydargavel@graingerplc.co.uk> Jonathan Pitt <JPitt@graingerplc.co.uk>;
10 | Lettings: Review Price Book, viewing feedback & high-level lettings process | 1 Hr | 27/28/29 Aug | 2024-09-12 | Complete | Jonathon Hyde
11 | Finance: Qube | 1 Hr |  | 2024-09-18 | Complete | Henry <hgervaise-jones@graingerplc.co.uk>
12 | Qube-GREP Integration | 1 Hr | After Finance | 2024-09-23 | Complete | Jaic
13 | Customer Lifetime Value | 1 Hr |  | 2024-09-16 | Complete | Andy Masson
14 | Qube-Salesforce Data Model Alignment | 30 Min |  | 2024-09-18 | Scheduled | Jaic, Scott Knight, Sam, Nikki, Jacob | Yvonne Dargavel <ydargavel@graingerplc.co.uk> Jonathan Pitt <JPitt@graingerplc.co.uk>;

## Data
Scheduled | 30 Min
Complete | 1 Hr
To be Scheduled | 1Hr 30
To be Scheduled (Availability Sent)
DO NOT SCHEDULE