## Costing
Key | Summary | Estimate (hours) | Cost
RJ-27 | Adjust renewal logic to use days instead of months | 4 | 464
RJ-26 | Do not exclude opportunities with child opps that are not renewals | 4 | 464
RJ-13 | Enhance offer creation process | 8 | 928
| Total | 16 | 1856

## Timeline
2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday
Development | Development
|  | UAT | UAT
PROD deployment