## Sheet1
Rate | 630
|  | Task | Notes | Duration (weeks) | Total Effort (days) | Cost
|  | Sprint 0 | Analysis / Tech approach / Add items to Jira and work with Grainger to have AC's approved (3 people involved) | 1 | 3 | 1890
|  | Sprint 1 | 3 week deliver. Dev, Test and deployments. Team of 1 Architecht, 1 developer, 1 QA, BA, PM | 3 | 18 | 11340
|  | UAT | 1 week | 1 | 2.5 | 1575
|  | Prod Support | 1 week | 1 | 2.5 | 1575
|  | Total |  | 6 | 26 | 16380

## TImeline
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20
2023-11-01 | 2023-11-08 | 2023-11-15 | 2023-11-22 | 2023-11-29 | 2023-12-06 | 2023-12-13 | 2023-12-20 | 2023-12-27 | 2024-01-03 | 2024-01-10 | 2024-01-17 | 2024-01-24 | 2024-01-31 | 2024-02-07 | 2024-02-14 | 2024-02-21 | 2024-02-28 | 2024-03-06
Analysis | Development | Development | Development | UAT | PROD go live