## Billing Milestones
Cost per sprint | 40950
|  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  |  | March | April | May | June | July | August | September | October | Total
| Release 1 | Sprint 0 | 3: 4095
|  | Sprint 1 | 3: 40950
|  | Sprint 2 | 4: 40950
|  | UAT | 5: 7200
|  | Extention of UAT | 6: 13650
|  | User Guide Updates | 7: 1575
|  | Prod Support | 7: 3600
| Release 2 | Sprint 3 | 5: 40950
|  | Sprint 4 | 6: 40950
|  | Sprint 5 | 7: 40950
|  | Sprint 6 | 8: 40950
|  | Sprint 7 | 9: 40950
|  | UAT | 9: 7200
|  | User Guide Updates | 9: 1575
|  | Prod Support | 10: 3600
|  | Total | 45045 | 40950 | 48150 | 54600 | 46125 | 40950 | 49725 | 3600 | 329145

## Velocity
Sprint | Velocity | Weeks | Velocity per week
Sprint 1 | 31.25 | 5 | 6.25
Sprint 2 | 67.25 | 4 | 16.8125
Sprint 3 | 77.75 | 4 | 19.4375
Sprint 4 | 62.5 | 4 | 15.625
Sprint 5 | 62 | 4 | 15.5
Sprint 6 | 73 | 3 | 24.3333
Sprint 7 | 65 | 3 | 21.6667
Ave | 62.6786 | Total | 119.625

## SOW Costing v2
| Cost per sprint | 40950
| Day Rate | 780
| Hour Rate | 97.5
| FTE Rate | 15600
Release 1
|  |  | Phase | Duration | Lower Bound | Upper Bound
|  |  | Sprint 0 | 2 weeks | 4095 | 4095
|  |  | 2 Sprints | 7 weeks | 81900 | 81900
|  |  | User guide updates | Done in parallel with sprints | 1575 | 1575
|  |  | UAT | 4 weeks | 7200 | 7200
|  |  | Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
|  |  | Total | 15 weeks | 98370 | 98370
Release 2
|  |  | Phase | Duration | Lower Bound | Upper Bound
|  |  | 4-5 Sprints | 12 - 15 weeks | 163800 | 204750
|  |  | User guide updates | Done in parallel with sprints | 1575 | 1575
|  |  | UAT | 2 weeks | 7200 | 7200
|  |  | Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
|  |  | Total | 16 - 19 weeks | 176175 | 217125
TOTAL |  |  |  |  | 274545 | 315495

## Actuals vs Esatimate
Team |  | Util Per Role
Dev Senior | 100% |  | Estaimte | Actual | Util | People
Dev Senior | 100% | Dev Senior | 1760 | 1932.75 | 109.8% | Akshat, Anjalie
Dev Junior | 50% | Dev Junior | 440 | 1272.75 | 289.3% | Matt P, Matt C, Lee, Toro
QA | 50% | QA | 440 | 1168.75 | 265.6% | Khonani, Sarah, Nadia
BA & Architect | 35% | BA & Architect | 308 | 1268 | 411.7% | Sam, Nikki, Jacob
PM | 15% | PM | 132 | 198 | 150% | Shaun
Total Build FTEs | 3.5 | Total | 3080 | 5840.25
Duration
Sprints | 7
Weeks | 21
UAT Extention | 1
Total Weeks | 22
Hours
Estimated | 3080
Billable | 5687.5
Non-Billable | 152.75
Total Actual Hours | 5840.25
Utilization | 189.6%
Over Util Cost | 269124.375
Invoice Total | 329145

## Actuals Vs Estiamte Data
Row Labels | Sum of Sum of Hours | Client Hierarchy - Client | Client Hierarchy - Project | Client Hierarchy - Section | Client Hierarchy - Task | Sum of Hours | % | Employee | Month
Akshat Jain | 1038.5 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 39.5 | 1 | Akshat Jain | Jan 2025
Anjali Salecha | 894.25 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 136 | 1 | Akshat Jain | Feb 2025
Jacob Smycz | 312.5 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 144.5 | 1 | Akshat Jain | Mar 2025
Khonani Davhana | 609.25 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 170 | 1 | Akshat Jain | Apr 2025
Lee Gibbs | 231 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 153 | 1 | Akshat Jain | May 2025
Matthew Cornfield | 637.5 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 170 | 1 | Akshat Jain | Jun 2025
Matthew Pitcairn | 377.75 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 178.5 | 1 | Akshat Jain | Jul 2025
Nadia Swarts | 242.75 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 47 | 1 | Akshat Jain | Aug 2025
Nikki Papenfus | 779.75 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 27.25 | 1 | Anjali Salecha | Jan 2025
Sam Duncan | 175.75 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 120 | 1 | Anjali Salecha | Feb 2025
Sarah Jessiman | 316.75 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 120.5 | 1 | Anjali Salecha | Mar 2025
Shaun Barrett | 198 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 148.5 | 1 | Anjali Salecha | Apr 2025
Tafadzwa Toro | 26.5 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 141 | 1 | Anjali Salecha | May 2025
Grand Total | 5840.25 | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 143.25 | 1 | Anjali Salecha | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 166 | 1 | Anjali Salecha | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 27.75 | 1 | Anjali Salecha | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 4 | 1 | Jacob Smycz | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 15.5 | 0.95385 | Jacob Smycz | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 28 | 1 | Jacob Smycz | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 46.75 | 1 | Jacob Smycz | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 51 | 1 | Jacob Smycz | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 68.5 | 1 | Jacob Smycz | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 70.75 | 1 | Jacob Smycz | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 27.25 | 1 | Jacob Smycz | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Sprint 0 | Sprint 0 | 0.75 | 0.046154 | Jacob Smycz | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 7.25 | 1 | Khonani Davhana | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 98.25 | 1 | Khonani Davhana | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 105.25 | 1 | Khonani Davhana | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 58.75 | 1 | Khonani Davhana | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 92.25 | 1 | Khonani Davhana | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 103.5 | 1 | Khonani Davhana | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 120 | 1 | Khonani Davhana | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 24 | 1 | Khonani Davhana | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 50 | 0.92166 | Lee Gibbs | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 74.5 | 0.8739 | Lee Gibbs | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 78 | 0.89914 | Lee Gibbs | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 4.75 | 1 | Lee Gibbs | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 4.25 | 0.078341 | Lee Gibbs | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 10.75 | 0.1261 | Lee Gibbs | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 8.75 | 0.10086 | Lee Gibbs | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 28.75 | 1 | Matthew Cornfield | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 124.5 | 1 | Matthew Cornfield | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 141.5 | 1 | Matthew Cornfield | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 114 | 1 | Matthew Cornfield | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 105.5 | 0.9814 | Matthew Cornfield | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 96.75 | 1 | Matthew Cornfield | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 24.5 | 1 | Matthew Cornfield | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Release 1 Prod Support | 2 | 0.018605 | Matthew Cornfield | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 0.75 | 0.42857 | Matthew Pitcairn | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 3.75 | 1 | Matthew Pitcairn | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 74 | 1 | Matthew Pitcairn | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 61.25 | 1 | Matthew Pitcairn | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 92.5 | 1 | Matthew Pitcairn | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 59.25 | 1 | Matthew Pitcairn | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 82.5 | 1 | Matthew Pitcairn | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 2.75 | 1 | Matthew Pitcairn | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Sprint 0 | Sprint 0 | 1 | 0.57143 | Matthew Pitcairn | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 21.5 | 0.93478 | Nadia Swarts | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 42 | 1 | Nadia Swarts | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 53.5 | 1 | Nadia Swarts | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 7 | 1 | Nadia Swarts | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 25 | 1 | Nadia Swarts | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 59.75 | 1 | Nadia Swarts | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 32.5 | 1 | Nadia Swarts | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 1.5 | 0.065217 | Nadia Swarts | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 19.25 | 0.57895 | Nikki Papenfus | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 39 | 1 | Nikki Papenfus | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 116.25 | 1 | Nikki Papenfus | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 152 | 1 | Nikki Papenfus | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 145.25 | 1 | Nikki Papenfus | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 103.25 | 1 | Nikki Papenfus | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 144 | 1 | Nikki Papenfus | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 32 | 1 | Nikki Papenfus | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Sprint 0 | Sprint 0 | 14.75 | 1 | Nikki Papenfus | Dec 2024
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Sprint 0 | Sprint 0 | 14 | 0.42105 | Nikki Papenfus | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 5 | 0.76923 | Sam Duncan | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 10 | 1 | Sam Duncan | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 28.75 | 0.93496 | Sam Duncan | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 38 | 1 | Sam Duncan | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 48 | 1 | Sam Duncan | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 14.25 | 0.87692 | Sam Duncan | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 19.25 | 1 | Sam Duncan | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 7 | 1 | Sam Duncan | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 2 | 0.065041 | Sam Duncan | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Release 1 Prod Support | 2 | 0.12308 | Sam Duncan | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Sprint 0 | Sprint 0 | 1.5 | 0.23077 | Sam Duncan | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 21 | 1 | Sarah Jessiman | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 60.5 | 1 | Sarah Jessiman | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 66 | 1 | Sarah Jessiman | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 93.25 | 1 | Sarah Jessiman | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 71.75 | 1 | Sarah Jessiman | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 4.25 | 1 | Sarah Jessiman | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 8 | 1 | Shaun Barrett | Jan 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 15.25 | 1 | Shaun Barrett | Feb 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 27.75 | 1 | Shaun Barrett | Mar 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 37 | 1 | Shaun Barrett | Apr 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 29 | 1 | Shaun Barrett | May 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 33 | 1 | Shaun Barrett | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 30.25 | 1 | Shaun Barrett | Jul 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 17.75 | 1 | Shaun Barrett | Aug 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery | 18.25 | 0.96053 | Tafadzwa Toro | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 0.75 | 0.039474 | Tafadzwa Toro | Jun 2025
|  | Grainger PLC | SVOT & Renewals Journey - Delivery (FC) | Build | Delivery (Non-Billable) | 7.5 | 1 | Tafadzwa Toro | Jul 2025

## Pre Sprint 0 Cost Summary
Cost per sprint | 40950
Day Rate | 780
Hour Rate | 97.5
FTE Rate | 15600 | Phase | Duration | Lower Bound | Upper Bound
|  | Sprint 0 | 3 weeks | 4095 | 4095
|  | Sprints: 5 - 6 | 15 - 18 weeks | 204750 | 245700
|  | User guide creation | Done in parallel with sprints | 3150 | 3150
|  | UAT | 4 weeks | 7200 | 7200
|  | Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
|  | Total | 24 - 29 weeks | 222795 | 263745

## Forecasting
|  |  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33
Scheduling
Velocity
| Total Velocity Done |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Backlog Size |  |  | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
For Bars | Optimistic Forecast |  |  | 0 | 38 | 76 | 114 | 152 | 190 | 228 | 266 | 304 | 342 | 380 | 418 | 456 | 494 | 532 | 570 | 608 | 646 | 684 | 722 | 760 | 798 | 836 | 874 | 912 | 950 | 988 | 1026 | 1064 | 1102 | 1140 | 1178 | 1216 | 1254
| Likely Forecast |  |  | 0 | 35 | 70 | 105 | 140 | 175 | 210 | 245 | 280 | 315 | 350 | 385 | 420 | 455 | 490 | 525 | 560 | 595 | 630 | 665 | 700 | 735 | 770 | 805 | 840 | 875 | 910 | 945 | 980 | 1015 | 1050 | 1085 | 1120 | 1155
| Pessimistic Forecast |  |  | 0 | 25 | 50 | 75 | 100 | 125 | 150 | 175 | 200 | 225 | 250 | 275 | 300 | 325 | 350 | 375 | 400 | 425 | 450 | 475 | 500 | 525 | 550 | 575 | 600 | 625 | 650 | 675 | 700 | 725 | 750 | 775 | 800 | 825
For T&M | Costing
| Team Sprint Cost (Actual) |  |  |  | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400
| Cumulative Team Cost (Actual) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Cumulative Team Cost (Forecast) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | 251550 | 292500 | 333450 | 374400 | 415350 | 456300 | 497250 | 538200 | 579150 | 620100 | 661050 | 702000 | 742950 | 783900 | 824850 | 865800 | 906750 | 947700 | 988650 | 1029600 | 1070550 | 1111500 | 1152450 | 1193400
Team Metrics | Velocity | Sprints | 10%
Optimistic Velocity ( Best Velocity in last 3 sprints) | 38 | 3.4211 | 3.7632
Likely Velocity (Avg Velocity over last 3 sprints) | 35 | 3.7143 | 4.0857 | Sprint 2: Sprint 0; Sprint 3: 3; Sprint 4: 3; Sprint 5: weeks; Sprint 9: 2025-11-15 | Start
Pessimistic Velocity (Worst Velocity in last 3 sprints) | 25 | 5.2 | 5.72 | Sprint 2: Sprints; Sprint 3: 5; Sprint 4: 6; Sprint 9: 2024-12-15 | Month 1 | Weeks | 4
|  |  |  | Sprint 2: Weeks; Sprint 3: 18; Sprint 4: 21; Sprint 5: to UAT; Sprint 9: 2024-01-15 | Month 2 |  | 8
Team Composition | Notes | Allocation | Cost Per Sprint | Sprint 2: Months; Sprint 3: 4.5; Sprint 4: 5.25; Sprint 9: 2023-02-15 | Month 3 |  | 12
Team cost / sprint |  |  | 40950 | Sprint 9: 2022-03-15 | Month 4 |  | 16
Dev Senior |  | 100% |  | Sprint 2: UAT; Sprint 3: 4; Sprint 4: 4; Sprint 5: weeks; Sprint 9: 2021-04-15 | Month 5 |  | 20
Dev Senior |  | 100% |  | Sprint 2: Weeks; Sprint 3: 22; Sprint 4: 25; Sprint 5: to go live; Sprint 9: 2020-05-15 | Month 6 |  | 24
Dev Junior |  | 50% |  | Sprint 2: Months; Sprint 3: 5.5; Sprint 4: 6.25; Sprint 5: to go live
QA |  | 50% |  | Sprint 3: 2024-04-25; Sprint 4: 2024-05-16
BA & Architect | 2x refinement sessions per week | 35%
PM |  | 15% |  | Sprint 2: support; Sprint 3: 2; Sprint 4: 2; Sprint 5: weeks
Total FTEs |  | 3.5 |  | Sprint 0: 420; Sprint 1: hours per sprint; Sprint 2: Weeks; Sprint 3: 24; Sprint 4: 27
Total |  |  | 40950
Day Rate |  | 780 |  | Sprint 0: 4.6154
Hourly Rate |  | 97.5
FTE Rate per month |  | 54600
Sprint |  | 40950

## SOW_OLD
Project Phases | Duration | Duration Lower Bound | Duration Upper Bound | Lower Bound | Upper Bound
Sprint 0 | 2-3 weeks | 2 | 3 | £ 6,000 | £ 9,000 | 6000 | 9000
Sprint 1 - 2 | 3-6 weeks | 3 | 6 | £ 23,400 | £ 46,800 | 23400 | 46800
UAT | 2 weeks | 2 | 2 | £ 3,600 | £ 3,600 | 3600 | 3600
Production Deployment & Post Go-Live Support | 2 weeks | 2 | 2 | £ 3,600 | £ 3,600 | 3600 | 3600
User guide creation | Done in parallel with sprints |  |  | £ 3,150 | £ 3,150 | 3150 | 3150
Sub Total | 9 - 13 weeks |  |  | £ 39,750 | £ 66,150 | 39750 | 66150
Contingency for ongoing post-go live support | 40 hours |  |  | £ - | £ 4,800 |  | 4800
Total | 9 -13 weeks |  |  | £ 39,750 | £ 70,950 | 39750 | 70950

## Timeline Old
Cost per sprint | 23400
UAT | 3600 | Sprint 1 | [20 empty] | Sprint 2 | [20 empty] | UAT | [6 empty] | UAT | [6 empty] | Prod Support | [6 empty] | Prod Support
Prod support | 3600 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
User Guide | 3150 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
 | time axis 2024-10-14 to 2024-12-22
Nov (S1) | 23400
Dec (S2 + UG) | 26550
Jan | 7200
Total | 57150
SOW
Sprint 0 | 9000
Build | 57150
Total | 66150

## Timeline v2 OLD
Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 25 | [6 empty] | Week 25 | [6 empty] | Week 25
Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
 | time axis 2024-12-09 to 2025-06-22
Sprint 0 | [13 empty] | Sprint 1 | [20 empty] | Sprint 2 | [20 empty] | Release 1 - SVOC - SIT | [13 empty] | Release 1 - SVOC - UAT
[56 empty] | Sprint 3 | [27 empty] | Sprint 4 | [20 empty] | Sprint 5 | [20 empty] | Sprint 6 | [20 empty] | Sprint 7 | [20 empty] | Release 2 - Renewals - UAT | [13 empty] | GO LIVE
[84 empty] | Release 1 GO LIVE | [97 empty] | Post go-live support
Release 1 - Post go-live support