## SOW_OLD
Project Phases | Duration | Duration Lower Bound | Duration Upper Bound | Lower Bound | Upper Bound
Sprint 0 | 2-3 weeks | 2 | 3 | £ 6,000 | £ 9,000 | 6000 | 9000
Sprint 1 - 2 | 3-6 weeks | 3 | 6 | £ 23,400 | £ 46,800 | 23400 | 46800
UAT | 2 weeks | 2 | 2 | £ 3,600 | £ 3,600 | 3600 | 3600
Production Deployment & Post Go-Live Support | 2 weeks | 2 | 2 | £ 3,600 | £ 3,600 | 3600 | 3600
User guide creation | Done in parallel with sprints |  |  | £ 3,150 | £ 3,150 | 3150 | 3150
Sub Total | 9 - 13 weeks |  |  | £ 39,750 | £ 66,150 | 39750 | 66150
Contingency for ongoing post-go live support | 40 hours |  |  | £ - | £ 4,800 |  | 4800
Total | 9 -13 weeks |  |  | £ 39,750 | £ 70,950 | 39750 | 70950

## Pre Sprint 0 Cost Summary
Cost per sprint | 40950
Day Rate | 780
Hour Rate | 97.5
FTE Rate | 15600 | Phase | Duration | Lower Bound | Upper Bound
|  | Sprint 0 | 3 weeks | 4095 | 4095
|  | Sprints: 5 - 6 | 15 - 18 weeks | 204750 | 245700
|  | User guide creation | Done in parallel with sprints | 3150 | 3150
|  | UAT | 4 weeks | 7200 | 7200
|  | Production Deployment & Post Go-Live Support | 2 weeks | 3600 | 3600
|  | Total | 24 - 29 weeks | 222795 | 259650

## Forecasting
|  |  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33
Scheduling
Velocity
| Total Velocity Done |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Backlog Size |  |  | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
For Bars | Optimistic Forecast |  |  | 0 | 30 | 60 | 90 | 120 | 150 | 180 | 210 | 240 | 270 | 300 | 330 | 360 | 390 | 420 | 450 | 480 | 510 | 540 | 570 | 600 | 630 | 660 | 690 | 720 | 750 | 780 | 810 | 840 | 870 | 900 | 930 | 960 | 990
| Likely Forecast |  |  | 0 | 26 | 52 | 78 | 104 | 130 | 156 | 182 | 208 | 234 | 260 | 286 | 312 | 338 | 364 | 390 | 416 | 442 | 468 | 494 | 520 | 546 | 572 | 598 | 624 | 650 | 676 | 702 | 728 | 754 | 780 | 806 | 832 | 858
| Pessimistic Forecast |  |  | 0 | 22 | 44 | 66 | 88 | 110 | 132 | 154 | 176 | 198 | 220 | 242 | 264 | 286 | 308 | 330 | 352 | 374 | 396 | 418 | 440 | 462 | 484 | 506 | 528 | 550 | 572 | 594 | 616 | 638 | 660 | 682 | 704 | 726
For T&M | Costing
| Team Sprint Cost (Actual) |  |  |  | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400
| Cumulative Team Cost (Actual) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Cumulative Team Cost (Forecast) |  |  | 0 | 23400 | 46800 | 70200 | 93600 | 117000 | 140400 | 163800 | 187200 | 210600 | 251550 | 292500 | 333450 | 374400 | 415350 | 456300 | 497250 | 538200 | 579150 | 620100 | 661050 | 702000 | 742950 | 783900 | 824850 | 865800 | 906750 | 947700 | 988650 | 1029600 | 1070550 | 1111500 | 1152450 | 1193400
Team Metrics | Velocity | Sprints | 10%
Optimistic Velocity ( Best Velocity in last 3 sprints) | 30 | 4.3333 | 4.7667 | Sprint 2: Sprint 0; Sprint 3: 3; Sprint 4: 3; Sprint 5: weeks; Sprint 9: 2025-11-15 | Start
Likely Velocity (Avg Velocity over last 3 sprints) | 26 | 5 | 5.5 | Sprint 2: Sprints; Sprint 3: 5; Sprint 4: 6; Sprint 9: 2024-12-15 | Month 1 | Weeks | 4
Pessimistic Velocity (Worst Velocity in last 3 sprints) | 22 | 5.9091 | 6.5 | Sprint 2: Weeks; Sprint 3: 18; Sprint 4: 21; Sprint 5: to UAT; Sprint 9: 2024-01-15 | Month 2 |  | 8
|  |  |  | Sprint 2: Months; Sprint 3: 4.5; Sprint 4: 5.25; Sprint 9: 2023-02-15 | Month 3 |  | 12
Team Composition | Notes | Allocation | Cost Per Sprint | Sprint 9: 2022-03-15 | Month 4 |  | 16
Team cost / sprint |  |  | 40950 | Sprint 2: UAT; Sprint 3: 4; Sprint 4: 4; Sprint 5: weeks; Sprint 9: 2021-04-15 | Month 5 |  | 20
Dev Senior |  | 100% |  | Sprint 2: Weeks; Sprint 3: 22; Sprint 4: 25; Sprint 5: to go live; Sprint 9: 2020-05-15 | Month 6 |  | 24
Dev Senior |  | 100% |  | Sprint 2: Months; Sprint 3: 5.5; Sprint 4: 6.25; Sprint 5: to go live
Dev Junior |  | 50% |  | Sprint 3: 2024-04-25; Sprint 4: 2024-05-16
QA |  | 50%
BA & Architect | 2x refinement sessions per week | 35% |  | Sprint 2: support; Sprint 3: 2; Sprint 4: 2; Sprint 5: weeks
PM |  | 15% |  | Sprint 2: Weeks; Sprint 3: 24; Sprint 4: 27
Total FTEs |  | 3.5 |  | Sprint 0: 420; Sprint 1: hours per sprint
Total |  |  | 40950
Day Rate |  | 780 |  | Sprint 0: 4.6154
Hourly Rate |  | 97.5
FTE Rate per month |  | 54600
Sprint |  | 40950

## Timeline
Cost per sprint | 23400
UAT | 3600 | Sprint 1 | [20 empty] | Sprint 2 | [20 empty] | UAT | [6 empty] | UAT | [6 empty] | Prod Support | [6 empty] | Prod Support
Prod support | 3600 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
User Guide | 3150 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
 | time axis 2024-10-14 to 2024-12-22
Nov (S1) | 23400
Dec (S2 + UG) | 26550
Jan | 7200
Total | 57150
SOW
Sprint 0 | 9000
Build | 57150
Total | 66150