## Sheet1
SVOT
Original Features | In Scope | Comments
Align Salesforce & Qube Tenancy Data Model | In
See Current Tenancy Arrears | Delayed | Salesforce development complete. Awaiting data warehouse integration to be completed before Tenancy Review go live.
Import Passing Rent | Delayed | Salesforce development complete. Awaiting data warehouse integration to be completed before Tenancy Review go live.
See a History of Price Book Rent & ERVs | Delayed | Grainger to confirm timing on whether ERVs can be pushed from Qube or whether files to be uploaded. Price book rent files to be uploaded at Tenancy Review go live.
Enable Omni-Channel Communications | On Hold - Revisit | Grainger to discuss including a WhatApp pilot for Tenancy Review team only.
Tenancy Review
Original Features | In Scope | Comments
Automatically Create Rent Review Opportunities | In
Receive Early Intention to Renew | Out | Replaced by 6-month touchpoint survey (out of scope, delivered by existing/enhanced touchpoint survey functionality on Marketing Cloud)
PM/RSM Approve Renewals | Out | Not required with Renter’s Rights
AM Set Offer & Minimum Price | In
AM See Projected Growth on Rent for Current Renewals | In
Manage Unit Condition & Pricing Factors | Simplified | Pricing factors in SF, Grainger investigating importing more unit information from Qube
Manage Renewal Requests & Blockers | Out | Simplified to be a single 'requests' field. Grainger working on other project to save tenant requests raised via the app in Salesforce; keeping this simple & can align with larger project in future.
Negotiators Manage/Monitor Renewal Progress | In
Tenants Respond to Offers Online | In
Tenant Counteroffer & AM Approval | In
Initiate EOT if tenant provides NTQ | Changed | Requirement is to rather close opportunity when EOT is initiated by Grainger. Want to follow up with tenant first & negotiate before moving ahead with EOT.
Backlog Features excluded from Original Scope
Send tenants a notification of rent increase (Section 13 notice) instead of contracts (for applicable agreement types). | In
Customise the renewals journey, including generating alternate documentation and alternate email templates, for: - Wales | In | Include generating documents if capacity?
Customise the renewals journey, including generating alternate documentation and alternate email templates, for: - Company Lets - Live/Work Units - DMR & Affordable Rent Units | Partial | Alternate email templates; generating documents out of scope
Provide a new dashboard for Asset Management that displays comparable rent & current performance by estate & unit type. | Simplified | See recent rent achieved & vacant units for comparable units.
Creating, updating, renewing tenancies with no term | In
Incorrect Assumptions
Identifying Grainger Trust Units | In | Was assumed would be completed durign Grainger Trust project beforehand. Adding tenure to Salesforce