## Updated Effort Estimate
Phase | Task |  | Hours | % | Notes | Rate | 120
Pre-Refresh Analysis |  |  | 25 |  | 1 week | Contingency | 10%
| Planning with Grainger across all connected systems | 4 |  |  |  | Range Driver | 30%
| Identify all Salesforce integrations/applications that require post refresh action & document refresh steps | 8
| Playbook document creation | 8 | [9 empty] | Dev Hours | Lower Bound | Upper Bound
| Backup of SIT and UAT configuraiton in version control | 1 |  |  |  |  | Lower bound | Upper Bound |  |  | Email Alerts - Logic Apps | 8 | 0 | 0
| Meetings and alignment | 4 |  |  |  | Hours | 69.3 | 90.09 |  |  | Default Tags - Custom Web | 12 | 0 | 0
Refresh |  |  | 4 |  | 3 weeks | Cost | 8316 | 10810.8 |  |  | Wachlist - Custom Web | 4 | 0 | 0
| Refresh UAT sandboxes (templates, monitoring progress, activation) | 2 | [9 empty] | 24 | 0 | 0
| Refresh SIT sandboxes (templates, monitoring progress, activation) | 2
[6 empty] | Phase | Hours Lower Bound | Hours Upper Bound | Lower Bound | Upper Bound
[6 empty] | Pre-Refresh Analysis | 25 | 28 | 3000 | 3360
[6 empty] | Refresh | 4 | 5 | 480 | 600
[6 empty] | Project Admin Phase | 8 | 9 | 960 | 1080
Project Admin Phase |  |  | 8 |  |  | Post Refresh Updates | 10 | 11 | 1200 | 1320
| Team familiarization | 0 |  |  |  | End-to-end Testing | 16 | 18 | 1920 | 2160
| Project Management | 2 |  |  |  | Total | 63 | 71 | 7560 | 8520
| Client Meetings and alignment | 6
Post Refresh Updates |  |  | 10
| Obfuscation of customer emails (and other PII data if required) - SIT & UAT | 4
| Update of endpoints for HomeLet, RightMove, Grainger Website API - SIT & UAT | 2
| Assitance with Grainger integration setup (Conga, AdobeSign, GREP, Letting portal etc.) | 4
End-to-end Testing |  |  | 16
| End-to-end testing - UAT | 10
| End-to-end testing - SIT | 6
63
0
Assupmtions
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove if Analysis estimate
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example: - There will only be 1 environment - Produciton. This may impact support and live use. - This will be a supervised solution (ie user will need to be logged in) - Project will be billed T&M @ a rate of xxx - Client will add a user with the appropriate licenses in Azure AD - (Power Automate RPA) - Licensing is $40 p/m per environment (Power Automate with RPA) - Production support xxx - A new account will be set up for the Automation to access xxxx

## Original Effort Estimate
Phase | Task |  | Hours | % | Notes | Rate | 120
Pre-Refresh Analysis |  |  | 21 |  | 1 week | Contingency | 10%
| Planning with Grainger across all connected systems | 4 |  |  |  | Range Driver | 30%
| Identify all Salesforce integrations/applications that require post refresh action & document refresh steps | 8
| Playbook document creation | 8 | [7 empty] | Dev Hours | Lower Bound | Upper Bound
| Backup of SIT and UAT configuraiton in version control | 1 |  |  |  |  | Lower bound | Upper Bound | Email Alerts - Logic Apps | 8 | 0 | 0
Refresh |  |  | 2 |  | 3 weeks | Hours | 49.5 | 64.35 | Default Tags - Custom Web | 12 | 0 | 0
| Refresh SIT and UAT sandboxes (templates, monitoring progress, activation) | 2 |  |  |  | Cost | 5940 | 7722 | Wachlist - Custom Web | 4 | 0 | 0
[10 empty] | 24 | 0 | 0
Project Admin Phase |  |  | 2
| Team familiarization | 0
| Project Management | 2
Post Refresh Updates |  |  | 10
| Obfuscation of customer emails (and other PII data if required) - SIT & UAT | 4
| Update of endpoints for HomeLet, RightMove, Grainger Website API - SIT & UAT | 2
| Assitance with Grainger integration setup (Conga, AdobeSign, GREP, Letting portal etc.) | 4
End-to-end Testing |  |  | 10
| End-to-end testing - SIT & UAT | 10
45
0
Assupmtions
Exclusions
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove if Analysis estimate
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example: - There will only be 1 environment - Produciton. This may impact support and live use. - This will be a supervised solution (ie user will need to be logged in) - Project will be billed T&M @ a rate of xxx - Client will add a user with the appropriate licenses in Azure AD - (Power Automate RPA) - Licensing is $40 p/m per environment (Power Automate with RPA) - Production support xxx - A new account will be set up for the Automation to access xxxx
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example: - There will only be 1 environment - Produciton. This may impact support and live use. - This will be a supervised solution (ie user will need to be logged in) - Project will be billed T&M @ a rate of xxx - Client will add a user with the appropriate licenses in Azure AD - (Power Automate RPA) - Licensing is $40 p/m per environment (Power Automate with RPA) - Production support xxx - A new account will be set up for the Automation to access xxxx

## Sheet1
Phase | Hours | Lower Bound | Upper Bound
Pre-Refresh Analysis | 20-22 | 2400 | 2640
Refresh | 2-3 | 240 | 360
Post-refresh updates | 10-12 | 1200 | 1440
End-to-end testing | 10-12 | 1200 | 1440
Project management | 2-3 | 240 | 360
Total | 44 - 52 | 5280 | 6240
| 20 | 22
| 2 | 3
| 10 | 12
| 10 | 12
| 2 | 3
| 44 | 52