## High Level Sequencing
UAT Refresh
Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday
17/06/2024 |  | 18/06/2024 |  | 19/06/2024 |  | 20/06/2024 |  | 21/06/2024
Task | Duration | Task | Duration | Task | Duration | Task | Duration | Task | Duration
Salesforce Refresh UAT | 6 hours | Salesforce post refresh tasks | 8 hours | Salesforce post refresh tasks | 8 hours | End-to-end testing | 8 hours | End-to-end testing | 8 hours
|  |  |  | Other system (GREP, Qube etc.) post refresh tasks |  |  |  | Smoke testing | 8 hours
GREP Refresh
|  | Qube UAT instance refresh full copy, DB restore | 8 hours
|  | Copy XREF - UAT | 8 hours
|  | Refresh Proactis (UAT) | 2 hours
|  | Refresh MyGrainger (UAT) | 2 hours
|  | Refresh Axis (UAT) | 2 hours

## Pre - Refresh Planning
| Refresh Coordinator | Grainger (Yvonne?)
S. No. | Task | Task Details
1 | Finalize refresh start date | find out summer 24 release date, minor release update date for production org. Avoid release update windows
2 | Sequence of refresh | Identify sequence of , staging, UAT & SIT refresh
3 | Identify key modules alongwith resposible person | renewals, homelet integration, renewals phase 2, grainger website, eot, axis eot
4 | Take backup | Take backup of existing configurations or clone existing sandbox if possible
5 | Plan for urgent issue fix needs | plan for any urgent fixes needs when refresh is in progress
6 | Email fields updates | Identify if email fields across all objects to be updated with refresh
7 | PII or personal info | Identify any PII or personal info to be masked with refresh
8 | Refresh notifications for team | Prepare refresh notifications for team
9 | Freeze production org updates | Do not allow production environment code updates and config changes
10 | Identitfy the key intergration and its related settings | Identify exisitng integration like Qube, GREP, RightMove, Conga etc and their related settings that may need to be performed
11 | Identify users who should retain valid email addresses in refreshed UAT sandbox | specify a public group of users at the time of refresh who will automatically get access to the sandbox after refresh.

## Pre - Refresh Tasks
Task ID | Task Summary | Start Date & Time | Task Details | Sandbox | Related Module | Responsible Person | Predecessors | Expected Duration | Status | Comments
SPRE_1 | Backup UAT sandbox configuration | 2024-06-17 | Use Gearset to commit all config metadata from UAT sandbox into Grainger Github repo. Create new branch "UAT_BACKUP_YYYY_MM_DD" for commit. | UAT | N/A | Openbox - Sachin | N/A | 20 mins | Completed
SPRE_2 | Backup SIT sandbox configuration | 2024-06-17 | Use Gearset to commit all config metadata from SIT sandbox into Grainger Github repo. Create new branch "SIT_BACKUP_YYYY_MM_DD" for commit. | SIT | N/A | Openbox - Sachin | N/A | 20 mins | Completed
SPRE_3 | Backup STAGING sandbox configuration | 2024-06-17 | Use Gearset to commit all config metadata from SIT sandbox into Grainger Github repo. Create new branch "STAGING_BACKUP_YYYY_MM_DD" for commit. | STAGING | N/A | Openbox - Sachin | N/A | 20 mins | Completed | STAGING sandbox will not exist in future refreshes
SPRE_4 | Delete STAGING sandbox | 2024-06-18 | Delete STAGING sandbox to free up full copy sandbox | STAGING | N/A | Openbox - Sachin | SPRE_3 | 20 mins | Completed
SPRE_5 | Refresh UAT sandbox | 2024-06-17 | Refresh UAT using full copy sandbox. Include all objects and data (field history, Chatter etc.) | UAT | N/A | Openbox - Sachin | SPRE_4 | 1 hour | Completed | Actual timings => 12:15 PM to 12:45 PM (30 mins)
SPRE_6 | Activate UAT sandbox | 2024-06-17 |  | UAT | N/A | Openbox - Sachin | SPRE_5 | 2 hours | Completed | Actual timings => 12:45 PM to 2:15 PM (1.5 hours)

## Salesforce Post Refresh Tasks
Detailed UAT Post Refresh Steps
Task ID | Task Summary | Task Details | Related Module | Responsible Person | Predecessors | Start Date & Time | Expected Duration | Status | Comments
SPOST_1 | Anonymise Lead data | Use Salesforce inspector to anonymise Lead records. Update email with Salesforce ID to ensure every email is unique e.g. jaic@gmail.com (from Lead ID 0032342342345add) would be updated to jaic@0032342342345add.invalid Update Phone and MobilePhone with "1234567890" Deactivate validation rule Require_building_for_conversion and Qualified_Out_Wait_Reason (Activate after the update) Create permission set From Setup, enter Permission Sets. Click Permission Sets. Click New. Enter a name for the permission set. Click Save. Click App Permissions. Click Edit. Under Sales, select the View and Edit Converted Leads permission. Save the permission set. From Setup, enter Users. Click Users. Click the user you want to assign the new permission set to. Scroll to the Permission Sets related list and then click Edit Assignments. Assign the permission set to the user and click Save. Remove Permission set after use |  | Openbox - Sachin | N/A | 2024-06-17 | 1 hours | Completed | 1,59,989 lead's Email and Phone number anonymised succesfully Actual time spent: 2 hrs
SPOST_2 | Anonymise Account data | Use Salesforce inspector to anonymise Contact records. Fields to be anonymised to be agreed with Grainger. |  | Openbox - Sachin | N/A | 2024-06-11 |  | No Longer Required | Person Account records are automatically updated when Contact records are updated
SPOST_3 | Anonymise Contact data | Create Custom Setting and Assign it to user Go to Setup => Search => Custom Settings =>Seach "Configuration"=> CLick Manage => Click New => Location = User => Select Openbox => Check below options=> Are Processes Off , Are Workflows Off, Are Validations Off => Save Delete this custom setting configuration , after update Use Salesforce inspector to anonymise Contact records. Update email with Salesforce ID to ensure every email is unique e.g. jaic@gmail.com (from Contact ID 0032342342345add) would be updated to jaic@0032342342345add.invalid Update Phone and MobilePhone with "1234567890" |  | Openbox - Sachin | N/A | 2024-06-17 | 1 hours | Completed | All 73,798 contact records Email, Phone anonymised succesfully 2,956 had missing email, hence added test@RecordIdAdd..invalid 2,827 records had missing FirstName, hence "Test" was added in their first name Actual time spent: 2 hours (due to multiple validation rules missing out)
SPOST_4 | Reset email for admin users | Remove .invalid from the admin users. Find users with SOQL below: select id,name,profile.name,email from user where profile.name like '%system%' and isactive = true |  | Openbox - Sachin | N/A | 2024-06-17 | 15 mins | Completed | Removed ".invalid" from 13 users with profiles System Support, Salesforce API Only System Integrations, System Administrator
SPOST_5 | Update Named Credentials for Grainger Website API | 1. Go to setup --> Named Credentials 2. Open Named Credentials - GraingerWebsite_Credentials 3. Make sure the URL is set to following for test environments. UAT: https://o74gxjzrsmda2ihnj4hair36ay0fbyef.lambda-url.eu-west-2.on.aws 4. Now click open the External Credentials related to above Named Credentials. Name of External Credentials is - GraingerWebsite_Auth 5. Go to Principals section --> click edit in front of "API_KEY" 6. Here under "Authentication Parameters", Parameter 1, which has name = Key, set the value for this UAT: f4441bcb9d618b3f39b91c196a423b Note this value will be different in production environment. | Grainger Website API | Openbox - Sachin | SPOST_4 | 2024-06-18 | 1 hours | Completed | Missing Tenancy Progression Manager profile Actual Time : 2 hours
SPOST_6 | API call out from Salesforce to HomeLet | Update named credential for API call out from Salesforce to HomeLet UAT Add Named Credentials Name Referencing HL Named Credentials URL https://kr51a3q1x5.execute-api.eu-west-2.amazonaws.com Check Enable for Callout External Credential Referencing HL Ext Creds Check Generate Authorization Header Add new Remote site setting - https://kr51a3q1x5.execute-api.eu-west-2.amazonaws.com/standardapi/v1 Update Callback URL in auth. provider to the value given under Salesforce Configuration section of Auth. Provider Add External Credentials Label Referencing HL Ext Creds Authentication Protocol OAuth 2.0 Authentication Flow Type Browser Flow Scope standardapiaccess Authentication Provider Referencing HL Auth Provider Add Auth Provider Name Referencing HL Auth Provider Agent Code 2023000961 Plugin ReferencingUtilHLAuthProvider (APEX Class) Auth Provider Name HomeLet Callback URL https://graingerplc--sit.sandbox.my.salesforce.com/services/authcallback/Referencing_HL_Auth_Provider Callout URL https://kr51a3q1x5.execute-api.eu-west-2.amazonaws.com Client Id 2023000961_GraingerUAT Client Secret U8uIzInxUd7l2ZpxBPFhCj9NbzkRcnIc Scope standardapiaccess Principals Parameter Name Referencing_HL_Callout_uvDTUtM1683181096536 Identity Type Named Principal | HomeLet referencing | Openbox - Sachin | N/A | 2024-06-18 | 30 mins | Completed | Actual Time : 2 hours
SPOST_7 | Connected app credentials for API call out from HomeLet to Salesforce | Get updated client key + secret for "HomeLet" connectd app (used by Vision+ API call-in from HomeLet to Salesforce to update referencing status) and supply to HomeLet team so they can update integration credentials on their side Send updated credentials via onetimesecret.com to Jignesh.Chovatiya@pib-insurance.com | HomeLet referencing | Open Box to liaise with HomeLet | N/A | 2024-06-19 | 10 mins | Completed
SPOST_8 | Connected app credentials for Single Sign On for HomeLet | Get updated client Key & secret for "VisionPlus Agent Portal" connected app (used by Vision+ Agent Portal for single sign on) Send updated credentials via onetimesecret.com to Jignesh.Chovatiya@pib-insurance.com | HomeLet referencing | Open Box to liaise with HomeLet | N/A | 2024-06-19 | 10 mins | Completed
SPOST_9 | Schedule renewal batch job | Ensure renewals batch job is scheduled Go to Setup=> Scheduled Jobs => Click Schedule Apex => Enter Job Name = Clone Renewal Opportunities => Apex Class = Renewals_OpportunityCloneScheduler Click Schedule Using = Schedule Builder => Run Weekly => Select every day => Start Date = today => End Date 5 years later => Prefered Start Time = 08:00 | Renewals | Open Box - Sachin | N/A | 2024-06-19 | 5 mins | Completed
SPOST_10 | Setup Axis EoT report Subscription | Login as “Axis Void Manager, Daily Report Recipient User“--> Make sure this user has email address "axisreletsuat@graingerplc.co.uk", if not update and get it verified --> Go to reports tab --> Look for 'Axis Void Report' --> click subscribe --> add Report running user “Axis Void Manager, Daily Report Recipient User“.- Make sure report running user has time zone of (GMT+01:00) British Summer Time (Europe/London) Subscribe report - as attachment, formatted xls, delivered at 2:00 AM. Subscribe to this report for Openbox user | EoT | Open Box - Sachin |  | 2024-06-18 | 15 mins | In Progress | Waiting for email axisrelets@graingerplc.co.uk to get verified by the end user
SPOST_11 | Update Single Sign On |  | Single Sign On | Grainger - Dan Snelling | N/A | 2024-06-19 | 15 mins | Completed
SPOST_12 | Update Rightmove referencing | Rightmove referencing updates that come back into Salesforce via API with connected app (key + secret) | Rightmove referencing | Grainger / RightMove - TBD | N/A | 2024-06-19 |  | Not Started
SPOST_13 | Updating the named credentials in Salesforce related to the integrations | Conga Integration Settings (Placeholder) | Conga | Grainger - Saji | N/A | 2024-06-19 |  | Completed
SPOST_14 | Updating the named credentials in Salesforce related to the integrations | AdobeSign Integration Settings (Placeholder) | AdobeSign | Grainger - Saji | N/A | 2024-06-19 |  | Completed
SPOST_15 | Updating the named credentials in Salesforce related to the integrations | Qube Integration Settings (Placeholder) | Qube | Grainger - Jaic | N/A | 2024-06-19 |  | Completed
SPOST_16 | Connected app credentials for GREP integration | GREP Integration Settings Go to Setup=> Search App Manager => Go to GREP => Click View => Click Manage Consumer Details => Copy Consumer Key and Consumer Secret to https://onetimesecret.com/ => Generate and share the secret link to jgeorge@graingerplc.co.uk | GREP | Grainger - Jaic | N/A | 2024-06-19 |  | Completed
SPOST_17 | Updating the named credentials in Salesforce related to the integrations | Asperato Integration Settings (Placeholder) | Asperato | Grainger - Saji | N/A | 2024-06-19 |  | Completed
SPOST_18 | Updating the named credentials in Salesforce related to the integrations | Media upload Integration Settings (Placeholder) UAT Lable : GraingerApi_MediaAssets Name GraingerApi_MediaAssets URL https://2ber5lica6.execute-api.eu-west-2.amazonaws.com/dev/ Identity Type Named Principal Authentication Protocol Password Authentication Username : x-api-key Password: <to be supplied by Jaic> Check Allow Merge Fields in HTTP Header | Media upload | Grainger - TBD | N/A | 2024-06-19 |  | Completed
SPOST_19 | Update FederationIdentifier of users | Update all active users with username containing "grainger" to set the FederationIdentifier = username (with first two letters capitalised) for SSO as per xls at https://openboxsoftwareweb.sharepoint.com/:x:/r/sites/GraingerPLC/Project%20Documents/UAT%20Refresh/04%20Delivery/Federation%20ID%20update.xlsx?d=w0fd1dbd77d9a4a748be56b4fa75c32c2&csf=1&web=1&e=1lyuD9 |  | Open Box - Sachin | N/A | 2024-06-19 |  | Completed
SPOST_20 | Connected app credentials for Grainger Letting Portal | Go to Setup=> Search App Manager => Go toWebApp=> Click View => Click Manage Consumer Details => Copy Consumer Key and Consumer Secret to https://onetimesecret.com/ => Generate and share the secret link to jgeorge@graingerplc.co.uk | WebApp | Open Box - Sachin | N/A | 2024-06-19 | 10 mins | Completed
SPOST_21 | Enable the OAuth Username-Password Flows for WebApp | Go to Setup=> Search OAuth and OpenID Connect Settings => Make sure that Allow OAuth Username-Password Flows and Allow OAuth User-Agent Flows are enabled | WebApp | WebApp | WebApp | WebApp | 10 mins | Completed
SPOST_22 | Update the IP Relaxation for WebApp | Go to Setup=> Search App Manager => Go to WebApp => Click Editt => Click Edit Policies => IP Relaxation = Relax IP Restrictions | WebApp | WebApp | WebApp | WebApp | 10 mins | Completed
SPOST_23 | Rightmove publishing configuration | Complete configuration steps so that Unit__c records can be published/updated/removed from Rightmove. | Unipt Publish and Update | Grainger - TBD | N/A
SPOST_24 | HomeLet Portal link | Update URL for "HomeLet Portal" button on Opportunity to use URL " n" [screenshot] | HomeLet referencing | Openbox - Sachin | N/A | 2024-06-26 |  | Completed | See screenshot

## Business Processes to Test
Lead to Lease
Create Lead
Convert lead
Create Offer
Create pdf of offer via Conga
Send offer and allow offer selection via lettings portal
Advance payment via Asperato
Referencing via HomeLet
Lease generation via Conga
Lease e-signature via AdobeSign
Publishing Unit to RightMove & Grainger Website
Upload media
Publish/remove listing from Grainger Website
Publish/remove listing from RightMove
End of Tenancy
Create EoT
Close tasks and validate phase progression
Check axis EoT report
Renewals
Check for opp cloning

## GREP Tasks
GREP Tasks
1 | Stop All the Polling services
2 | Copy the XREF from Prod backup
3 | Ensure the XREF is updated with Email masking
4 | Ensure the customer portal and Axis enteries cleared.
5 | Update the COA and SC mapping table in GREP

## Screenshots
V+ Agent Portal
Homelet App
Rightmove referencing
UAT GraingerWebsite Credentials
X-API-KEY
{! '' & $Credential.GraingerWebsite_Auth.Key}
SIT Named Credentials |  | GraingerApi_MediaAssets | Referencing HL Named Credentials
Axis Void User
axisreletsuat@graingerplc.co.uk
Anonymise Lead Data
Anonymise Contact Data
Custom Setting
Auth Provider
HomeLet Portal button

## Picklist values
Not Started
In Progress
Completed
No Longer Required