## Sheet1
Phase | Hours | Lower Bound | Upper Bound
Analysis & Solution Architecture billed on a Time & Materials (T&M) basis @ £120/hour. | 80 - 120 | 9600 | 14400
Delivery billed @ £18 900 per sprint. | 200 - 260 | 24000 | 31200
Project Management | 12 - 15.6 | 1440 | 1872
UAT | 40 - 52 | 4800 | 6240
Production | 5 - 6.5 | 600 | 780
Total | 337 - 454 | 40440 | 54492
| 80 | 120
| 200 | 260
| 12 | 15.6
| 40 | 52
| 5 | 6.5
| 337 | 454.1
Project Phase |  | Lower Bound | Upper Bound | Estimated Duration
Analysis & Solution Architecture billed on a Time & Materials (T&M) basis @ £120/hour. | 80–120 hours | 9600 | 14400 | 4 – 5 weeks
Delivery billed @ £35 100 per sprint. | 2-3 sprints | 70200 | 105300 | 6 - 9 weeks
UAT billed on a T&M basis @ £120/hour. | 40 hours | 4800 | 4800 | 2 weeks
Post Go-Live Support billed on a T&M basis @ £120/hour. | 20 hours | 2400 | 2400 | 2 weeks
Total |  | 87000 | 126900 | 14-17 weeks