## Sheet1
| Change | Lower Bound (Hours) | Upper Bound (Hours) | Notes / Assumptions
new | Disable api callout to create referencing request when Advance Payment is made | 2 | 4 | Dsiable callout. Test classes will need to be adjusted
current - update | Email to non-lead tenant to complete referencing | 2 | 4 | Assuming letting portal URL remains unchanged and lettings portal will handle the logic to guide the tenant through the process. We just need to stop email being sent to lead tenant and send to non-lead tenants only
current - update | Email to applicants to complete referencign - chases | 2 | 4 | Assuming chaser emails don't need any changes (i.e. letting portal URL remains unchanged). Minor changes to copy.
new | Additional details captured for the referencing status (approved etc) (new field to have data in) | 1 | 1 | New field to capture additional information passed back from HomeLet via the REST API
new | OCRs added manually after advance payment made, email sent to leasing portal so they can complete refrerencing | 4 | 8 | Create new flow to trigger emails when OCR's added. Assuming that email will contain URL to letting portal. Letting portal will be responsible for orchestrating callouts to HomeLet to create new referencing request
current - update | Remove Error component on opp - not needed anymore as errors handled on the website | 1 | 1 | Remove component from lightning record page (LRP)
| Assistance during end-to-end UAT | 0 | 10 | Depends on what level of support is required during UAT
| Total Hours | 12 | 32
| Total Cost @ £126/hour (T&M) | 1512 | 4032