## SOW Cost
Rates (£) |  |  | Points |  | Sprint Team | [5 empty] | Key
Currency | £ |  | Estimated Feature Points |  | Role | # People | Allocation | FTE | Split | Target | Enter value
Sprint 0 Rate per Hour (T&M) | 155 |  | Unanticipated Scope |  | Dev Senior | 1 | 100% | 1 | 58.82% |  | Default value across projects
Project Rate per Hour | 102.375 | 105% | Unanticipated Complexity |  | Dev Junior | 1 | 0% | 0 |  |  | Calculated (formula)
Weeks per Sprint | 3 |  | Total Points | 0 | QA | 1 | 30% | 0.3 | 17.65%
[5 empty] | Jacob | 1 | 0% | 0 | 17.65% |  | People involved in Estimate
UAT & Production Support |  |  | Build - Sprints |  | BA | 1 | 20% | 0.2 |  |  | Sam Duncan
UAT Weeks | 1 |  | Optimistic Sprint # | 2 | Architect | 1 | 10% | 0.1 |  |  | Shaun Barrett
Prod Support Weeks | 2 |  | Pessimistic Sprint # | 2 | PM | 1 | 10% | 0.1 | 5.882% |  | Jacob
Team Size (FTEs) - UAT | 0.5 |  | Team Size (FTEs) | 1.7 | Team Size |  |  | 1.7 | 100% | 0%
Cost per Week (£) | 2047.5 |  | Cost per Sprint (£) | 20890
Velocity
Notes |  |  |  |  | Range | Points per Dev per 3-week Sprint |  |  | Points per Sprint
[5 empty] | Optimistic | 1 Senior Dev FTE |  | 20 | 20
[6 empty] | 1 Junior Dev FTE |  | 17
[5 empty] | Pessimistic | % of Optimistic |  | 80% | 16
Internal
Project Phase | Min Effort | Max Effort | Lower Bound (£) | Upper Bound (£) | Sprint 0 |  |  |  | Consultancy (Min)
Consultancy (Hours) | 0 | 0 | 0 | 0 | Weeks (Min) |  | 3
Sprint 0 | 60 | 80 | 9300 | 12400 | BA Allocation (Min) |  | 30%
Build (Sprints) | 2 | 2 | 41780 | 41780 | BA Allocation (Max) |  | 45% | Pax: | Backlog (Hrs) |  | 24 | pax
Final UAT (Weeks) 0,5 FTE | 1 | 1 | 2047.5 | 2047.5 | Client Meetings (hrs/week) |  | 3 | 4 | Client Meetings (Hrs) |  | 5 | 4
Prod Deployment & Support (Weeks) 0,25 FTE | 2 | 2 | 2047.5 | 2047.5 | Internal Meetings (hrs/week) |  | 1 | 3 | Internal Meetings (Hrs) |  | 4 | 3
Update Lettings User Guide (Hours) | 16 | 16 | 2480 | 2480 | Total Hours (Min) |  | 81 |  | Document (Hrs) |  | 24
Total | 12 | 12 | 57655 | 60755 | Total Hours (Max) |  | 99 |  | Total Hours (min) |  | 80
External Quote |  |  |  |  | Timelines
| Duration (Weeks) |  | Lower Bound (£) | Upper Bound (£) | Target Start Date |  |  | 2025-11-01
Consultancy |  |  | 0 | 0 | Estimated End Date
Sprint 0 | 3 | 3 | 9300 | 12400 | Release 1 | Lower Bound |  | Upper Bound
Build | 6 | 6 | 41780 | 41780 | Consultancy / Sprint 0 | 2025-11-21 |  | 2025-11-21
Final UAT | 1 | 1 | 2047.5 | 2047.5 | Xmas Break (days) | 14 |  | 14
Prod Deployment & Support | 2 | 2 | 2047.5 | 2047.5 | Build | 2026-01-16 |  | 2026-01-16
Update Lettings User Guide | 0 | 0 | 2480 | 2480 | UAT/Go Live | 2026-01-23 |  | 2026-01-23
Total | 12 | 12 | 57655 | 60755 | Support | 2026-02-06 |  | 2026-02-06
Xmas | 2 | 2
Months Duration | 3.2308 | 3.2308
Formulas:
FTE = K32+D32*7+[FTE, row above]
FTE = [FTE, row above]+D33*7
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider the extent of discovery already completed, and knowledge of the client's business & Org.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider extent of custom component development, use of 3rd party apps, 3rd party integrations.
Note on B11: Nikki Papenfus: Seems high for support. Should we allow for different FTEs for UAT & support?
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 point story = 5 days to dev, QA, fix bugs & deploy
Note on K15: Nikki Papenfus: TO BE DECIDED SVOT project: Average points delivered by 1 Dev FTE in a 3 week sprint = 16.4 points

## Project Timeline
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Sprint 0
Sprint 1
Sprint 1 UAT
Sprint 2
Sprint 2 UAT
Production Support
Sprint 1 Go Live
Sprint 2 Go Live

## DNU_SOW v1 (hidden)
Key
Enter Value
Do not update (Formula)
Currency | £
Rates & Team |  | Velocity & Duration
Sprint 0 Rate (T&M) | 120 | Estimated Story Points | 110
Project Rate | 97 | Optimistic Velocity | 25
Team Size - Build | 3 | Pesimistic Velocity | 15
Team Size - UAT & Prod Support | 1 | Optimistic Sprint # | 5
Cost Per 3 Week Sprint | 120 | Pesimistic Sprint # | 8
Cost for UAT & Prod (per week) | 3880 | UAT Weeks | 2
|  | Prod Support Weeks | 2
Internal
Project Phase | Lower Bound Effort | Upper Bound Effort | Notes | Lower Bound | Upper Bound
Sprint 0 (hours) | 80 | 100 | 4 weeks | 9600 | 12000
Release 1: 5 to 8 Sprints | 5 | 8 |  | 600 | 960
Final UAT | 2 | 2 |  | 7760 | 7760
Production Deployment & Post Go-Live Support | 2 | 2 |  | 7760 | 7760
User guide creation | 6 | 8 | Done in parallel with sprints | 720 | 960 | `
Total Cost for Release 1 |  |  |  | 26440 | 29440
External
Project Phase | Duration | Lower Bound | Upper Bound
Sprint 0 (hours) |  | 9600 | 12000
Release 1: 5 to 8 Sprints |  | 600 | 960
Final UAT |  | 7760 | 7760
Production Deployment & Post Go-Live Support |  | 7760 | 7760
User guide creation |  | 720 | 960
Total Cost for Release 1 |  | 26440 | 29440
Note on F7: Nikki Papenfus: Need to add a contingency factor - this is a SOW / proposal-level estimate. Add a % for unknown 'must have' requirements, which may vary depending on the extent of discovery already done, knowledge of the client's business & org. Add a % for unanticipated complexity of known features, which may vary depending on extent of custom components, external plug ins, 3rd party integration.
Note on F8: Nikki Papenfus: The veloocity #s should be a formula based on number of developers / dev FTEs
Note on D9: Nikki Papenfus: this should round up to the nearerst 0,5 or 0,25
Note on D11: Nikki Papenfus: this needs to be a formula
Note on E32: Nikki Papenfus: these totals should be a sum of the above in case we change them

## DNU_Team & Velocity v1 (hidden)
Team Composition | Allocation
Architect | 100%
Dev Senior | 100%
Dev Junior | 50%
QA | 25%
BA | 12.5%
PM | 20%
Team Size | 3.075
Velocity | Story Points per Sprint
Optimistic | 25
Pessimistic | 15
Note on B1: Nikki Papenfus: Is this FTE or allocation? If allocation, then the # of resources is mising from the equation
Note on B6: Nikki Papenfus: these inputs need to go on the main page. This will vary based on project complexity / size / etc, e.g. renewals was a 75% BA allocation for the project. Other projects might not be. If this is a formula, then the inputs to the formula should be transparant and editable
Note on B11: Nikki Papenfus: This needs to be a formula based on number of devs. or this need to be the number of points for one dev? Question = do we modify the velocity depending the junior / senior dev mix? Yes - this will be updated per project and taking team into consideration

## Currency (hidden)
Dollar | $
Pound | £
Rand | R