## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2024-07-25
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | UAT | UAT Complete | 2024-08-02 | Scheduled several calls to work with Grainger to assist with the UAT Process Planning to close out by Friday 2 Aug Provided updated estimates for closing out this project on Jul 24 | [JP] Follow up with Dan to confrim his availability for closing out the marketing cloud UAT element of this project UAT Sign-off call to be rescheduled to Friday Aug 02 1 week of Production support (Aug 05 - 09)
2
2 | T&M Support | Time and Material ad hoc support, capped at 30 hours per month | In Progress | Contract End Date | 2024-09-30 | Prioritizing BSS-27 as it is impacting renewals. Continuously working with Jaic to manage the 30 hours allocated for the month We are generally hitting the 30 hour limit before month end, causing us to put various tickets on hold until the following month
3 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2024-12-31 | Set up processes to facilitate refinement, planning and deployments (Inc. hot fixes) for the various BAU features.
4 | Renewals - Consultancy | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | In Progress | Consultancy Complete | 2024-10-15 | Workshops completed: - Renewals #1: Jul 22 - Renewals #2: Jul 24 | [YD] To share the process flows with Open Box for the Asset Management Group - Done Jul 25 [SB] To confirm all users have accepted the meeting invitations - Done Jul 25 Workshops Scheduled: - Property Man & Residential Services #1: Jul 29 - Asset Management #1: Jul 30 - Accounts Receivable - Credit Control #1: Jul 31
5 | Grainger Trust Leasing Journey | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | SOW in Review | Tentative Project Start Date | 2024-08-01 | SOW sent, meeting to discuss scope, costs and approach on Friday Jul 26 | Anish will be able to confirm timings for when this can start. He is on the SOW clarification call on Friday Jul 26. Assess if splitting this project into 2 deliverables makes sense. To be discussed with Anish
6 | Commercial Property Leasing Journey | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | SOW Agreed in Principle | Tentative Project Start Date | 2024-11-01 | SOW sent, project reviewed by Business Optimisation Forum and November start date tentatively agreed. | SOW to be signed
7
8
General
Risks/Issues
| Personnel Notes | Jon on leave from Aug 5 - Aug 16
Note on B73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AP: Include the forecast hours if known. This allows visibility into where we expect to finish as we progress with the T&M time.

## Drop Down Menus (hidden)
Status | MileStone
Awaiting Feedback | Analysis Complete
Analysis | Consultancy Complete
Build | Build Complete
UAT | UAT Complete
Cancelled | Production Support Complete
Completed | Project Complete
Delayed | Contract End Date
Scheduled | Tentative Project Start Date
SOW Signed
SOW Agreed in Principle
SOW in Review