## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2024-08-22
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Production Support | 2024-08-30 | 19 Aug - Deployed to Production 21 Aug - Production backup at 07.30 am of all Lead and Contact records. Batch run took place at 08.00 am which flagged all candidate Lead and contact records to be anonymised in 14 days time | On 4th Sept (14 days after Wednesday 21st August) at 8am BST, all Contacts and Leads that have not opted in will be anonymised. Open Box will take a backup of all Leads and Contacts at 7:30am BST prior to the execution of this process Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.
2 | T&M Support | Time and Material ad hoc support, capped at 30 hours per month | In Progress | Contract End Date | 2024-09-30 | We are a little concerned with the limited traction we making on some of the support items, and the potential negative sentiment business could be experiancing as a result. A number of cards have been in the "Awaiting Feedback (Grainger)" column for a while. Open Box continues to work with Grainger to get them resolved. A number of cards have been sitting in the "To Do" that we have not been able to address (some logged as far back as June) Open Box exceeded the 30 hour time limit before month end for the second month in a row. | Shaun to set up meeting with Jaic to discuss contract renewal options. Will raise the option to handle adhoc requests as well. Shaun to confirm what we need to do with the PO since we have exceeded the 30 hour limit in the past 2 months.
3 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2024-12-31 | Sprint 1 & 2 deployed to Production on 19 Aug. Sprint 3 in progress
4 | Renewals - Consultancy | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | In Progress | Consultancy Complete | 2024-10-15 | Workshops completed: - Renewals #1: 22 Jul - Renewals #2: 24 Jul - Prop Man & Resi Services #1: 29 Jul - Asset Management #1: 30 Jul - Accounts Receivable - Credit Control #1: 31 Jul - Complaints Process #1: 06 Aug - Accounts Receivable - Credit Control # 2: 08 Aug - Renewals Team #3: 16 Aug | Workshops Scheduled: - Demo of MRI Evolution: Complaints Functionality, Work Orders, PVIs (Complaints Process #2): 10 Sep - Lettings: Review Price Book, viewing feedback & high-level lettings process - Finance: Qube - Qube-GREP Integration Set up a discussion with Andy Masson (Customer Lifetime Value)
5 | Grainger Trust KYC | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | SOW in Review | Tentative Project Start Date | 2024-10-01 | Updated SOW delivered on 29 Jul. Yvonne started to collate annual leave and availability of the working group. Open Box is able to begin analysis ahead of the project proposed start date. | Grainger to review the SOW and provide feedback of approval. Jon following up week of 27th with Yvonne and new head of Grainger Trust
6 | Commercial Property Leasing Journey | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | SOW Agreed in Principle | Tentative Project Start Date | 2024-11-01 | No update since last time: "SOW sent, project reviewed by Business Optimisation Forum and November start date tentatively agreed." | SOW to be signed
7
8
| General | John is meeting with Sam on Friday to discuss 'mini projects' for groups of deliverables that could be scoped / approved quicker than larger projects.
Risks/Issues
Personnel Notes
Note on B73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AP: Include the forecast hours if known. This allows visibility into where we expect to finish as we progress with the T&M time.

## Drop Down Menus (hidden)
Status | MileStone
Awaiting Feedback | Analysis Complete
Analysis | Consultancy Complete
Build | Build Complete
UAT | UAT Complete
Production | Production Support
Cancelled | Production Support Complete
Completed | Project Complete
Delayed | Contract End Date
Scheduled | Tentative Project Start Date
SOW Signed
SOW Agreed in Principle
SOW in Review