## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2024-12-19
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | T&M Support | Time and Material ad hoc support, capped at 40 hours per month | In Progress | Contract End Date | 2024-03-31 | All running well. There is a question about whether Saji should be enabled to make simple config changes to Salesforce. If yes, it introduces some complexities to our SDLC to have non-Open Box team members making changes. | Open Box to raise this with Jaic
2 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2024-12-31 | 2025 SOW for 6 months was delivered to Grainger on Dec 18. Backlog discussed at high level with plan for first few sprints for 2025 pencilled in. | Grainger to approve the SOW Grainger to confirm the pushing out by 1 week for release of current sprint. This is to allow UAT to be completed w/c 6th January.
3 | Renewals | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | Delayed | Consultancy Complete | 2024-10-31 | V3.0 of the Proposal was delivered on Dec 16. Delivered Proposal without costs/timeline Dec 19. | Grainger to review and approve / provide feedback
4 | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | On Hold | Tentative Project Start Date | 2025-02-17 | Open Box provided revised scope and costs on 29 Oct | Grainger to review and provide feedback. Jon is meeting with Anish to review User Stories.
6 | Commercial Lead to Lease | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | In Progress | Build Complete | 2025-02-21 | Sprint 0 complete. - Estimates remain the same (3 sprints) Build is starting Monday. Approaching slightly differently and taking on more of a Product Owner role - not going through each user story with business as do not feel it will be an efficient use of all stakeholders time. | Shaun to send availability for weekly 30 minute sessions to keep team informed and updated. Grainger (Jaic) to complete some dev changes once MRI have created the new web services. This is needed before we go to UAT.
7 | Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | In Progress | Build Complete | 2024-12-20 | Completing build this week. UAT kick-off scheduled for Mon 13 Jan 2025. | Current dependencies to close out build: 1. Grainger (Gary's Team) to configure new email addresses with forwarding to Salesforce 2. Grainger to confirm filters on Qube extract
8 | LeadPro Replacement with Form Assembly |  | In Progress | Build Complete | 2024-12-20 | Aiming to complete build this week. UAT kick-off scheduled for Mon 13 Jan 2025 | Awaiting confirmation on whether RightMove emails can be reverted to old format Shaun to send UAT kick-off availability.
9 | T&M Marketing Cloud Investigation |  | In Progress |  | 2024-12-02 | Initial feedback given to Jenny, Irina and Alistair. To be discussed with Andy Mason afternoon of 19th December. | Open Box to summarise findings, suggest next steps and estimated effort.
| General | MyGrainger App Relaunch discussion
Risks/Issues
| Personnel Notes | Note our availability on the "Leave Tab"

## Completed Projects
Completed Projects
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps
| GDPR Anonymisation CC1 | Additional functionality to accommodate 2 scenarios that were not included in the initial release: 1. Contacts / Leads are added to new opps during the “Communication Opt in Window” 2. Converted Leads that never made it to Closed Won Opportunities are not being anonymised | Production | Project Closed | 2024-09-23 | Deployed to Production on 23 Sep | Project Retro on 2 Oct with Grainger and Open Box to review lessons learnt.
| GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.

## Drop Down Menus (hidden)
Status | MileStone
In Progress | Analysis Complete
Awaiting Feedback | Consultancy Complete
Analysis | Build Complete
Build | UAT Complete
UAT | Production Support
Production | Production Support Complete
Cancelled | Project Closed
Completed | Contract End Date
Delayed | Tentative Project Start Date
Scheduled | Project Start Date
SOW Signed | Sprint 0
SOW Agreed in Principle
SOW in Review
On Hold
At Risk