## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2025-03-13
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | T&M Support | Time and Material ad hoc support, capped at 40 hours per month | In Progress | Contract End Date | 2025-03-31 | We are still seeing discrepancies' between UAT & Production. We met with Jaic yesterday to review. | Salesforce Email Address Anonymization - feedback required. Shaun to reach out to Jaic around the renewal Need to align on long term agreement on how "internal" Grainger items can be deployed to UAT without impacting Open Box deployments.
2 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2025-06-30 | RBAC work for most users is almost complete, switching to IT/Support/Integraiton users | Returning to improvement/enhancement items from next sprint.
3 | SVOT & Renewals | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | Build | Build Complete | 2024-10-31 | Sprint 1 UAT ending this week Sprint 2 Demo on Monday 17 Release 1 Prod: 21 April (may need to push out) Release 2 Prod: 04 Aug | Agreed that we should consider moving PROD deployment 1 week later due to Easter holidays (Jon is back on 22nd April after 2 weeks OOO) Discuss 1 week of SIT as a stage gate for UAT and the impact on the project. Omni channel/WhatsApp will only be addressed in Release 2. Jon was going to with Jenny asap
4 | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio | On Hold |  | 2025-03-31 | Grainger is busy consolidating the last of the requirements. Grainger is planning to re-engage with Open Box towards the end of March. | Grainger to reach out to Open Box once in a position to proceed. Grainger being audited on GT next month
6 | Commercial Lead to Lease | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | In Progress | UAT Complete | 2025-03-15 | This project identified some gaps with the UAT process that we feel can be improved upon. Shaun sent Yvonne an email on 03 March detailing our thoughts on this. Production deployment delayed by 1 week at no cost to Grainger. | Open Box planning to carry out the Salesforce production deployment on Saturday 15 March. Jaic will send Open Box the Production Deployment schedule for Saturday. We have a go/no-go meeting on Friday 14 March Phase 2: Need to discuss timing and options with Grianger Smaller items can be addressed as BAU once approved by the BOF. Bigger changes to be considered once users have been using the system for a while. Grainger to manage business expectations in relation to this.
| General | Known Opportunities: - Replace MRI Evolution (system architecture strategy going to plc board in May) - Touchpoint Survey Rebuild - Estimates sent to Jenny. Would be good to understand if we should start planning to do the work as we'll need Marketing Cloud skills to be available. Grainger setting up touch base with Salesforce Marketing Cloud person (Tom), OB to join if possible.
| Risks/Issues | 1. Omni channel/WhatsApp - See notes in SVOT Project above
Personnel Notes

## Completed Projects
Completed Projects
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps
| GDPR Anonymisation CC1 | Additional functionality to accommodate 2 scenarios that were not included in the initial release: 1. Contacts / Leads are added to new opps during the “Communication Opt in Window” 2. Converted Leads that never made it to Closed Won Opportunities are not being anonymised | Production | Project Closed | 2024-09-23 | Deployed to Production on 23 Sep | Project Retro on 2 Oct with Grainger and Open Box to review lessons learnt.
| GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.
7 | Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | Production | Production Support Complete | 2025-02-17 | Project Closed | Project Review on Thu 20 Feb
8 | LeadPro Replacement with Form Assembly |  | Production | Production Support Complete | 2025-02-17 | Project Closed

## Drop Down Menus (hidden)
Status | MileStone
In Progress | Analysis Complete
Awaiting Feedback | Consultancy Complete
Analysis | Build Complete
Build | UAT Complete
UAT | Production Support
Production | Production Support Complete
Cancelled | Project Closed
Completed | Contract End Date
Delayed | Tentative Project Start Date
Scheduled | Project Start Date
SOW Signed | Sprint 0
SOW Agreed in Principle
SOW in Review
On Hold
At Risk