## Instructions (hidden)
Welcome to the PM Review Template for Projects
A few key notes before you start working on this template:
1. The PM Review tab was intended to be a "Living Report" (i.e. shared during calls with the client).
However, you need to keep record of reports as they were at a certain point in time, so Copy the last report you did before making updates.
2. This tab should not be visible to the client (please remove / hide it before sharing).
To hide it, Right Click on the tab and click on Hide. To unhide, Right Click on any tab & click on Unhide.
3. The Dropdown Menus tab is a workings tab (for us to update/manage) to make reporting easier. Please Hide this before sharing (follow instructions in point 2).
4. The PM Review tab has comments with instructions on different data points. Please ensure that comments are deleted before sharing. Cells with comments are marked with a purple flag in the corner.
5. The "Display" column at the end of the report is for filtering purposes. It will only change to "No" when the Status column is set to "Completed". This is not compulsory, but and easy method to filter for discussion items.
Please amend this filtering column as you see fit.
6. The Status column's drop down is controlled by the list on the Drop Down Menus tab, to add/ remove items from the drop down, make the changes on the Drop Down Menus tab

## Program Overview
Program Management Summary – Grainger PLC |  |  | Date |  | 2025-10-30
Status Overview
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps | Utilization | Display
1 | T&M Support | Time and Material ad hoc support, capped at 40 hours per month | In Progress | Contract End Date | 2026-03-31
2 | BAU Enhancements | Jacob will provide support & assistance to deliver items in the Grainger PLC Salesforce backlog, assist with Salesforce issues that may arise in the normal course of business and continue to be involved in various activities as required by Grainger PLC. | In Progress | Contract End Date | 2026-09-30 |  | Meeting 5 Nov to discuss tranparency and prioritization of work items
Opportunities
1 | SIT & UAT Refresh | Refresh SIT & UAT environments from Prod now that there are no major projects in progress. |  |  |  | Costs provided to Grainger | Yvonne is collating an understanding of other systems requirements and costs to then pull together the full understanding of what we need and when we need to do this.
2 | Data Storage - Clean Up Automation | Develop an automated process within Salesforce that will delete relevant records that meet a set specific set of criteria daily, thereby ensuring that there is not a proliferation of excess records stored within the system. |  |  |  | Open Box delivered the SOW on 20 Oct | Awaiting feedback from Scott
3 | Service Cloud Implementation - RRB | Includes: Anti-Social Behaviour Pet Reg & Management Rent Challenge Process |  |  |  | Open Box delivered the SOW on 14 Oct. Mike has been doing some internal work for Grainger. | Open Box to meet with Scott to discuss this, Data Storage, Renetrs Rights Changes to Tenancy Review) & New Let Process & Renters Rights projects.
4 | Incentive Management | Track incentives for units during lease up, including totals for buildings Maintain visibility of used and unused incentives throughout the New Let and Tenancy Review processes Adding incentives to the Single View of Tenancy Allowing multiple 'payment' options for the customer to receive their incentive Automating the deductions on specified months Ensuring that incentives are not paid once a customer has given notice Multiple reports and dashboards to track various KPIs Updating existing user guide to include this new process |  |  |  | Delivered high level costs on 10 Oct | Look to deliver what we can as part of BAU. Will close out this project.
5 | Homelet Integration Enhancements | Improve the user experience within the existing Homelet Integration |  |  |  | Open Box provided costs to Jaic on 18 Sep. | This is with Jon at the moment. Grainger are looking at some of the challenges with homelet to see if these will be resolved with these changes. Homelet may cover some of these costs) Grainger have a meeting with Homelet, we will look to regroup middle of November to get feedback.
6 | Renters Rights (Changes to Tenancy Review) | Final changes required for Tenancy Review process to make it RRB compliant |  |  |  | Indicative cost and timeline sent on 25 July £30 225 - £58 012 | Priority
7 | New Let Process & Renters Rights | Possibly look to combine with "Renters Rights (Change to Tenancy Review) |  |  |  | Sent high level costs to Scott on 8 Aug £99 750 - £141 800 | Priority - Yvonne meeting with Scott on 29 Aug
8 | Lead Optimization | The project aims to improve lead conversion through faster response times, customer self-service capabilities, and automations while leveraging existing licences. This project will focus on the initial part of the lead management process up until the customer’s final viewing. |  |  |  | Delivered draft SOW on 29 Oct | Based on Grainger’s timelines to get everything ready for the June – August busy season, we’d like to get started ASAP. We have capacity on our side to start in November if this works for you
9 | Complaints Management CRM |  |  |  |  | Delivered costs to Janine on 24 Aug
10 | End of Tenancy Phase 2 | Enhancing the existing EoT process to include other task templates for different property types, as well as adding functionality related to deposits, and different levels of work |  |  |  | Open Box will provide high level costs based on the information and documentation already provided | Open Box to provide costs on this
11 | Grainger Trust | New consumer regulation requires Grainger Trust (GT) to evidence that they meet standards regarding Know Your Customer (KYC) and use the information to provide appropriate support and services for vulnerable customers within the GT Portfolio |  |  |  | Grainger is busy consolidating the last of the requirements. Grainger is planning to re-engage with Open Box towards the end of June/July. | Jan to March 2026
12 | Commercial Lead to Lease - Migration | Data migration of existing Commercial Leases into Salesforce (Commercial Tenancies/Opportunities) |  |  |  | Further enhancements being requested through CAB to improve process | Keep on the backlog and drop the priority
13 | Start of Tenancy "Move-In" | Develop the inverse of the EoT process so that Operations teams have a streamlined (and not on excel) way to manage the compliance and works related to a tenant moving into a new home |  |  |  |  | Potential overlap with End of Tenancy Phase 2 2027 fin year
14 | Replace MRI Evolution |  |  |  |  | Agreed to move into "rolling licenses" so no urgency around that. Grainger looking at other options in the meantime | 2027 (Oct 2026)
Renters Rights
General
Risks/Issues
| Personnel Notes | Leave: - December is a heavy leave period for Open Box

## Completed Projects
Completed Projects
Reference | Project | Description | Status | Milestone | Milestone Target Date | Status Overview | Action Items / Next Steps
| GDPR Anonymisation CC1 | Additional functionality to accommodate 2 scenarios that were not included in the initial release: 1. Contacts / Leads are added to new opps during the “Communication Opt in Window” 2. Converted Leads that never made it to Closed Won Opportunities are not being anonymised | Production | Project Closed | 2024-09-23 | Deployed to Production on 23 Sep | Project Retro on 2 Oct with Grainger and Open Box to review lessons learnt.
| GDPR Anonymisation | Develop an automated process within Salesforce that will anonymise the relevant Lead and Contact records, thereby removing the PII data while retaining the records themselves for use in reporting that isn’t reliant on valid PII data (historical trends, volumes, conversion rates etc.) | Production | Project Closed | 2024-08-30 | Open Box is addressing some discrepancies relating to the GDPR Anonymisation process. | Open Box will continue to take a backup of all Leads and Contacts every Wednesday at 7:30am BST prior to the execution of this process for the next 3 months (26 Nov). This time will be logged against the BAU work that Jacob is assisting with.
| Right to Rent | The proposed solution would utilize Salesforce to automatically create tasks for the appropriate users to obtain R2R documents as well as generate requests to residents to provide updated documentation, where necessary. | Production | Production Support Complete | 2025-02-17 | Project Closed | Project Review on Thu 20 Feb
| LeadPro Replacement with Form Assembly |  | Production | Production Support Complete | 2025-02-17 | Project Closed
| Commercial Lead to Lease | The proposed solution would provide a Lead-to-Lease process for commercial leases within Salesforce that would reduce manual data capture, standardize the deposit payment process, and improve reporting and visibility into commercial leasing activity. | Completed | Project Closed | 2025-05-28 | Project Completed. Some project backlog items already being worked on in BAU. Consideraiton for other items to take place in the future to identify complexity and priority of backlog items.
| On the Market Integration | This project will allow Grainger Salesforce to initiate listings and delisting of units on OTM directly from within Salesforce. It will also allow prospective tenant details submitted to OTM to be captured as Leads in Salesforce so that the Lettings team can then follow the existing qualification and conversion process | Production | Production Support | 2025-08-15 | Project closed | None
| SVOT & Tenancy Review | Grainger PLC are looking to design a Salesforce-based future state renewals journey that leverages the single view of the customer to streamline the process, reduce the level of manual effort and create a standardised, simplified and transparent process. | Completed | Project Closed | 2025-09-12 | Project closed Grainger team to start using the functionality "in anger" from 22 Sep. | Lessons Learnt session on Thu 2 Oct. Can this be moved to Wed 8th or Thu 9th at the same time?

## Drop Down Menus (hidden)
Status | MileStone
In Progress | Analysis Complete
Awaiting Feedback | Consultancy Complete
Analysis | Build Complete
Build | UAT Complete
UAT | Production Support
Production | Production Support Complete
Cancelled | Project Closed
Completed | Contract End Date
Delayed | Tentative Project Start Date
Scheduled | Project Start Date
SOW Signed | Sprint 0
SOW Agreed in Principle
SOW in Review
On Hold
At Risk