Project Management Review Summary – Grainger PLC

| Project | Void Process - Consultancy |  |  |  |
| --- | --- | --- | --- | --- |
| Period | Apr 24th – May 2nd |  |  |  |
| Status Overview | In progress |  |  |  |
| Progress in the last week | - Item |  | - Completed | - Responsible |
|  | - Process review meeting |  | - Apr 24th | - Grainger / Open Box |
|  | - Presentation deck & draft process documentation |  | - Apr 24th | - Open Box |
| Upcoming deliverables / feedback required | - Item | - Due | - Responsible | - Status |
|  | - Qube demo | - May 3rd | - Grainger / Open Box | - Scheduled |
|  | - Document Management review | - May 4th | - Grainger / Open Box | - Scheduled |
|  | - Salesforce demo | - May 10th | - Grainger / Open Box | - Scheduled |
| Discussions/Risks /Issues | Approval of additional time. Currently 40 hours is approved. Will you be able to share a recording (Zoom) of the demo’s with Open Box |  |  |  |
| Utilization | 30 of 110 hours (27%) |  |  |  |
| Personnel Notes | None. |  |  |  |

Historical Reports