## Pivot
Period | 2025-01-01 |  |  | Forecast
|  |  |  | Month | Rate | Hours | Cost
Billable Timecode | Billable timecode |  |  | 2024-10-01 | £120,00 | 40 | £4 800,00
|  |  |  | 2024-11-01 | £120,00 | 40 | £4 800,00
Sum of Hours | Column Labels |  |  | 2024-12-01 | £120,00 | 40 | £4 800,00
Row Labels | General Support (Billable) | Grand Total |  | 2025-01-01 | £126,00 | 40 | £5 040,00
Anjali Salecha | 5.25 | 5.25 |  | 2025-02-01 | £126,00 | 40 | £5 040,00
Khonani Davhana | 1.25 | 1.25 |  | 2025-03-01 | £126,00 | 40 | £5 040,00
Grand Total | 6.5 | 6.5
Jira Ticket | Status | Assigned To | Jira Epic
BSS-76 Disable publishing units to live Rightmove environment when a sandbox is refreshed or newly created | To Do | Jaic George
BSS-69 Add fault path to "An Error Occurred with Your "EoT- Check Out (Task Subflow)" Flow " | To Do | Unassigned | BSS-13 Flow error message improvement
BSS-70 Add fault path to "UpdateOffers" Flow | To Do | Unassigned | BSS-13 Flow error message improvement
BSS-71 Add fault path to "RTF_Account_UpdateRTRFields_OBS" flow | To Do | Unassigned | BSS-13 Flow error message improvement
BSS-68 Add fault path to "EoT - Reopen Amend Direct Debit" Flow | In Progress | Unassigned | BSS-13 Flow error message improvement
BSS-77 Closed Won opportunities with Anonymised Accounts | Awaiting Feedback (Grainger) | Jaic George
BSS-65 Add fault path to "EoT - Clean Unit (Task Subflow)" Flow | In Review (Open Box) | Khonani Davhana | BSS-13 Flow error message improvement
BSS-66 Add fault path to "EoT- Deposit Release (Task Subflow)" Flow | Client Confirmation (Grainger) | Saji Gunasekaran | BSS-13 Flow error message improvement
BSS-78 Make Homelet API request timeout Configurable | Client Confirmation (Grainger) | Jaic George
BSS-67 Add fault path to "EoT- PVI (Task Subflow)" Flow | Done | Anjali Salecha | BSS-13 Flow error message improvement
BSS-79 Peer Review of the validation changes | Done | Jacob Smycz
[6 empty] | To Do |  | Khonani Davhana
[6 empty] | In Progress |  | Jaic George
[6 empty] | Awaiting Feedback (Grainger) |  | Anjali Salecha
[6 empty] | In Review (Open Box) |  | Jacob Smycz
[6 empty] | Client Confirmation (Grainger) |  | Saji Gunasekaran
UAT Approved
Done

## Current Month
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status
2025-01-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340063 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP |  | QA environment setup for End of Tenancy process to support testing of BSS-66. Deployment of BSS-66 to uat. | Not submitted
2025-01-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340065 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | Daily standup | Not submitted
2025-01-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340073 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  | GDPR data backup. | Not submitted
2025-01-10 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340734 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 |  |  |  | GBP |  | Worked on BSS-65, BSS-67 and BSS-68. Testing and deployment to QA. Daily standup. | Not submitted
2025-01-13 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 341267 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | Daily standup | Not submitted
2025-01-07 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 339740 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted
2025-01-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 340475 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted
2025-01-10 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 341266 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted

## All Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status
2025-01-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340063 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP |  | QA environment setup for End of Tenancy process to support testing of BSS-66. Deployment of BSS-66 to uat. | Not submitted
2025-01-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340065 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | Daily standup | Not submitted
2025-01-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340073 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  | GDPR data backup. | Not submitted
2025-01-10 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 340734 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 |  |  |  | GBP |  | Worked on BSS-65, BSS-67 and BSS-68. Testing and deployment to QA. Daily standup. | Not submitted
2025-01-13 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Support | 341267 | General Support (Non-Billable) | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP |  | Daily standup | Not submitted
2025-01-07 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 339740 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted
2025-01-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 340475 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted
2025-01-10 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000493 | Salesforce Support (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Support | 341266 | General Support (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted