## Pivot
Month | (All) | <- Filter By Month
Sum of Hours | Column Labels | SOW Estimates
Row Labels | Delivery | Phase | Hours |  | Lower Bound | Upper Bound
Grainger PLC | 338.5 | Analysis | 40 | 52 | 4800 | 6240
Website Integration (T&M) | 338.5 | Build | 180 | 234 | 21600 | 28080
Analysis & Build | 338.5 | Project Management | 12 | 15.6 | 1440 | 1872
Anjali Salecha | 89 | UAT | 20 | 26 | 2400 | 3120
Nikki Papenfus | 51.5 | Production | 5 | 6.5 | 600 | 780
Sam Duncan | 10.25 | Total | 257 | 334.1 | 30840 | 40092
Shaun Barrett | 3.25
Khonani Davhana | 31
Matthew Cornfield | 64
Sachin Deshmukh | 89.5
Grand Total | 338.5

## Project Timesheets(1)
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-02-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 214229 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 | 480 | 120 | IN07860 | GBP | Reviewed | Worked on editing json file swagger editor. Discussion with Sam about SwaggerHub mock api calling setup. Time to be logged to Grainger website integration work for publishing units. | Not submitted | 2 | February
2024-03-01 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 220320 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 |  |  |  | GBP |  | Discussion with Sam and Matt about mock server setup and integration approach. Testing in UAT callout request not working. Anaylised existing code. | Not submitted | 3 | March
2024-03-04 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 220321 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Worked on completing the story SAWI-2. Acs and IA. Daily standup. Discussion with Sam Matt Sachin. Created sandbox users. | Not submitted | 3 | March
2024-03-05 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 220322 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 |  |  |  | GBP |  | worked on SAWI-1. Daily standup. | Not submitted | 3 | March
2024-03-06 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221405 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Discusttion with Sam Sachin and Matt. Daily standup. Worked on SAWI-1 | Not submitted | 3 | March
2024-03-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221411 | Delivery | Billable timecode | Standard Timecode | 90 | 13 | 13:00 | 1170 |  |  |  | GBP |  | Daily standup. Worked on SAWI-1 --> entry from Feb 27th for 5 hours- Disussion with Sam. Reading stories for project SAWI. Story sizing session with Sam and Mattew. | Not submitted | 3 | March
2024-03-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221929 | Delivery | Billable timecode | Standard Timecode | 90 | 14 | 14:00 | 1260 |  |  |  | GBP |  | Daily standup. Worked on SAWI-1. Review with Sachin. Deployment and Show me with Khonani and Matthew Cornfield. Entry from Feb 28 for 8 hours-->Analysed existing code for unit publish and update. Error handling details. | Not submitted | 3 | March
2024-03-11 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 222793 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Daily standup. Worked on SAWI-7 and SAWI-11. | Not submitted | 3 | March
2024-03-12 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 222792 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Daily standup. Story review with Sachin for SAWI-7 and SAWI-11. Deployment to staging environment. Testing. Show me with Khonani. | Not submitted | 3 | March
2024-03-13 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223768 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  | Daily standup. Worked on SAWI-8 amd SAWI-10. Discussion with Matthew. Show me with Khonani for SAWI-8 amd SAWI-10. Deployment and testing. | Not submitted | 3 | March
2024-03-14 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 224764 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 |  |  |  | GBP |  | Daily standup. Discussion with Sam. Worked on SAWI-15 & SAWI-26. Discussion with Sachin about SAWI-20 | Not submitted | 3 | March
2024-03-04 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 219767 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-05 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 219760 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-06 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221432 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-07 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221439 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221695 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-11 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222865 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-12 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222864 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-13 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223766 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-14 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 224990 | Delivery | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-15 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225010 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-01 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 220269 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-04 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 220268 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-05 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 219901 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-06 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 220688 | Delivery | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-07 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221312 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-08 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221647 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-11 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222364 | Delivery | Billable timecode | Standard Timecode | 90 | 7.75 | 7:45 | 697.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-12 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222988 | Delivery | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-13 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223541 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-14 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223989 | Delivery | Billable timecode | Standard Timecode | 90 | 6.75 | 6:45 | 607.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-15 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 224504 | Delivery | Billable timecode | Standard Timecode | 90 | 6.25 | 6:15 | 562.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-02-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 209126 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 212410 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 840 | 210 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-16 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 212409 | Delivery | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 | 300 | 75 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 214277 | Delivery | Billable timecode | Standard Timecode | 90 | 7.25 | 7:15 | 652.5 | 870 | 217.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-21 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 214280 | Delivery | Billable timecode | Standard Timecode | 90 | 4.25 | 4:15 | 382.5 | 510 | 127.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-22 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 214563 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-26 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 216146 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 240 | 60 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 217055 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-28 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 217696 | Delivery | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 | 390 | 97.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-29 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 217701 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-03-01 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 219384 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 219370 | Delivery | Billable timecode | Standard Timecode | 90 | 5.25 | 5:15 | 472.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 219880 | Delivery | Billable timecode | Standard Timecode | 90 | 4.75 | 4:45 | 427.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 220833 | Delivery | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-07 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 221107 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 221735 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 222478 | Delivery | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 223124 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 223117 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 224079 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP |  |  | Not submitted | 3 | March
2024-03-04 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221465 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP |  | #NAME? | Not submitted | 3 | March
2024-03-05 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221467 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Code walkthrough of existing Integration -- Implementation approach finalized with Sam Duncan -- Worked on SAWI 1 | Not submitted | 3 | March
2024-03-06 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221468 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Worked on SAWI 1 | Not submitted | 3 | March
2024-03-07 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221469 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Worked on SAWI 1 and related Test classes and LWC component | Not submitted | 3 | March
2024-03-08 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221473 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Worked on SAWI 7 | Not submitted | 3 | March
2024-03-11 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223686 | Delivery | Billable timecode | Standard Timecode | 90 | 9.5 | 9:30 | 855 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Worked on SAWI 11 | Not submitted | 3 | March
2024-03-12 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223687 | Delivery | Billable timecode | Standard Timecode | 90 | 9 | 9:00 | 810 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Worked on SAWI 11 -- Completed code review show me and deployed SAWI 7 and 11 to Staging | Not submitted | 3 | March
2024-03-13 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223688 | Delivery | Billable timecode | Standard Timecode | 90 | 9 | 9:00 | 810 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Worked on SAWI 810 -- Completed code review show me and deployed SAWI 8 and 10 to Staging | Not submitted | 3 | March
2024-03-14 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223685 | Delivery | Billable timecode | Standard Timecode | 90 | 11 | 11:00 | 990 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Working on SAWI 20 | Not submitted | 3 | March
2024-03-15 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 224214 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP |  | -- Grainger Website Integration Standup -- Working on SAWI 20 | Not submitted | 3 | March
2024-02-02 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 215409 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed | Requirements gathering with Code+ Grainger | Not submitted | 2 | February
2024-02-15 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 215527 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed | Refinement with Nikki | Not submitted | 2 | February
2024-02-20 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 215530 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed | Refinement session with Grainger | Not submitted | 2 | February
2024-03-04 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222207 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP |  | Refinement session (2 hours) Daily standup (15 mins) | Not submitted | 3 | March
2024-03-05 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222221 | Delivery | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP |  | Refinement session (1 hour) Daily standup (15 mins) | Not submitted | 3 | March
2024-03-06 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222223 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  | Daily standup (15 mins) Working session with Anjali and Matt C (45 mins) | Not submitted | 3 | March
2024-03-07 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222224 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  | Daily standup (15 mins) | Not submitted | 3 | March
2024-03-08 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222225 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP |  | Daily standup (15 mins) Environment management call (30 mins) | Not submitted | 3 | March
2024-03-11 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223052 | Delivery | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP |  | Refinement session (1 hour) Daily standup (15 mins) | Not submitted | 3 | March
2024-03-12 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223062 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP |  | Daily standup (15 mins) Deployment session with Matt C (30 mins) | Not submitted | 3 | March
2024-02-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 211400 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-26 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 216824 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 217543 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-03-06 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 220641 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-07 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221392 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221855 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222786 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223231 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223427 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March