## Pivot
Month | (All) |  |  | <- Filter By Month
Sum of Hours | Column Labels |  |  | SOW Estimates
Row Labels | Delivery | Delivery - UAT | Grand Total | Phase | Hours |  | Lower Bound | Upper Bound
Grainger PLC | 358.5 | 14 | 372.5 | Analysis | 40 | 52 | 4800 | 6240
Website Integration (T&M) | 358.5 | 14 | 372.5 | Build | 180 | 234 | 21600 | 28080
Analysis & Build | 358.5 | 14 | 372.5 | Project Management | 12 | 15.6 | 1440 | 1872
Anjali Salecha | 115.5 | 5 | 120.5 | UAT | 20 | 26 | 2400 | 3120
Nikki Papenfus | 62.5 | 4 | 66.5 | Production | 5 | 6.5 | 600 | 780
Sam Duncan | 13.25 |  | 13.25 | Total | 257 | 334.1 | 30840 | 40092
Shaun Barrett | 5.25 | 1.25 | 6.5
Khonani Davhana | 48.75 | 1.75 | 50.5
Sachin Deshmukh | 112.5 | 2 | 114.5 | SOW |  |  |  | Actuals/Forecast | Notes
Matthew Cornfield | 0.75 |  | 0.75 | Phase | Hours | Lower Bound | Upper Bound | Hours | As at 18 March
Grand Total | 358.5 | 14 | 372.5 | Analysis | 40 - 52 | £4,800.00 | £6,240.00 | 53.25
|  |  |  | Build | 180 - 234 | £21,600.00 | £28,080.00 | 248.25 | + 12 hours Sachine has not logged - Matts time
|  |  |  | Project Management | 12 - 15.6 | £1,440.00 | £1,872.00 | 3.75
|  |  |  | UAT | 20 - 26 | £2,400.00 | £3,120.00 | 26 | Estimate
|  |  |  | Production | 5 - 6.5 | £600.00 | £780.00 | 6 | Estimate
|  |  |  | Total | 257 - 334 | £30,840.00 | £40,092.00 | 337.25
[7 empty] | Estimated remaining effort | 48 | 2 days for 3 people
[7 empty] | Reforecasted Total | 385.25
[7 empty] | Reforecasted Cost | £46,230.00
[7 empty] | Delta from upper bound | £6,138.00
[7 empty] | % | 115%
Target Hours - 353 at 22 March
Remaining hours -> 32 (UAT & Prod)

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-02-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 214229 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 | 480 | 120 | IN07860 | GBP | Reviewed | Worked on editing json file swagger editor. Discussion with Sam about SwaggerHub mock api calling setup. Time to be logged to Grainger website integration work for publishing units. | Not submitted | 2 | February
2024-03-01 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 220320 | Delivery | Billable timecode | Standard Timecode | 90 | 4 | 4:00 | 360 | 480 | 120 | IN07958 | GBP | Reviewed | Discussion with Sam and Matt about mock server setup and integration approach. Testing in UAT callout request not working. Anaylised existing code. | Not submitted | 3 | March
2024-03-04 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 220321 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN07958 | GBP | Reviewed | Worked on completing the story SAWI-2. Acs and IA. Daily standup. Discussion with Sam Matt Sachin. Created sandbox users. | Not submitted | 3 | March
2024-03-05 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 220322 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 840 | 210 | IN07958 | GBP | Reviewed | worked on SAWI-1. Daily standup. | Not submitted | 3 | March
2024-03-06 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221405 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN07958 | GBP | Reviewed | Discusttion with Sam Sachin and Matt. Daily standup. Worked on SAWI-1 | Not submitted | 3 | March
2024-03-07 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221411 | Delivery | Billable timecode | Standard Timecode | 90 | 13 | 13:00 | 1170 | 1560 | 390 | IN07958 | GBP | Reviewed | Daily standup. Worked on SAWI-1 --> entry from Feb 27th for 5 hours- Disussion with Sam. Reading stories for project SAWI. Story sizing session with Sam and Mattew. | Not submitted | 3 | March
2024-03-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221929 | Delivery | Billable timecode | Standard Timecode | 90 | 14 | 14:00 | 1260 | 1680 | 420 | IN07958 | GBP | Reviewed | Daily standup. Worked on SAWI-1. Review with Sachin. Deployment and Show me with Khonani and Matthew Cornfield. Entry from Feb 28 for 8 hours-->Analysed existing code for unit publish and update. Error handling details. | Not submitted | 3 | March
2024-03-11 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 222793 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN07958 | GBP | Reviewed | Daily standup. Worked on SAWI-7 and SAWI-11. | Not submitted | 3 | March
2024-03-12 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 222792 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN07958 | GBP | Reviewed | Daily standup. Story review with Sachin for SAWI-7 and SAWI-11. Deployment to staging environment. Testing. Show me with Khonani. | Not submitted | 3 | March
2024-03-13 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223768 | Delivery | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 | 960 | 240 | IN07958 | GBP | Reviewed | Daily standup. Worked on SAWI-8 amd SAWI-10. Discussion with Matthew. Show me with Khonani for SAWI-8 amd SAWI-10. Deployment and testing. | Not submitted | 3 | March
2024-03-14 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 224764 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 840 | 210 | IN07958 | GBP | Reviewed | Daily standup. Discussion with Sam. Worked on SAWI-15 & SAWI-26. Discussion with Sachin about SAWI-20 | Not submitted | 3 | March
2024-03-18 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 225278 | Delivery | Billable timecode | Standard Timecode | 90 | 10 | 10:00 | 900 | 1200 | 300 | IN07958 | GBP | Reviewed | Daily stand up. Discussion with Sachin. Worked on SAWI-11 15 2630. Deployment to staging. Testing and Show me with khonani. Code x Open Box API Feed demo. Touch Base. | Not submitted | 3 | March
2024-03-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 225791 | Delivery | Billable timecode | Standard Timecode | 90 | 9 | 9:00 | 810 | 1080 | 270 | IN07958 | GBP | Reviewed | Daily standup. Worked on SAWI-2 and SAWI-36. Deployment. Testing. Show me with khonani. Discussion with Sam. Discussion on SAWI-33 with Matt. Discussion Story SAWI-2 and 36 review with SAchin. | Not submitted | 3 | March
2024-03-20 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 226260 | Delivery | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 600 | 150 | IN07958 | GBP | Reviewed | Daily standup. Worked on SAWI-52. Deployment and testing. Discussion with Khonani. Discussion with Matt about SAWI-33. | Not submitted | 3 | March
2024-03-26 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 229200 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN07958 | GBP | Reviewed | Deployment of SAWI-57 to staging testing. Deployment to uat. Daily standup | Not submitted | 3 | March
2024-03-27 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 229333 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 240 | 60 | IN07958 | GBP | Reviewed | deployment to uat related to reverting profile permissions in uat from staging env | Not submitted | 3 | March
2024-04-11 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 233886 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP |  | Worked on SAWI-66 and SAWI-67 testing and deployment to staging. | Not submitted | 4 | April
2024-04-12 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 234390 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP |  | 1. deployment to uat and discussion and confirmation of date field format with khonani. | Not submitted | 4 | April
2024-03-04 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 219767 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-05 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 219760 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-06 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221432 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-07 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221439 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221695 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-11 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222865 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-12 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222864 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 | 720 | 180 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-13 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223766 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 | 720 | 180 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-14 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 224990 | Delivery | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 | 690 | 172.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-15 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225010 | Delivery | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 | 360 | 90 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-18 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225329 | Delivery | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 | 600 | 150 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-19 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225809 | Delivery | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 | 720 | 180 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-20 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 226736 | Delivery | Billable timecode | Standard Timecode | 90 | 6.75 | 6:45 | 607.5 | 810 | 202.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-25 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 228118 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed | Daily standup | Not submitted | 3 | March
2024-03-26 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 228090 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN07958 | GBP | Reviewed | Standup & QA (59 57 &60) | Not submitted | 3 | March
2024-04-12 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 235014 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-03 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 230733 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed | SAWI-63 - UAT Feedback - Added additional user permissions in UAT (Grainger revoked OB sys admin permissions) | Not submitted | 4 | April
2024-02-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 209126 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 212410 | Delivery | Billable timecode | Standard Timecode | 90 | 7 | 7:00 | 630 | 840 | 210 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-16 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 212409 | Delivery | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 | 300 | 75 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 214277 | Delivery | Billable timecode | Standard Timecode | 90 | 7.25 | 7:15 | 652.5 | 870 | 217.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-21 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 214280 | Delivery | Billable timecode | Standard Timecode | 90 | 4.25 | 4:15 | 382.5 | 510 | 127.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-22 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 214563 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-26 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 216146 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 240 | 60 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 217055 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-28 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 217696 | Delivery | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 | 390 | 97.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-29 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 217701 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-03-01 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 219384 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 | 270 | 67.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 219370 | Delivery | Billable timecode | Standard Timecode | 90 | 5.25 | 5:15 | 472.5 | 630 | 157.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 219880 | Delivery | Billable timecode | Standard Timecode | 90 | 4.75 | 4:45 | 427.5 | 570 | 142.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 220833 | Delivery | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 | 330 | 82.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-07 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 221107 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 221735 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 222478 | Delivery | Billable timecode | Standard Timecode | 90 | 2.75 | 2:45 | 247.5 | 330 | 82.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 223124 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 223117 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 224079 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 | 270 | 67.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-18 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 225270 | Delivery | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 210 | 52.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-19 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 225840 | Delivery | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 | 150 | 37.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-20 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 225836 | Delivery | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 210 | 52.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-22 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 226473 | Delivery | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 180 | 45 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-25 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 227596 | Delivery | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 | 270 | 67.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-26 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 227592 | Delivery | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 180 | 45 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 228791 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-04-08 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 233907 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 233908 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 233909 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 233906 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-04-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Analysis & Build | 234505 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 4 | April
2024-03-04 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221465 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 | 1020 | 255 | IN07958 | GBP | Reviewed | #NAME? | Not submitted | 3 | March
2024-03-05 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221467 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 | 1020 | 255 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Code walkthrough of existing Integration -- Implementation approach finalized with Sam Duncan -- Worked on SAWI 1 | Not submitted | 3 | March
2024-03-06 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221468 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 | 1020 | 255 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Worked on SAWI 1 | Not submitted | 3 | March
2024-03-07 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221469 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 | 1020 | 255 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Worked on SAWI 1 and related Test classes and LWC component | Not submitted | 3 | March
2024-03-08 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 221473 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 | 1020 | 255 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Worked on SAWI 7 | Not submitted | 3 | March
2024-03-11 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223686 | Delivery | Billable timecode | Standard Timecode | 90 | 9.5 | 9:30 | 855 | 1140 | 285 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Worked on SAWI 11 | Not submitted | 3 | March
2024-03-12 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223687 | Delivery | Billable timecode | Standard Timecode | 90 | 9 | 9:00 | 810 | 1080 | 270 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Worked on SAWI 11 -- Completed code review show me and deployed SAWI 7 and 11 to Staging | Not submitted | 3 | March
2024-03-13 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223688 | Delivery | Billable timecode | Standard Timecode | 90 | 9 | 9:00 | 810 | 1080 | 270 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Worked on SAWI 810 -- Completed code review show me and deployed SAWI 8 and 10 to Staging | Not submitted | 3 | March
2024-03-14 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 223685 | Delivery | Billable timecode | Standard Timecode | 90 | 11 | 11:00 | 990 | 1320 | 330 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Working on SAWI 20 | Not submitted | 3 | March
2024-03-15 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 224214 | Delivery | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 | 1020 | 255 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Working on SAWI 20 | Not submitted | 3 | March
2024-03-18 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 225674 | Delivery | Billable timecode | Standard Timecode | 90 | 12 | 12:00 | 1080 | 1440 | 360 | IN07958 | GBP | Reviewed | -- Grainger Website Integration Standup -- Working on SAWI 20 6 | Not submitted | 3 | March
2024-03-19 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 225675 | Delivery | Billable timecode | Standard Timecode | 90 | 11 | 11:00 | 990 | 1320 | 330 | IN07958 | GBP | Reviewed | #NAME? | Not submitted | 3 | March
2024-03-26 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Analysis & Build | 229435 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 240 | 60 | IN07958 | GBP | Reviewed | Worked on SAWI-59 and deployed to Staging and UAT | Not submitted | 3 | March
2024-02-02 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 215409 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed | Requirements gathering with Code+ Grainger | Not submitted | 2 | February
2024-02-15 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 215527 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed | Refinement with Nikki | Not submitted | 2 | February
2024-02-20 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 215530 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07860 | GBP | Reviewed | Refinement session with Grainger | Not submitted | 2 | February
2024-03-04 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222207 | Delivery | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 | 240 | 60 | IN07958 | GBP | Reviewed | Refinement session (2 hours) Daily standup (15 mins) | Not submitted | 3 | March
2024-03-05 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222221 | Delivery | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 | 150 | 37.5 | IN07958 | GBP | Reviewed | Refinement session (1 hour) Daily standup (15 mins) | Not submitted | 3 | March
2024-03-06 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222223 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07958 | GBP | Reviewed | Daily standup (15 mins) Working session with Anjali and Matt C (45 mins) | Not submitted | 3 | March
2024-03-07 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222224 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 3 | March
2024-03-08 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222225 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) Environment management call (30 mins) | Not submitted | 3 | March
2024-03-11 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223052 | Delivery | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 | 150 | 37.5 | IN07958 | GBP | Reviewed | Refinement session (1 hour) Daily standup (15 mins) | Not submitted | 3 | March
2024-03-12 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223062 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) Deployment session with Matt C (30 mins) | Not submitted | 3 | March
2024-03-13 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225179 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 3 | March
2024-03-14 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225180 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 3 | March
2024-03-15 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225181 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 3 | March
2024-03-18 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225185 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) Code API demo (30 mins) | Not submitted | 3 | March
2024-03-19 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 226119 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 3 | March
2024-03-20 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 227443 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 3 | March
2024-03-22 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 227449 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07958 | GBP | Reviewed | Demo to Grainger & Code | Not submitted | 3 | March
2024-02-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 211400 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-26 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 216824 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-02-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 217543 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07860 | GBP | Reviewed |  | Not submitted | 2 | February
2024-03-06 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 220641 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-07 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221392 | Delivery | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 | 90 | 22.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 221855 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 222786 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223231 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-13 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 223427 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 225250 | Delivery | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 | 60 | 15 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 226039 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-20 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 226371 | Delivery | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-22 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 227407 | Delivery | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07958 | GBP | Reviewed |  | Not submitted | 3 | March
2024-04-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 231548 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 231549 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 233822 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000532 | Website Integration (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Analysis & Build | 234264 | Delivery - UAT | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  |  | Not submitted | 4 | April