## Pivot
Month | (All) |  | <- Filter By Month
Sum of Hours | Column Labels |  |  |  | Phase | Hours | Lower Bound | Upper Bound
Row Labels | Delivery (Billable) | Delivery (non-billable) @ $0.00 | EoT Deployment to UAT | Grand Total | Analysis | 60 - 78 | £7,200 | £9,360
Nikki Papenfus | 42 | 0.25 |  | 42.25 | Build | 200 - 260 | £24,000 | £31,200
Sam Duncan | 10.25 |  |  | 10.25 | Project Management | 12 - 15.6 | £1,440 | £1,872
Shaun Barrett | 12.75 | 2 |  | 14.75 | UAT | 40 - 52 | £4,800 | £6,240
Anjali Salecha | 134.25 | 15.5 | 0.5 | 150.25 | Production | 5 - 6.5 | £600 | £780
Khonani Davhana | 19.5 | 5.5 | 1.5 | 26.5 | Total | 317 - 412 | £38,040 | £49,452
Tafadzwa Toro | 30 | 27.75 |  | 57.75
Carami Le Grange |  | 8.5 |  | 8.5
Dillan Landsberg | 37 | 20.75 |  | 57.75
Matthew Cornfield |  | 12.25 |  | 12.25
Matthew Pitcairn |  | 3.5 |  | 3.5
Sachin Deshmukh |  |  | 19.5 | 19.5
Grand Total | 285.75 | 96 | 21.5 | 403.25
Just keeping track of Non-Billable
Billable Total | 307.25

## Project Timesheets
Date | Person | Agreement Type | Person Organisation | Person Team | Person Location | Company Name | Project Number | Project Name | Project Type | Project Organisation | Project Manager | Account Manager | Line Manager | Budget Name | Time Entry ID | Timecode Name | Billable Timecode | Timecode Type | Timecode Rate | Hours | Time | Worked Amount | Invoiced Amount | Invoiced Delta | Invoice # | Currency | Reviewed Status | Comment | Timesheet Status | Period | Month
2024-03-27 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 229578 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 4 | 4:00 | 0 |  |  |  | GBP | Reviewed | Axis project stanup. Reading sow doc for axis project discussion with SAm khonani Toro and Dillan about Axis project. Checked Tenancy__c field dependancy on eot for axis project | Not submitted | 3 | March
2024-03-28 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 229577 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 6 | 6:00 | 0 |  |  |  | GBP | Reviewed | Daily standup. Meeting with client - Grainger: Axis Void Management Refinement. Discussion with Sam - Axis void managemet work. Worked on trigger to capture Axis_Modstamp__c field | Not submitted | 3 | March
2024-04-01 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 230625 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | Daily standup with Nikki. Workedon RMAXIS-196 Calculate when 'Axis Fields Last Modified' so that we can inform Axis of changes to relevant EOT details. worked on RMAXIS-196 in devxas deployed to devxob and tested. Prepared questions to discuss with Sam and Nikki | Not submitted | 4 | April
2024-04-02 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 230627 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | Worked on RMAXIS-185 in devxob. Daily standup. Meeting with client - Grainger: Axis Void Management Refinement. Understanding and analysis of requirements for RMAXIS-180 | Not submitted | 4 | April
2024-04-03 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 231180 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | Daily standup. Worked on RMAXIS-181 RMAXIS-180. Test class for RMAXIS-196. | Not submitted | 4 | April
2024-04-04 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 231179 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | Daily standup. Discussion with Sam about new sandbox setup. Questions on stories. Worked on RMAXIS-180. Testing. Worked on moving stories from devxob sadnbox to new dev sandbox called grainger.dev. Refinement session. | Not submitted | 4 | April
2024-04-05 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232187 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP | Reviewed | Daily standup. Worked on AVM-18. Could not complete AVM-18 due to other dependant stories. Worked on AVM-6. Researched about using time fields in flow. | Not submitted | 4 | April
2024-04-08 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232810 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 |  |  |  | GBP | Reviewed | Daily standup. Discussion with Sam and Nikki about AVM-5. Worked on Time field value defaulting for AVM-5 did not work. Another discussion with SAm. Tested QA sandbox setup. Worked on new approach for AVM-5 | Not submitted | 4 | April
2024-04-09 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232813 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | Daily standup. Worked on AVM-5. Dev review meeting with Sam - Axis Void Management - Dev Review. Meeting with client - Grainger: Axis Void Management Refinement. Show me with Khonani - Grainger show-me. QA environment deployment for AVM-4 10 & 11. Testing. | Not submitted | 4 | April
2024-04-10 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233885 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | Daily standup. Worked on AVM-5610 & 11. Testing and deployment to qa environment. Show me with Dillan. | Not submitted | 4 | April
2024-04-11 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233887 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP | Reviewed | 1. discussion with toro dev review of AVM-1 with Toro 2. Dev review with Sam for AVM-18 and AVM-7 3. Daily standup 4. Meeting with Shaun and Sam - Grainger deployment estimates 5. Worked on AVM-7 18 | Not submitted | 4 | April
2024-04-12 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 234398 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 6.25 | 6:15 | 562.5 |  |  |  | GBP | Reviewed | 1. discussion with toro about unit layout related to AVM-1 2. daily standup 3. Partial deployment of AVM-7 and AVM-5 and manual steps note 4. Worked on AVM-20 5. Discussion with Matt C and Khonani - Grainger Website Permissions in UAT | Not submitted | 4 | April
2024-04-15 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 235368 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 7.5 | 7:30 | 675 |  |  |  | GBP | Reviewed | 1. Dev review of AVM-8 with Toro 2. Implementation approach discussion AVM-21 with Toro 3. Worked on AVM-7 & 18. Deployment and testing 4. Show me with Dillan about AVM-7 & 18 5. Daily standup | Not submitted | 4 | April
2024-04-15 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 235602 | EoT Deployment to UAT | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed | Deployment of EoT from prod to uat - discussion with Sachin | Not submitted | 4 | April
2024-04-16 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 235711 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP | Reviewed | 1. Daily standup 2. Discussion wtih Dillan related to issue on AVM-18 3 Worked on AVM-12 and AVM-21. 4. Deployment and testing of AVM-12 and AVM-21 | Not submitted | 4 | April
2024-04-17 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236326 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | 1. Daily standup 2. Show Me wtih Dillan and Khonani for AVM-12 and AVM-21 3 Worked on AVM-2 4. Discussion review and deployment of AVM-48 and AVM-49 with Toro | Not submitted | 4 | April
2024-04-18 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236894 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 7.75 | 7:45 | 697.5 |  |  |  | GBP | Reviewed | 1. Daily standup 2. Show Me wtih Dillan for AVM-2. Deployment to QA and testing. 3 Worked on AVM-14 4. Discussion review and deployment of AVM-49 with Toro | Not submitted | 4 | April
2024-04-19 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 237730 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 |  |  |  | GBP | Reviewed | 1. daily standup 2. Worked on AVM-14 3. Deployment and testing of AVM-14 4. Show me AVM-14 with Dillan | Not submitted | 4 | April
2024-04-22 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 238037 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 5.5 | 5:30 | 0 |  |  |  | GBP | Reviewed | 1. Daily standup 2. Worked on AVM-52 deployment and testing 3. Worked on apex test classes and deployment to qa 4. Discussion with Dillan about Tenancy End Date on Tenancy record. | Not submitted | 4 | April
2024-04-24 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 239612 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8 | 8:00 | 720 |  |  |  | GBP | Reviewed | 1. Discussion with Sam about AVM-14 and AVM-15 2. Daily standup 3. Worked on story AVM-15 4. Axis & Void Management Report / Data Sharing for Day 1 5. Axis Update and Plan | Not submitted | 4 | April
2024-04-25 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 240109 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 9 | 9:00 | 810 |  |  |  | GBP | Reviewed | 1. Daily standup 2. AVM-15 testing and deployment to qa environment 3. UAT deployment and pre-post deployment steps and configuration 4. Worked on deployment issues - Key Location - Axis Voids permission issue 5. UAT deployment issue - creating EoT from Unit record and default values 6. UAT deployment issue - closing Confirm Notice task 7. UAT deployment issue - creating EoT from Unit record and closed lost opps | Not submitted | 4 | April
2024-04-26 | Anjali Salecha | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 240678 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP | Reviewed | 1. Daily standup 2. worked on AVM-55 deployment to qa and uat. Testing. 3. Discussion with Khonani about PVI time not populating on EoT. Worked on issue deployment and testing. 4. worked on below issues reported AVM - 57. duplicate heading AVM - 58. link to opp AVM - 59. status - can not be done AVM - 60. Start Date not populated & End Date not calculated AVM - 61. break clause Deployment and testing of above issues | Not submitted | 4 | April
2024-04-02 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230420 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.5 | 2:30 | 0 |  |  |  | GBP | Reviewed | Refinement Standup & Time Report | Not submitted | 4 | April
2024-04-03 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230878 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-04 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231489 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-05 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231615 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Sorting out Jira | Not submitted | 4 | April
2024-04-08 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 232448 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Standup & Time Reports | Not submitted | 4 | April
2024-04-09 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 232768 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-10 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233860 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-11 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 234193 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-12 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 234553 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-15 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 235379 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Standup & Time Report | Not submitted | 4 | April
2024-04-18 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 237566 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-19 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 237567 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-22 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 238279 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Time Report | Not submitted | 4 | April
2024-04-23 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 238781 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed | Standup & refinement | Not submitted | 4 | April
2024-04-24 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 239451 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed | Standup & Plan update | Not submitted | 4 | April
2024-04-25 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 240397 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed | Standup | Not submitted | 4 | April
2024-04-26 | Carami Le Grange | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 240485 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Final Checks | Not submitted | 4 | April
2024-03-27 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 228702 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-28 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 229130 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1.25 | 1:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-04-02 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 230277 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.5 | 2:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-03 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 230934 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.75 | 2:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-04 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 231177 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1.25 | 1:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-05 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 231785 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-08 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232312 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | Stand up & QA planning with Khonani | Not submitted | 4 | April
2024-04-09 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232947 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed | QA on AVM-4 | Not submitted | 4 | April
2024-04-09 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232789 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.5 | 2:30 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-10 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233842 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-10 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233410 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.5 | 2:30 | 0 |  |  |  | GBP | Reviewed | Test case creation for refined user stories | Not submitted | 4 | April
2024-04-11 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233845 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed | QA AVM-3 AVM-4 | Not submitted | 4 | April
2024-04-11 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233848 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-12 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 234451 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-12 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 234335 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 3.5 | 3:30 | 0 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-15 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 235146 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 |  |  |  | GBP | Reviewed | - Show me and QA: AVM-7 AVM-18 AVM-20 - Stand up | Not submitted | 4 | April
2024-04-16 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 235697 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.25 | 3:15 | 292.5 |  |  |  | GBP | Reviewed | QA AVM-18 & AVM-20 | Not submitted | 4 | April
2024-04-17 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236327 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed | AVM-48 AVM-18 QA Ac's | Not submitted | 4 | April
2024-04-18 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236739 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed | AVM-18&AVM20 - final test and Close bug - AVM-2 & AVM36 | Not submitted | 4 | April
2024-04-19 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 237310 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 |  |  |  | GBP | Reviewed | Stand Up QA AVM-14 | Not submitted | 4 | April
2024-04-22 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 238053 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 4.25 | 4:15 | 382.5 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-23 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 238744 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-24 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 239095 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 4.75 | 4:45 | 427.5 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-25 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 239971 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 6.25 | 6:15 | 562.5 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-26 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 240087 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-29 | Dillan Landsberg | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 240869 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP |  | #NAME? | Not submitted | 4 | April
2024-03-27 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 228847 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-28 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 229506 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-04-02 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230154 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1.75 | 1:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-03 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231087 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-03 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231085 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-04 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231086 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-04 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231764 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-05 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231762 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233022 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-08 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233021 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-09 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233010 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-09 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233011 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-10 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233987 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-11 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233993 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-12 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 235011 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-15 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 235137 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-16 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 235799 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-17 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 236433 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-18 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 236964 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-19 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 237773 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-19 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 237557 | EoT Deployment to UAT | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-22 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 238218 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-23 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 238763 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-24 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 239311 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-25 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 240058 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 4.25 | 4:15 | 382.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-26 | Khonani Davhana | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 240400 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-03-28 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230109 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 3.75 | 3:45 | 0 |  |  |  | GBP | Reviewed | Data migration from prod to dev sandbox | Not submitted | 3 | March
2024-04-02 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230092 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.75 | 2:45 | 0 |  |  |  | GBP | Reviewed | Data migration from prod to dev environment | Not submitted | 4 | April
2024-04-03 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230731 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 3 | 3:00 | 0 |  |  |  | GBP | Reviewed | Migrating EOT templates from prod to dev | Not submitted | 4 | April
2024-04-08 | Matthew Cornfield | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 232585 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.75 | 2:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-03-06 | Matthew Pitcairn | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 220375 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1.5 | 1:30 | 0 |  |  |  | GBP | Reviewed | Grainger meeting | Not submitted | 3 | March
2024-03-11 | Matthew Pitcairn | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 222297 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed | Requirements planning | Not submitted | 3 | March
2024-03-13 | Matthew Pitcairn | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 223525 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 220379 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-06 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 220377 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.75 | 1:45 | 157.5 | 210 | 52.5 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 222480 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-13 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 223599 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-25 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 227600 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-03-27 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 228789 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 | 540 | 135 | IN07963 | GBP | Reviewed | .. | Not submitted | 3 | March
2024-03-28 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 229677 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.5 | 2:30 | 225 | 300 | 75 | IN07963 | GBP | Reviewed |  | Not submitted | 3 | March
2024-04-01 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 230320 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-02 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 230323 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.75 | 3:45 | 337.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-03 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 230327 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-04 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 231189 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-05 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 231856 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 4.5 | 4:30 | 405 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-09 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 233018 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-10 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 233629 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-11 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 234324 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-12 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 234504 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-15 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 235220 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-16 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 235869 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-17 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 236458 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-19 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 237421 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-22 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 238268 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-23 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 238842 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-24 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 239304 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-25 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 239301 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-26 | Nikki Papenfus | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Andrew Pollock | Delivery | 240487 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-15 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 235369 | EoT Deployment to UAT | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-16 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 235701 | EoT Deployment to UAT | Billable timecode | Standard Timecode | 90 | 8.5 | 8:30 | 765 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-18 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236839 | EoT Deployment to UAT | Billable timecode | Standard Timecode | 90 | 5 | 5:00 | 450 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-04-19 | Sachin Deshmukh | Hourly | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 237358 | EoT Deployment to UAT | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed | #NAME? | Not submitted | 4 | April
2024-03-06 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 222230 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 | 180 | 45 | IN07963 | GBP | Reviewed | User story review & discussion | Not submitted | 3 | March
2024-03-11 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 223051 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 | 120 | 30 | IN07963 | GBP | Reviewed | Requirments gathering session with Jaic Jacob Scott | Not submitted | 3 | March
2024-04-02 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231445 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP | Reviewed | Daily standup (15 mins) Refinement session (2 hours) | Not submitted | 4 | April
2024-04-03 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231463 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 4 | April
2024-04-04 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231462 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP | Reviewed | Refinement session (1 hour) Daily standup (15 mins) | Not submitted | 4 | April
2024-04-05 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231464 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 4 | April
2024-04-08 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233746 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed | Daily standup (15 mins) | Not submitted | 4 | April
2024-04-09 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233747 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP | Reviewed | Daily standup (15 mins) Refinement session (1 hour) Environment refresh planning (1 hour) | Not submitted | 4 | April
2024-04-11 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 234828 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed | Daily standup (15 mins) Dev review with Anjali (30 mins) | Not submitted | 4 | April
2024-04-24 | Sam Duncan | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 240654 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed | Meeting with Axis to confirm report requirements | Not submitted | 4 | April
2024-03-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 228823 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 | 30 | 7.5 | IN07963 | GBP | Reviewed | stand up | Not submitted | 3 | March
2024-03-27 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 228824 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed | project prep | Not submitted | 3 | March
2024-03-28 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 229552 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 1 | 1:00 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 3 | March
2024-04-02 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230406 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-03 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 230870 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-04 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231545 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-05 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 231550 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-08 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 232523 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-09 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233121 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-09 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233128 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.5 | 0:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-10 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 233820 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-11 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 234262 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-12 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 234429 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-15 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 235323 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-16 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 235995 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-17 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 236706 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.5 | 0:30 | 45 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-18 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 237124 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-19 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 237710 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-22 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 238352 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-23 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 239021 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1 | 1:00 | 90 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-24 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 239575 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-25 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 240338 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.75 | 0:45 | 67.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-26 | Shaun Barrett | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Custom Software | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny |  | Delivery | 240368 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.5 | 1:30 | 135 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-03-27 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 229343 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2 | 2:00 | 0 |  |  |  | GBP | Reviewed | Reviewing User Stories | Not submitted | 3 | March
2024-03-28 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 229342 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 3 | 3:00 | 0 |  |  |  | GBP | Reviewed | Axis Void Stand Up Refinement Stories Review | Not submitted | 3 | March
2024-04-02 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232225 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2.25 | 2:15 | 202.5 |  |  |  | GBP | Reviewed | Refinement Stand Up | Not submitted | 4 | April
2024-04-03 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232229 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-04 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232231 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 1.25 | 1:15 | 112.5 |  |  |  | GBP | Reviewed | Refinement Stand Up | Not submitted | 4 | April
2024-04-05 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 232236 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 0.25 | 0:15 | 22.5 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-08 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233901 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 7 | 7:00 | 0 |  |  |  | GBP | Reviewed | AVM-16 Meeting with Sam Stand Up | Not submitted | 4 | April
2024-04-09 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233902 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 6.25 | 6:15 | 0 |  |  |  | GBP | Reviewed | Refinement Catch Up with Tapiwa Standup AVM-16 | Not submitted | 4 | April
2024-04-10 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233904 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 |  |  |  | GBP | Reviewed | AVM-1 | Not submitted | 4 | April
2024-04-10 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233903 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 2.25 | 2:15 | 0 |  |  |  | GBP | Reviewed | Stand Up Dynamic Label Research | Not submitted | 4 | April
2024-04-11 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233910 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3.5 | 3:30 | 315 |  |  |  | GBP | Reviewed | Approach Review with Anjali Dev Review with Anjali AVM-1 & AVM-8 | Not submitted | 4 | April
2024-04-11 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 233905 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 3.5 | 3:30 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-12 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 234940 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 3 | 3:00 | 270 |  |  |  | GBP | Reviewed | Show Me & AVM-1 & AVM-8 | Not submitted | 4 | April
2024-04-12 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 234930 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-15 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236542 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 5.75 | 5:45 | 517.5 |  |  |  | GBP | Reviewed | AVM 21 | Not submitted | 4 | April
2024-04-15 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236359 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-16 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236538 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-17 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236544 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 6 | 6:00 | 540 |  |  |  | GBP | Reviewed | Fixing bug 48 & 49 | Not submitted | 4 | April
2024-04-17 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 236543 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-18 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 237110 | Delivery (Billable) | Billable timecode | Standard Timecode | 90 | 2 | 2:00 | 180 |  |  |  | GBP | Reviewed | Debugging and reviewing bug with Anjali and Khonani | Not submitted | 4 | April
2024-04-18 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 237109 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-19 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 237927 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-22 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 238325 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-23 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 239100 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.75 | 0:45 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-24 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 240066 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-25 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 240069 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April
2024-04-26 | Tafadzwa Toro | Salaried / Fixed | Open Box Software (Pty) Ltd (Open Box SA) | Salesforce | SA | Grainger PLC | OB-000599 | Axis Void Process (T&M) | Billable | Open Box Software (Pty) Ltd (Open Box SA) | Shaun Barrett | Brendan Canny | Sam Duncan | Delivery | 240824 | Delivery (non-billable) @ $0.00 | Non-billable timecode | Standard Timecode | 0 | 0.25 | 0:15 | 0 |  |  |  | GBP | Reviewed |  | Not submitted | 4 | April